## current_iteration
Id | WorkItemType | Parent | Title | Description | Tags | ValueArea | BusinessValue | AssignedTo | State | CreatedDate | ChangedDate | AreaPath | IterationPath | Operation | Region | Planned
1007 | Product Backlog Item |  | GViewer: Add Functionality to Autopopulate Print Templates | <p>Requestor: John K</p><p>This functionality was lost when G.Viewer moved from Silver Light to Geocortex.</p> | HOU | GViewer | 21 | Christopher Thomas | Done | 2020-09-30T13:47:58.18Z | 2021-02-18T17:14:30.063Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
1020 | Product Backlog Item | 1233 | Create Conduit Manager Data Extraction Tool | <p>Requestor: Kathy Holtz &amp; MUG Engineering</p><p>HD 523673</p><p>A tool/command needs to be created to extract out conduit manager information that is stored in the DUCTBANKCCONFIGURATION field within MUG_UGLinearStructure_ln. This is a BLOB field that Schneider has said the only way to extract that information is through custom code. </p><p>Mary has C# projects that the vendor provided that should be helpful. </p> | ELECTRIC; HOU | Data Extraction | 40 | C_Varalakshmi Srinivasan | Done | 2019-10-17T13:02:55.967Z | 2021-01-25T14:33:39.263Z | CNP.GIS | CNP.GIS\Sprint 21.01-A | ELECTRIC
2548 | Product Backlog Item |  | Deploy Outage Reporting to Production | Test website is completed.&nbsp;<div><br></div><div>To deploy it to the production:&nbsp;</div><div><ul style="margin-top:0in;"> <li class=MsoListParagraph style="margin-left:0in;"><span style="">IT: Change to be made on NetScalar to allow BotDetect.ashx</span></li> <li class=MsoListParagraph style="margin-left:0in;"><span style="">IT:&nbsp;Add task for Cregg Hardwick about moving IVR WebService to PROD, in our change ticket</span></li> <li class=MsoListParagraph style="margin-left:0in;"><span style="">IT:&nbsp;Open IVRWebService folder to public</span></li> </ul><br></div> | HOU | Outage | 40 | Saud Ahmad | Done | 2020-10-25T22:45:39.207Z | 2021-01-17T15:48:14.4Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
2904 | Task | 3291 | EIP - Defect 775 - Gas Contract Labor CU Data - Update/Validate remaining CUs for Gas Labor Contract Items |  |  |  |  | Darren Damman | Done | 2020-11-10T15:12:27.643Z | 2021-01-12T16:42:58.47Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3029 | Task | 3291 | EIP - Defect 775 - Gas Contract Labor CU Data - Create Unique Crew Types and send to Nat |  |  |  |  | Darren Damman | Done | 2020-11-23T15:18:55.763Z | 2021-01-12T16:43:01.837Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3113 | Product Backlog Item |  | Include zipped GDB copy into CNPMIMSReplicaCopy | <div><span style="background-color:rgb(255, 255, 0);">To be completed by Jan 18th</span><br><ul><li>The copy trigger should be the same as the GDB copy</li><li>Change xcopy to RoboCopy&nbsp;</li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Done | 2020-12-03T13:07:44.637Z | 2021-01-27T19:50:41.033Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  | INOH
3115 | Task | 3113 | Include the zipped GDB into the copy process | <ul style="box-sizing:border-box;padding:0px 0px 0px 40px;outline:none;"><li style="box-sizing:border-box;">The copy trigger should be the same as the GDB copy</li></ul><br> |  |  |  | Hanh Tran | Done | 2020-12-03T13:30:27.753Z | 2021-01-13T14:25:44.887Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3116 | Task | 3113 | Change xcopy to RoboCopy |  |  |  |  | Hanh Tran | Done | 2020-12-03T13:30:37.787Z | 2021-01-13T14:25:43.223Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3117 | Task | 3114 | Change the config file to include multiple servers |  |  |  |  | Hanh Tran | Done | 2020-12-03T13:31:50.617Z | 2021-01-14T14:26:42.727Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3114 | Product Backlog Item |  | Allow multiple Fileservers to download the MIMSReplica | <div><span style="background-color:rgb(255, 255, 0);display:inline !important;">To be completed by Jan 18th</span><br></div><div>MIMSReplicaCopy copies the replica files from one file server. This is for the users to download data for GO!Sync.&nbsp;</div><div><ul><li>Change the config file to accommodate multiple download sources.&nbsp;</li><li>Add UI to select which file server they download files from.&nbsp;</li><li>Download one selected fileserver to the local drive&nbsp;&nbsp;<br></li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Started | 2020-12-03T13:12:50.887Z | 2021-03-10T14:33:13.913Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3120 | Task | 3114 | Change xcopy to RoboCopy |  |  |  |  | Hanh Tran | Done | 2020-12-03T13:45:14.613Z | 2021-01-15T14:28:00.75Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3177 | Task | 1020 | Create a test tool and check the output report |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2020-12-08T16:25:23.57Z | 2021-01-14T14:16:32.83Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3230 | Product Backlog Item |  | GISLatLongWebService: Fix 'Error: Help' |  | HOU | SAP-GIS | 23 | Christopher Thomas | Done | 2020-12-13T22:33:16.473Z | 2021-01-14T14:28:43.667Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3258 | Product Backlog Item |  | EIP - Functional SWAT Testing and DINOQ Updates |  | EIP; INOH | EIP | 50 |  | Done | 2020-12-17T14:19:31.44Z | 2021-01-28T00:22:00.97Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  | INOH
3273 | Product Backlog Item |  | Data Model: Consolidate Transmission Data btw GIS and Planning | <div>Planning and GIS have very different data model of transmission data. Need to consolidate them into one.&nbsp;</div><div><br></div><div><b>Originated from&nbsp;</b></div><div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;"><span style="box-sizing:border-box;color:rgb(70, 130, 180);font-family:Verdana;font-size:12px;font-weight:700;text-align:start;display:inline !important;">HD0000524600</span><br style="box-sizing:border-box;"></span></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;"><span style="box-sizing:border-box;color:rgb(70, 130, 180);font-family:Verdana;font-size:12px;font-weight:700;text-align:start;display:inline !important;"><br style="box-sizing:border-box;"></span></span></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;">we will need an automated task set up to pull data, on a recurring basis, from Houston electric and place on an FTP site for<span>&nbsp;</span><span style="box-sizing:border-box;display:inline !important;">IBM<span style="box-sizing:border-box;">&nbsp;</span></span>to get. Information in this extract should include (with limited fields included):</span><br style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;"><ul style="box-sizing:border-box;padding:0px 0px 0px 40px;"><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;">Transmission electric lines</span></li><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;">Overhead Circuit lines</span></li><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;">Overhead Primary lines</span></li><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;">Pole Points</span></li><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;">Switches</span></li></ul></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;">IBM Upload Site:</span><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;"><ul style="box-sizing:border-box;padding:0px 0px 0px 40px;"><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;"><span style="box-sizing:border-box;display:inline !important;">Production - \\ecdcfscl4vs9\CORP9_SHARE\GIS\IBM</span></span></li><li style="box-sizing:border-box;"><span style="box-sizing:border-box;font-family:verdana, tahoma, helvetica;font-size:13.3333px;text-align:left;display:inline !important;"><span style="box-sizing:border-box;display:inline !important;">Test -<span>&nbsp;</span><a href="file://ecdcfscl4vs9/CORP9_SHARE/GIS/IBMTest" style="box-sizing:border-box;text-decoration:underline;cursor:pointer;">\\ecdcfscl4vs9\CORP9_SHARE\GIS\IBMTest</a></span></span></li></ul></div></div><div><br></div> | HOU | Business | 29 | William Robertson Jr | Done | 2020-12-21T14:56:20.377Z | 2021-01-19T14:24:22.16Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3277 | Product Backlog Item |  | Production Items: Duplicate Meter Numbers | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">There are around <b><span style="background:silver;">53</span> </b>meters that are associated with 2 different ESIID/GLN. Please see the attached file. Looks like a data issue. Please look into this issue</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88786262</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88265001</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92488840</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92172650</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92942935</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I79002766</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92475723</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I89686307</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I90906554</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92929409</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I64101393</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I63564751</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92481915</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I90865123</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I65711555</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92360940</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I64720638</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88342808</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92410208</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92926476</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I60793835</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92927603</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92119387</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I64657787</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92054996</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92419098</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92050124</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I89409640</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88043480</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92377501</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I89481577</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92471608</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I60932288</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88050573</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I87585074</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92237232</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88295627</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92148198</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92955908</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92469569</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92458092</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I88518588</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I63083709</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I87036479</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92021334</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I78496881</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92086061</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92389762</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I63556766</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I89657668</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I92485703</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I62245506</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I65557512</p><br></div> | HOU | SAP-GIS | 20 | Chen Liang | Done | 2020-12-28T14:35:43.76Z | 2021-01-15T14:31:45.37Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3279 | Task | 3258 | Update DINOT2 and DINOQ with new Subtypes needed for linear calculations |  |  |  |  | Kelsey Mobley | Done | 2020-12-28T15:13:47.837Z | 2021-01-15T21:18:02.033Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3288 | Product Backlog Item |  | WOTS: Migrate WOTS-FileNET Interface |  | HOU | WOTS | 30 | Aaron Miller | Done | 2020-12-29T13:57:03.83Z | 2021-02-01T14:55:40.427Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3289 | Product Backlog Item |  | WOTS: Migrate WOTS-FileNET SO Interface |  | HOU | WOTS | 30 | Subhankar, C_Baidya X | Done | 2020-12-29T13:57:43.36Z | 2021-01-13T15:09:37.35Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3291 | Product Backlog Item |  | EIP - CU Data Updates |  | EIP; INOH | EIP | 50 | Darren Damman | Done | 2020-12-29T20:33:32.773Z | 2021-01-28T00:21:31.463Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  | INOH
3292 | Task | 3291 | Defects 836 & 939 - Update Identified CUs missing Materials | <div><div style="box-sizing:border-box;">Alex has identified that these missing materials were a result of the Materials not being migrated by supply chain.&nbsp; We will need to do a CU data review to see what is missing.&nbsp;</div><div style="box-sizing:border-box;"><br></div><div style="box-sizing:border-box;">Tracer Wire Material is missing on some pipeline CUs.&nbsp; &nbsp;Investigate and reconcile.</div><div style="box-sizing:border-box;outline:none;"><span style="box-sizing:border-box;outline:none;">&nbsp;Some instances, a pipe example, the tracer wire material referenced in Maximo is not on the CU in ArcFM. 60204102.&nbsp; I imagine that we need to do a global reconcile at some point anyways, and Alex may already be tracking this.&nbsp;</span></div><br></div> |  |  |  | Darren Damman | Done | 2020-12-29T20:35:24.843Z | 2021-01-18T18:02:28.89Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3293 | Task | 3291 | EIP - Defect 862 - Update Non-Asset CUs missing costs (Sand) | <div>Review Non-Asset CUs and identify missing information<br></div> |  |  |  | Darren Damman | Done | 2020-12-29T20:35:43.77Z | 2021-01-12T21:37:11.537Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3294 | Task | 3291 | EIP Defect 1004 - Work with CU Administrators to update affected CUs | <div><span style="box-sizing:border-box;">We have found a subset of CUs for Gas and Electric that seem to have the materials duplicated on them. &nbsp;The ArcFM team needs to do a global reconcile of this information in the Mock Load 4 data to ensure this issue is not carried forward in the UAT environment. &nbsp;EAI does not support material calculations when material nodes are duplicated on a CU. &nbsp;If additional material is needed, then the material quantity on the CU needs to be updated accordingly in the CU Admin Tool.<span>&nbsp;</span><br style="box-sizing:border-box;"></span><div style="box-sizing:border-box;"><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;">Gas Example = CU 71706800<br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;"><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;">Electric Example = CU 0925025<br style="box-sizing:border-box;"></div><span style="box-sizing:border-box;"></span><br><br></div> |  |  |  | Darren Damman | Done | 2020-12-29T20:37:16.69Z | 2021-01-12T21:37:09.273Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3296 | Task | 3258 | Troubleshoot issue with Process Framework in DINOQ | <div>Process Framework will not open in DINOQ.&nbsp; Also, may need to reload the workflow from DINOT2 so we can perform testing.&nbsp;</div> |  |  |  | Kelsey Mobley | Done | 2020-12-29T20:50:12.093Z | 2021-01-05T16:15:47.54Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3297 | Task | 3258 | Configure Gas Service QC rule in DINOQ |  |  |  |  | Kelsey Mobley | Done | 2020-12-29T20:50:47.677Z | 2021-01-06T21:19:14.377Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3298 | Task | 3258 | Run E2E Design in DINOQ |  |  |  |  | Bradley Painter | Done | 2020-12-29T20:51:07.33Z | 2021-01-11T23:25:18.607Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3299 | Task | 3258 | Update Process Framework Cost Factor Tables | <div>Update Process Framework Cost Factor and Cost Factory Type Tables with new info based on Domain changes that were cleaned up in DINOQ</div> |  |  |  | Kelsey Mobley | Done | 2020-12-29T20:51:47.47Z | 2021-01-11T15:08:25.1Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3300 | Task | 3258 | Add New Users to DINOQ - Will Need new SAP Employee Numbers | <div>Users that need CU Administration</div><div>Andrew Danhauer</div><div>Josh Davis</div><div>Ed Cooper</div><div>Jon Eastham</div><div><br></div><div>Users that need Access to DINOQ for testing</div><div>TBD</div><div><br></div><div>Also need the SAP employee numbers that were loaded into UAT environment</div><div><br></div><div><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"><img src="https://dev.azure.com/centerpoint-GIS/dd41b79d-1665-4c55-9863-175bd4cd1d78/_apis/wit/attachments/38926a71-c386-4f6e-baad-8df3994c0ba0?fileName=image.png" alt=Image></span><br></div> |  |  |  | Kelsey Mobley | Done | 2020-12-29T20:54:06.49Z | 2021-01-12T14:06:10.32Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3301 | Task | 3258 | Capture Needed Dry Run QC Tasks |  |  |  |  | Bradley Painter | Done | 2020-12-29T20:58:34.593Z | 2021-01-15T21:18:05.973Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3302 | Task | 3258 | Validate Pole by Circuit Functionality |  |  |  |  | Bradley Painter | Done | 2020-12-29T20:59:09.997Z | 2021-01-14T23:59:51.713Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3303 | Task | 3258 | Validate Circuit Functional Location Data Load |  |  |  |  | Bradley Painter | Done | 2020-12-29T21:01:39.26Z | 2021-01-11T15:03:24.727Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3304 | Task | 3258 | Test new CU Consolidation Tools Installer from SE - V.10.22 |  |  |  |  | Bradley Painter | Done | 2021-01-04T20:39:57.873Z | 2021-01-07T21:43:46.893Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3307 | Product Backlog Item |  | Production Issue: Missing or NULL GLNs | <div><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;">Divi, Tirumala Rao X (Contractor) &lt;tirumalarao.divi@centerpointenergy.com&gt;<br></div><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;"><br></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi Saud,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">We have noticed below GISTOSAPRT transactions are failed in validation at EAI due to received null for GLN code. could you please review and do the needful. </p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">TRAN_SEQ_ID&nbsp; : 20201214020212000853004033690036526201</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">ESI_ID : 1008901020900362110109</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&lt;NetworkSyncPayload xmlns:aia=&quot;<a href="https://nam04.safelinks.protection.outlook.com/?url=http://www.oracle.com/XSL/Transform/java/oracle.apps.aia.core.xpath.AIAFunctions&amp;data=04%7c01%7cchen.liang%40centerpointenergy.com%7ce2076159251a48c3dd7108d8a29e6d07%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637438148643676129%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=kxvxvL4CHZE24urEPUbBSY7Lk4FkDu8wqediKE/ukQ4%3D&amp;reserved=0">http://www.oracle.com/XSL/Transform/java/oracle.apps.aia.core.xpath.AIAFunctions</a>&quot; xmlns:ns2=&quot;<a href="https://nam04.safelinks.protection.outlook.com/?url=http://com.cnp.eai/NetworkSyncPayload&amp;data=04%7c01%7cchen.liang%40centerpointenergy.com%7ce2076159251a48c3dd7108d8a29e6d07%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637438148643686126%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=gu8NytgdamIofIK/5QQQVTAJcyxcoA7CcsvQUnUFVuA%3D&amp;reserved=0">http://com.cnp.eai/NetworkSyncPayload</a>&quot; xmlns=&quot;<a href="https://nam04.safelinks.protection.outlook.com/?url=http://com.cnp.eai/NetworkSyncPayload&amp;data=04%7c01%7cchen.liang%40centerpointenergy.com%7ce2076159251a48c3dd7108d8a29e6d07%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637438148643696115%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=uAwM3aBMQn2TwT4CT/NZk5tcb24erDjBAtVkvTXU%2Bm0%3D&amp;reserved=0">http://com.cnp.eai/NetworkSyncPayload</a>&quot;&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:ESI_ID&gt;1008901020900362110109&lt;/ns2:ESI_ID&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:MeterNumber&gt;I64668806&lt;/ns2:MeterNumber&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:ServiceCenter&gt;BEL&lt;/ns2:ServiceCenter&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:ServiceCenterCode&gt;1013&lt;/ns2:ServiceCenterCode&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; <span style="background:yellow;">&lt;ns2:GLN&gt;&amp;lt;Null&gt;&lt;/ns2:GLN&gt;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:Latitude&gt;29.797091&lt;/ns2:Latitude&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:Longitude&gt;-95.408845&lt;/ns2:Longitude&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:SubArea&gt;BE01XEA05X&lt;/ns2:SubArea&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:Substation/&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:Circuit/&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp; &nbsp;&lt;ns2:Section/&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:LineFuseID/&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:OrderNum/&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp; &lt;ns2:GISTranID&gt;0&lt;/ns2:GISTranID&gt;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&lt;/NetworkSyncPayload&gt;</p><br></div> | HOU | SAP-GIS | 40 | Saud Ahmad | Done | 2021-01-04T23:31:00.22Z | 2021-01-13T15:07:05.267Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3308 | Product Backlog Item |  | Data Model: add fields to the WOTS monthly_problem_orders table | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">we need to add two column to the monthly_problem_orders table. </p><ul style="margin-bottom:0in;margin-top:0in;"> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span>alter table monthly_problem_orders add (OH NUMBER(6,0), IND NUMBER(6,0));</span></li></ul><br></div><div>----&nbsp;</div><div><span style="font-family:Calibri, sans-serif;font-size:14.6667px;display:inline !important;">Below is ready for deployment</span><br></div><div><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"><ul><li><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">The new version of the daily_month_problem_orders scheduled task&nbsp;</span></li><li><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">GIS Executive Dashboard&nbsp;</span></li></ul></span></div><div><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"><br></span></div> | HOU | WOTS |  | Chen Liang | Done | 2021-01-04T23:35:02.11Z | 2021-01-14T22:27:18.423Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3309 | Product Backlog Item |  | WOTS: Verify Interfaces - Turnarounds | <ul><li><span style="">Completed QC Turnaround</span><br></li><li>Non-Completed QC Turnaround<br></li><li style="box-sizing:border-box;">Completed Turnaround<br style="box-sizing:border-box;"></li><li style="box-sizing:border-box;"><span style="">Non-Completed Turnaround</span></li></ul> | HOU; WOTS | WOTS | 30 | C_Varalakshmi Srinivasan | Done | 2021-01-04T23:42:51.08Z | 2021-01-11T14:27:13.68Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3310 | Task | 3113 | Review the existing scripts |  |  |  |  | Hanh Tran | Done | 2021-01-05T14:16:37.38Z | 2021-01-11T14:25:31.193Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3311 | Task | 3309 | Verify the difference in dates |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-05T14:20:43.21Z | 2021-01-07T14:17:13.003Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3312 | Task | 3307 | Verify with Karen on the missing GLNs in versioned tables | <div>Will follow up with Karen. A course could only be decided after we find out where the fix lies.<br></div> |  |  |  | Saud Ahmad | Done | 2021-01-05T14:22:46.557Z | 2021-01-12T14:23:39.75Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3313 | Task | 3230 | Capture exception and make error more descriptive | <div>Update GISLatLong web service code<br></div> |  |  |  | Christopher Thomas | Done | 2021-01-05T14:24:37.503Z | 2021-01-13T14:23:29.98Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3314 | Task | 3306 | 1. Outage RED Production Layers are not turned on by default |  |  |  |  | Saud Ahmad | Done | 2021-01-05T14:52:22.78Z | 2021-01-07T14:18:48Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3306 | Product Backlog Item |  | Migrate RED Approval to HTML5 | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Jacob:&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Here are my review comments.</p><ol style="margin-bottom:0in;margin-top:0in;" start=1 type=1> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Outage RED Production Layers are not turned on by default</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">“Push to PROD” button missing within Outage RED widget.</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Change “Red” to “RED”</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Unable to test due to lack of Substation and Circuit Restoration data</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Legend Widget should be always on. May be split half way thru between Layers and Legend widgets?</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Report widget not working correctly. Outage numbers are not showing by City.</span></li></ol><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I will setup a meeting to go over these in detail.</p><br></div> | HOU | Outage | 40 | Saud Ahmad | Done | 2021-01-04T23:18:37.827Z | 2021-03-10T17:19:45.677Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3315 | Task | 3306 | Change “Red” to “RED” | <div>Jacob will point where to make that change</div> |  |  |  | Saud Ahmad | Done | 2021-01-05T14:53:16.147Z | 2021-01-11T14:19:46.373Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3317 | Task | 3309 | Fix any issues found in verification |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-05T14:55:32.227Z | 2021-01-08T14:15:49.587Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3319 | Task | 3306 | Legend Widget should be always on. May be split half way thru between Layers and Legend widgets? | <div>Will explore the best option to address this<br></div> |  |  |  | Saud Ahmad | Done | 2021-01-05T14:57:32.383Z | 2021-01-08T14:17:26.22Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3321 | Task | 3289 | Migrate code from VB to C# |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-05T14:58:25.193Z | 2021-01-11T14:17:18.247Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3323 | Task | 3289 | Unit test |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-05T14:59:01.913Z | 2021-01-13T14:17:07.95Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3327 | Task | 3288 | Review existing code |  |  |  |  | Aaron Miller | Done | 2021-01-05T15:02:33.093Z | 2021-01-08T14:17:04.607Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3328 | Task | 3277 | Identify the TEMP records and move them into TSAW table |  |  |  |  | Goddard, Susan C. | Done | 2021-01-05T15:03:00.823Z | 2021-01-12T14:34:38.1Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3332 | Task | 3277 | Gather records with retired meters and manually remove them |  |  |  |  | Goddard, Susan C. | Done | 2021-01-05T15:03:44.2Z | 2021-01-12T14:34:20.4Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3335 | Task | 3277 | Cross-check with EAI to verify records with different ESIIDs |  |  |  |  | Chen Liang | Done | 2021-01-05T15:04:32.627Z | 2021-01-15T14:26:02.54Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3337 | Task | 3273 | Determine if we will replace the Transmission data with the data from Planning. |  |  |  |  | William Robertson Jr | Done | 2021-01-05T15:05:56.677Z | 2021-01-07T14:19:21.833Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3339 | Task | 3289 | Review existing code |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-05T15:07:40.053Z | 2021-01-06T15:04:02.98Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3341 | Product Backlog Item |  | Verify AMS web service (migrated to C#) |  | HOU | System |  | Aaron Miller | Done | 2021-01-05T15:09:42.537Z | 2021-01-12T14:38:31.81Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3344 | Product Backlog Item |  | Populate the SAP rejection reason into Analytics_Incremental_DB table |  | HOU | SAP-GIS |  | Saud Ahmad | Done | 2021-01-05T15:15:52.63Z | 2021-01-13T15:07:11.58Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3345 | Task | 3230 | Update Test GISLatLongWebService |  |  |  |  | Christopher Thomas | Done | 2021-01-05T15:17:12.787Z | 2021-01-13T14:23:35.297Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3347 | Task | 3309 | Verify Excels |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-05T15:19:01.33Z | 2021-01-11T14:16:45.4Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3349 | Task | 3341 | Investigate the incorrect query |  |  |  |  | Aaron Miller | Done | 2021-01-05T15:28:08.823Z | 2021-01-12T14:17:44.323Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3351 | Task | 3344 | Look into why the reason is not popoulated in production db |  |  |  |  | Saud Ahmad | Done | 2021-01-05T15:35:45.333Z | 2021-01-06T15:06:55.067Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3354 | Product Backlog Item |  | Production Issue: GIS-SAP interfaces cause performance issue on Metro db | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Saud,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">You have three tasks that were created in October that seem to be killing the Metro performance when they run and after they complete.&nbsp; Can you work with Rakesh and Nasir to see if this issue can be resolved?</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">GIS_to_SAP_Nightly_ACK</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">GIS_SAP_WeeklyFullSync</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">GIS_toCIS_Interf</p><br> | HOU; UNPLANNED | System |  | Saud Ahmad | Done | 2021-01-06T02:06:39.43Z | 2021-01-12T14:15:15.62Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  |  | UNPLANNED
3355 | Task | 3354 | Meet with Nasir and Rakesh |  |  |  |  | Saud Ahmad | Done | 2021-01-06T15:01:49.58Z | 2021-01-08T14:23:31.903Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3356 | Task | 3344 | Look into status not changing for 1 missing file |  |  |  |  | Saud Ahmad | Done | 2021-01-06T15:07:21.67Z | 2021-01-08T14:19:53.473Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3358 | Product Backlog Item |  | EIP - Review SAP/Premise Data Load File Errors for EIP | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Brad, can you review the attached results? The prem/service numbers that are listed in this output are ones that I could not update due to it not being on UCRSERV. Last time it was the south services you reviewed. This time it’s all 3 companies for the dry run 0.</p><br></div> | INOH | EIP | 20 | Bradley Painter | Done | 2021-01-07T14:13:19.953Z | 2021-01-28T00:22:39.107Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  | INOH
3359 | Task | 3358 | Compare discrepancies and report findings to EIP |  |  |  |  | Bradley Painter | Done | 2021-01-07T14:14:36.013Z | 2021-01-13T14:23:05.47Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3360 | Task | 3273 | Load data into production database |  |  |  |  | William Robertson Jr | Done | 2021-01-07T14:19:32.533Z | 2021-01-12T14:25:09.62Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3361 | Product Backlog Item |  | Add Texarkana TRRC Polys to ETX | <div><div align=center style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-align:center;"><span style="font-size:10.0pt;font-family:&quot;Georgia&quot;,serif;"><hr size=2 width="100%" align=center></span></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:13.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:#000066;">Help Desk Ticket #HD0000524772</span><span style="font-size:10.0pt;font-family:&quot;Georgia&quot;,serif;"><br><span style="color:#E60010;">Status: </span>Open<br><span style="color:#E60010;">Assigned to: </span><br><span style="color:#E60010;">Date Opened: </span>1/6/2021 3:22:23 PM EST<br><span style="color:#E60010;">Date Closed: </span><br><span style="color:#E60010;">Customer: </span>Belinda Walker<br><span style="color:#E60010;">Category: </span>Other<br><br><br><span style="color:#E60010;">Sub Category: Summary: </span>'Where Am I' tool to show TRRC SYS ID </span></p><div align=center style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-align:center;"><span style="font-size:10.0pt;font-family:&quot;Georgia&quot;,serif;"><hr size=2 width="100%" align=center></span></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:10.0pt;font-family:&quot;Georgia&quot;,serif;color:#E60010;">Details: </span><span style="font-size:10.0pt;font-family:&quot;Georgia&quot;,serif;"></span></p><table style=""> <tbody><tr style=""> <td style="padding:.75pt .75pt .75pt .75pt;"> <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Submitted by</p> </td> <td style="padding:.75pt .75pt .75pt .75pt;"> <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Timestamp</p> </td> <td style="padding:.75pt .75pt .75pt .75pt;"> <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Comment or Activity</p> </td> </tr> <tr style=""> <td style="padding:.75pt .75pt .75pt .75pt;"> <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">00229746</p> </td> <td style="padding:.75pt .75pt .75pt .75pt;"> <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">1/6/2021 3:22:23 PM</p> </td> <td style="padding:.75pt .75pt .75pt .75pt;"> <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">There are five TRRC polygons located within the Arkansas database; Is it possible to get these system ids to show up using the 'Where Am I' tool when selecting the area in the ETX database, despite the facilities being in the Arkansas database?<br> <br> RE-346 (311281), WAKE VILLAGE (311354), RE-571 (311282), TEXARKANA TX (311279), &amp; REDWATER (311146)</p> </td> </tr></tbody></table><br></div> | HOU | Business | 20 | William Robertson Jr | Done | 2021-01-07T14:33:36.41Z | 2021-01-11T14:27:16.373Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3362 | Task | 3361 | Export the Features to a FGDB and project to the ETX projection |  |  |  |  | William Robertson Jr | Done | 2021-01-07T15:37:13.487Z | 2021-01-07T15:38:33.053Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3363 | Task | 3361 | Append the features to the TRRC_PY in East Texas. |  |  |  |  | William Robertson Jr | Done | 2021-01-07T15:38:10.7Z | 2021-01-07T15:38:36.54Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3365 | Task | 3307 | Electric DM Researching |  |  |  |  | Saud Ahmad | Done | 2021-01-08T14:19:24.53Z | 2021-01-12T14:23:37.963Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3366 | Task | 3344 | Review Traffic over next few days |  |  |  |  | Saud Ahmad | Done | 2021-01-08T14:20:03.42Z | 2021-01-13T14:20:54.977Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3367 | Task | 3291 | Update Subset of Material Descriptions for new materials - Defect 934 | <div>Purchase Long Text to include IN and FT measurements.&nbsp;</div> |  |  |  | Darren Damman | Done | 2021-01-08T22:18:36.787Z | 2021-01-12T14:06:32.773Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3368 | Task | 3291 | Load new Material Numbers, Costs, and Descriptions into DINOQ for Mock Load 4 Data |  |  |  |  | Darren Damman | Done | 2021-01-08T22:33:45.027Z | 2021-01-12T14:06:29.737Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3374 | Product Backlog Item |  | Add the link of Outage Report to Outage Tracker | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Add the link of of Outage Report at the bottom of the <span style="display:inline !important;">Outage Trakker&nbsp;</span>page.&nbsp;<span style="font-size:11pt;">The popup is configurable. No coding required.</span></p><span></span><p></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"></p><ul><li><span style="font-size:11pt;background-color:rgb(255, 255, 0);">The change needs to be in place in production by 1/13</span></li></ul><p></p> | HOU; UNPLANNED | Outage | 20 | Saud Ahmad | Done | 2021-01-09T03:08:40.537Z | 2021-01-15T14:31:42.437Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  |  | UNPLANNED
3376 | Task | 3341 | Get w/ Varu on some questions |  |  |  |  | Aaron Miller | Done | 2021-01-11T14:17:57.743Z | 2021-01-12T14:17:38.53Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3377 | Task | 3341 | Get w/ Varu on some questions |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-11T14:18:40.03Z | 2021-01-12T14:17:33.423Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3378 | Task | 3374 | Create link on landing page |  |  |  |  | Saud Ahmad | Done | 2021-01-11T14:19:08.77Z | 2021-01-12T14:21:05.737Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3379 | Task | 3258 | Add New Users for CU Admin Tool | <div style="box-sizing:border-box;">Users that need CU Administration</div><div style="box-sizing:border-box;">Andrew Danhauer - I140735</div><div style="box-sizing:border-box;">Josh Davis - I141213</div><div style="box-sizing:border-box;">Ed Cooper - I141014</div><div style="box-sizing:border-box;">Jon Eastham - I141117</div><div style="box-sizing:border-box;">Brad Painter - I141523</div><div style="box-sizing:border-box;">Kelsey Mobley - I141677</div><br> |  |  |  | Kelsey Mobley | Done | 2021-01-11T18:15:02.67Z | 2021-01-12T16:42:44.527Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3381 | Task | 3273 | Change data sources for Transmission Portal Map Service |  |  |  |  | William Robertson Jr | Done | 2021-01-12T12:42:44.693Z | 2021-01-12T14:25:18.8Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3382 | Task | 3288 | Meet with Subhankar to go over differences |  |  |  |  | Aaron Miller | Done | 2021-01-12T14:18:34.52Z | 2021-01-13T14:17:37.26Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3383 | Task | 3288 | Meet with Aaron Miller |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-12T14:19:06.91Z | 2021-01-13T14:17:40.193Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3384 | Task | 3374 | Move to HQ production boxes. Coordinate with Sys Admin. Move on Friday 1/15 |  |  |  |  | Saud Ahmad | Done | 2021-01-12T14:20:53.547Z | 2021-01-15T14:21:30.737Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3385 | Task | 3306 | Meeting with Jacob, Chen, Mary |  |  |  |  | Saud Ahmad | Done | 2021-01-12T14:22:03.76Z | 2021-01-13T14:18:47.03Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3386 | Task | 3307 | Follow up with electric DM for missing GLNS |  |  |  |  | Chen Liang | Done | 2021-01-12T14:23:59.643Z | 2021-01-13T15:06:44.44Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3388 | Task | 3277 | Verify downstream read outs for duplicate records |  |  |  |  | Goddard, Susan C. | Done | 2021-01-12T14:36:19.907Z | 2021-01-14T14:22:00.72Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3389 | Task | 3277 | Verify downstream read outs for duplicate records |  |  |  |  | Hanh Tran | Done | 2021-01-12T14:36:57.677Z | 2021-01-14T14:22:03.15Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3390 | Task | 3277 | Investigate remaining duplicate meters |  |  |  |  | Goddard, Susan C. | Done | 2021-01-12T14:37:26.543Z | 2021-01-14T14:22:53.107Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3391 | Product Backlog Item |  | ArcGIS 10.6.1 Patch Installer | <div>Create an installer for ArcGIS 10.6.1</div> | 10.6.1 | 1061 Migration | 30 | William Robertson Jr | Done | 2021-01-12T17:23:16.45Z | 2021-01-13T15:07:02.277Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3392 | Task | 3391 | Create InstallShield Suite Package installer for 10.6.1 Patches | <div><span>Copied the installer here.</span></div><span><div><br></div><div>J:\GIS Tools and Programs\CNPArcFM 1061\ArcGIS 1061 Patches</div><div><br></div><div><br></div></span> |  |  |  | William Robertson Jr | Done | 2021-01-12T17:25:37.713Z | 2021-01-13T14:22:40.13Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3395 | Task | 3306 | Change Red to RED on heading & Pop-Up |  |  |  |  | Saud Ahmad | Done | 2021-01-12T19:46:02.083Z | 2021-01-15T14:22:25.153Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3396 | Task | 3306 | Reduce Zoom level for circuit & substation |  |  |  |  | Saud Ahmad | Done | 2021-01-12T19:46:48.1Z | 2021-01-13T14:20:12.587Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3406 | Task | 1020 | Create test case |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-14T14:16:50.087Z | 2021-01-15T14:17:28.847Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3407 | Task | 3113 | Zip the GDB |  |  |  |  | Hanh Tran | Done | 2021-01-14T14:26:11.57Z | 2021-01-15T14:27:45.44Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3408 | Task | 3114 | Unzip GDB |  |  |  |  | Hanh Tran | Done | 2021-01-14T14:26:57.36Z | 2021-01-19T14:25:26.62Z | CNP.GIS | CNP.GIS\Sprint 21.01-A