## current_iteration
Id | WorkItemType | Parent | Title | Description | Tags | ValueArea | BusinessValue | AssignedTo | State | CreatedDate | ChangedDate | AreaPath | IterationPath | Operation | Region | Planned
2944 | Product Backlog Item |  | 10.6.1 - Reconcile Email Action Handler |  | INOH | 1061 Migration | 3 | Kelsey Mobley | Done | 2020-11-16T15:25:24.7Z | 2021-02-01T21:24:46.153Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
2946 | Task | 2944 | Kelsey investigate |  |  |  |  | Kelsey Mobley | Done | 2020-11-16T15:27:59.687Z | 2021-01-21T15:07:14.923Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3025 | Product Backlog Item |  | Enable the ServiceXY GP Service to use file geodatabase | <div>Change the config to make the Production ServiceXY GP Service use file geodatabase.&nbsp;<br></div><div><ul><li>This one requires the coordination with Bryan Mappe's team.&nbsp;</li><li>Next maintenance window is Sunday 1-3am.&nbsp;</li></ul></div> | HOU | System | 40 | Christopher Thomas | Done | 2020-11-23T14:41:38.44Z | 2021-02-01T14:29:17.62Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3118 | Task | 3114 | Download the zipped GDB file from a selected file server |  |  |  |  | Hanh Tran | Done | 2020-12-03T13:32:33.07Z | 2021-01-25T14:39:05.557Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3114 | Product Backlog Item |  | Allow multiple Fileservers to download the MIMSReplica | <div><span style="background-color:rgb(255, 255, 0);display:inline !important;">To be completed by Jan 18th</span><br></div><div>MIMSReplicaCopy copies the replica files from one file server. This is for the users to download data for GO!Sync.&nbsp;</div><div><ul><li>Change the config file to accommodate multiple download sources.&nbsp;</li><li>Add UI to select which file server they download files from.&nbsp;</li><li>Download one selected fileserver to the local drive&nbsp;&nbsp;<br></li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Started | 2020-12-03T13:12:50.887Z | 2021-03-10T14:33:13.913Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3256 | Product Backlog Item |  | EIP - Defect 1003 - Enhance EAI to ArcFM interface to send Received and Processed Statuses |  | EIP; INOH | EIP | 1 | Bradley Painter | Done | 2020-12-16T21:39:11.157Z | 2021-02-11T17:45:10.067Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3259 | Product Backlog Item |  | EIP - Enhancement - SAP Equipment Number Monthly Data Report | <div>Send Delta file with SAP Equipment Number, Premise and Service Number</div><div><br></div><div>Need to look at variance between monthly files</div><div>&nbsp;</div><div>Send in CSV</div><div><br></div><div>Load to Sharepoint</div><div><br></div><div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><b>Agenda</b>: Discuss post go-live process for obtaining data changes in GIS and maintaining a sync with Banner. </p><ul style="margin-bottom:0in;margin-top:0in;"> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span>What is the post go-live process for ensuring that data in GIS remains in sync with Banner?</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span>Does GIS have the capability to identify change pointers or records modified after a certain date?</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span>Request to query GIS data changes on a specified frequency (ex. Monthly)</span></li></ul><br></div> | EIP; INOH | EIP | 20 | Bradley Painter | Done | 2020-12-17T17:47:26.753Z | 2021-01-28T00:24:37.15Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3260 | Product Backlog Item |  | EIP - CU Quantity QC Rule and AU Adjustment | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Got it.&nbsp; We would likely build a QC rule for the other fields and update the existing Measured Length AU to round appropriately.</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Thanks,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Brad</p><br></div><div><br></div><div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Yes.&nbsp; But on initial draw the shape length is put in the measured length field through a AU.&nbsp; So this is always a decimal and this is what is being sent if the designer doesn’t update it.&nbsp; So you may have to catch it on the XML for measured length.&nbsp;&nbsp; Or checked in a QA/QC when it is run other than messing with the AU. </p><br></div><div><br></div><div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Andrew, </p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">If you are talking about the actual quantities that are manually input by a designer, we should be able to develop some type of QC rule to catch when non-integer numbers are entered into these fields. </p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Thanks,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Brad</p><br></div><div><br></div><div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Brad,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Can we get a QA/QC in Arcfm to not allow for decimal values in the CU quantities?</p><br></div> | EIP; INOH | EIP | 10 | Kelsey Mobley | Done | 2020-12-17T21:33:03.45Z | 2021-02-01T18:51:21.01Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3261 | Product Backlog Item | 3544 | Database: Delete domains on Deleted and Sold assets (AR) |  | ELECTRIC; HOU | System | 20 | William Robertson Jr | Done | 2020-12-18T14:00:34.277Z | 2021-02-01T20:02:43.283Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | ELECTRIC
3275 | Task | 3256 | Support EAI in testing Status Changes |  |  |  |  | Bradley Painter | Done | 2020-12-21T15:39:08.28Z | 2021-01-22T20:34:22.933Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3295 | Task | 3398 | Defect 918 & 839 - Update CUs with Material Contingencies (E# & G#s) | <div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;"><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi Brad,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I have created this material only in one plant 7001 with 1$ just for testing if this works.</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">But I do believe we have E and G materials with some cost on it. if you can provide me the list of all E and G material with their cost and plants in which they are required. I can go ahead and create them accordingly. I am not able to open <a href="file://SIGENET/GLOBAL/COMMON/damman/ArcFM/costEFGP.txt">G:\COMMON\damman\ArcFM\costEFGP.txt</a><a href="file://gistobin.cnp.int/Shared/adamman/rip/costEFGP.txt">\\gistobin.cnp.int\Shared\adamman\rip\costEFGP.txt</a> which Andrew had sent earlier.</p><br></span></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;"><br></span></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;">Update Contingency Materials with new Material Numbers Provided by Supply Chain<br></span></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;"><br></span></div><div style="box-sizing:border-box;"><span style="box-sizing:border-box;">Material cost not listed for material contingency CUs (see attachments: Pg 19 of first attachment &amp; Pg 29 of second attachment). &nbsp; WO#93257179 &amp; WO#93257213 have examples of material contingencies (&amp; no cost).<br style="box-sizing:border-box;"></span><div style="box-sizing:border-box;">[Also, no cost listed for meters]<br style="box-sizing:border-box;"></div><span style="box-sizing:border-box;"></span><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;"><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;">April McGarrh &lt;amcgarrh&gt;, 11/25/2020: Assiging to ArcFm to look at CU 0199101</div><br></div> |  |  |  | Bradley Painter | Done | 2020-12-29T20:37:56.313Z | 2021-01-21T15:32:29.567Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3305 | Product Backlog Item |  | 10.6.1 - Integrations Touch Point/Validation/Sanity Check | <div>We need to do a quick sanity check that all the integration touchpoints for INOH are ready to go for the end of March cutover activities.&nbsp; &nbsp;If not, we still have a bit of runway but we need to get them up to speed quickly.&nbsp;</div><div><br></div><div>1 - ArcFM Mobile</div><div>2 - Reporting</div><div>3 - 811 Locate Tickets</div><div>4 - AVL</div><div>5 - Banner</div><div>6 - Maximo</div><div>7 - Optimizer</div><div>8 - Synergi</div><div>9 - NMS Team</div><div>10 - OnBase</div><div>11 - Portal - Field and Locators</div> | INOH | 1061 Migration | 50 | Aaron Miller | Done | 2021-01-04T22:14:48.26Z | 2021-02-11T17:45:10.067Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3316 | Task | 3306 | “Push to PROD” button missing within Outage RED widget. | <div>This has to be designed in conjunction with the initial data push into acceptance table<br></div> |  |  |  | Saud Ahmad | Done | 2021-01-05T14:54:45.88Z | 2021-01-22T14:15:20.563Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3306 | Product Backlog Item |  | Migrate RED Approval to HTML5 | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Jacob:&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Here are my review comments.</p><ol style="margin-bottom:0in;margin-top:0in;" start=1 type=1> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Outage RED Production Layers are not turned on by default</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">“Push to PROD” button missing within Outage RED widget.</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Change “Red” to “RED”</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Unable to test due to lack of Substation and Circuit Restoration data</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Legend Widget should be always on. May be split half way thru between Layers and Legend widgets?</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Report widget not working correctly. Outage numbers are not showing by City.</span></li></ol><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I will setup a meeting to go over these in detail.</p><br></div> | HOU | Outage | 40 | Saud Ahmad | Done | 2021-01-04T23:18:37.827Z | 2021-03-10T17:19:45.677Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3322 | Task | 1007 | Create workflow for templates for Houston Electric | <div>Create forms for each template<br></div> |  |  |  | Christopher Thomas | Done | 2021-01-05T14:58:37.227Z | 2021-01-20T14:20:49.657Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
1007 | Product Backlog Item |  | GViewer: Add Functionality to Autopopulate Print Templates | <p>Requestor: John K</p><p>This functionality was lost when G.Viewer moved from Silver Light to Geocortex.</p> | HOU | GViewer | 21 | Christopher Thomas | Done | 2020-09-30T13:47:58.18Z | 2021-02-18T17:14:30.063Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3329 | Task | 3288 | Migrate Code from VB to C# |  |  |  |  | Aaron Miller | Done | 2021-01-05T15:03:10.57Z | 2021-01-29T14:18:07.62Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3288 | Product Backlog Item |  | WOTS: Migrate WOTS-FileNET Interface |  | HOU | WOTS | 30 | Aaron Miller | Done | 2020-12-29T13:57:03.83Z | 2021-02-01T14:55:40.427Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3330 | Task | 3288 | Unit Test |  |  |  |  | Aaron Miller | Done | 2021-01-05T15:03:35.75Z | 2021-02-01T14:17:38.583Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3333 | Task | 1007 | Team discussion on what fields need to be populated | <div>Need to have team meeting about each print template and what we want to Auto Populate<br></div> |  |  |  | Christopher Thomas | Done | 2021-01-05T15:03:56.97Z | 2021-02-01T14:21:31.813Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3336 | Task | 3288 | Code Review |  |  |  |  | Aaron Miller | Done | 2021-01-05T15:04:35.36Z | 2021-01-29T14:18:11.967Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3340 | Task | 1007 | Research if Geocortex can access Active Directory |  |  |  |  | Christopher Thomas | Done | 2021-01-05T15:08:15.407Z | 2021-01-21T14:17:25.163Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3350 | Task | 3288 | Code Review |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-05T15:33:22.85Z | 2021-01-29T14:18:15.31Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3364 | Product Backlog Item |  | EIP - Remove Labor and OH Rates from ArcFM Web Service | <div><span style="font-size:12.0pt;font-family:&quot;Calibri&quot;,sans-serif;color:black;">The finance team is planning to remove an obsolete part of the ArcFM webservices - Labor and OH rates since it is now being handled by EAI. </span><br></div><div><span style="font-size:12.0pt;font-family:&quot;Calibri&quot;,sans-serif;color:black;"><br></span></div><div><span style="font-size:12.0pt;font-family:&quot;Calibri&quot;,sans-serif;color:black;">POC is Jeff Chua</span></div> | EIP; INOH | EIP | 1 | Christopher Thomas | Done | 2021-01-08T14:16:31.49Z | 2021-01-28T00:25:00.98Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3371 | Product Backlog Item |  | 10.6.1 - 10.6.1a SP1 Sanity Check - INOH | <div>Test build on 10.6.1a SP1</div> | INOH | 1061 Migration | 10 | Aaron Miller | Done | 2021-01-09T00:43:25.627Z | 2021-02-01T21:24:40.93Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3387 | Task | 1007 | Research print preview for Houston Electric |  |  |  |  | Christopher Thomas | Done | 2021-01-12T14:28:13.333Z | 2021-01-25T14:20:29.947Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3393 | Task | 3306 | Make the banner style consistent to Outage Tracker | <div>Font and height&nbsp;</div> |  |  |  | Saud Ahmad | Done | 2021-01-12T18:38:14.82Z | 2021-01-20T14:16:41.04Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3394 | Task | 3306 | Fix the bug of substation list not displaying | <div>substation list not displaying sometimes<br></div> |  |  |  | Saud Ahmad | Done | 2021-01-12T18:38:44.6Z | 2021-01-25T14:18:39.38Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3398 | Product Backlog Item |  | EIP - CUs for Material Contingencies Data Updates | <div>This is blocked by Supply Chain.&nbsp; We need the new material numbers to be able to load into DINOQ and update the necessary CUs</div><div><br></div><div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi April,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">In our meeting we reviewed all the items which were listed as missing cost or not available and one of the business person confirmed they do not have any cost concern with those meter materials. </p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><a href="mailto:Brad.Painter@centerpointenergy.com"><span style="font-family:&quot;Calibri&quot;,sans-serif;">@Painter, Bradley</span></a> do you remember the name of the business person who confirmed us nonissue for the materials we reviewed? And regarding E and G material Miriam checked with Michelle on using material with material type ZPLN (i.e. similar to CLBR material) and Michelle had only one concern with it i.e. EAI may have to do some coding similar to what they had to do for CLBR. I have created material E13025 in ETB which is similar to CLBR. Can you please get this tested E2E and let us know if it works. Let me know if you have any question.</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">As far as this defect is concern if it was only related to the cost of meter then I think it can be closed as one of the business has confirmed it’s a nonissue in our call.</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Regards,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Bhaskar</p><br></div><div><br></div><div>I have a question out to Bhaskar what the cost of this will be and if we should just go ahead an apply this to all E and G scenarios in ArcFM.&nbsp;</div> | EIP; INOH | EIP | 40 | Bradley Painter | Done | 2021-01-13T13:59:14.557Z | 2021-01-28T00:23:55.773Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3400 | Task | 3113 | Test Process w/ Production Data |  |  |  |  | Hanh Tran | Done | 2021-01-13T14:25:13.767Z | 2021-01-27T14:17:40.49Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3113 | Product Backlog Item |  | Include zipped GDB copy into CNPMIMSReplicaCopy | <div><span style="background-color:rgb(255, 255, 0);">To be completed by Jan 18th</span><br><ul><li>The copy trigger should be the same as the GDB copy</li><li>Change xcopy to RoboCopy&nbsp;</li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Done | 2020-12-03T13:07:44.637Z | 2021-01-27T19:50:41.033Z | CNP.GIS | CNP.GIS\Sprint 21.01-A |  | INOH
3401 | Product Backlog Item |  | Place OK Gas Meters | <div>Utilize Service Delivery Point to improve the load success rate.&nbsp;</div><div>Susan has already loaded into the test. It is in the business review currently.&nbsp;</div> | GAS; HOU | Business | 50 | Goddard, Susan C. | Done | 2021-01-13T19:10:26.053Z | 2021-02-01T14:55:40.427Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | GAS
3405 | Task | 1020 | GSD Testing |  |  |  |  | Mary Torres | Done | 2021-01-14T14:16:29.62Z | 2021-01-25T14:33:41.607Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
1020 | Product Backlog Item | 1233 | Create Conduit Manager Data Extraction Tool | <p>Requestor: Kathy Holtz &amp; MUG Engineering</p><p>HD 523673</p><p>A tool/command needs to be created to extract out conduit manager information that is stored in the DUCTBANKCCONFIGURATION field within MUG_UGLinearStructure_ln. This is a BLOB field that Schneider has said the only way to extract that information is through custom code. </p><p>Mary has C# projects that the vendor provided that should be helpful. </p> | ELECTRIC; HOU | Data Extraction | 40 | C_Varalakshmi Srinivasan | Done | 2019-10-17T13:02:55.967Z | 2021-01-25T14:33:39.263Z | CNP.GIS | CNP.GIS\Sprint 21.01-A | ELECTRIC
3409 | Product Backlog Item |  | 10.6.1 - Migrate the Electric work orders import part of CNP.MaximoToWOTS | <div><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">The migrated 1061 code is missing the code of importing &nbsp;Electric work orders. </span><br></div><div><br></div><div>see the attached email.&nbsp;</div> | ELECTRIC; GAS; HOU; WOTS | 1061 Migration | 70 | Hanh Tran | Done | 2021-01-14T22:15:09.07Z | 2021-02-01T20:02:43.283Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | GAS
3410 | Product Backlog Item |  | EIP - CU Admin & CU Consolidation Tool issues in DINOQ | <div>Work with Sys Admin Team and SE to resolve CU Admin Tool issues</div> | EIP; INOH | EIP | 50 | Bradley Painter | Done | 2021-01-15T14:12:44.03Z | 2021-02-01T15:07:02.887Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  | INOH
3411 | Task | 3410 | CU Admin Tool - Work with SE to resolve Issues | <div>Cannot access Details item in CU module.&nbsp; Get 500 Error Code</div> |  |  |  | Bradley Painter | Done | 2021-01-15T14:14:30.147Z | 2021-01-21T14:27:29.31Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3414 | Task | 3305 | Reporting Validation | <div><span style="background-color:rgb(255, 255, 0);">Mobile Replication Status</span></div><div><span style="background-color:rgb(255, 255, 0);">Version Report - SDE Reconcile Priority EN-1500</span></div><div><br></div><div>Gas DOT Mileage and Version Report.&nbsp; - Adam, reporting portal.&nbsp; Are these still in use?&nbsp;</div><div>DES Reporting interface.</div><div><br></div><div>Talk with Reporting Group - April McGarr?&nbsp;</div> |  |  |  | Krejcirik, C_Vlad | Done | 2021-01-15T14:18:07.43Z | 2021-01-27T14:54:44.413Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3415 | Task | 3305 | 811 Locate Tickets Validation | <div>Aaron Hills - FME Workbench - High Profile Locates</div><div><br></div><div>Approved by Aaron Hills on 2/2/21</div> |  |  |  | Aaron Miller | Done | 2021-01-15T14:18:21.01Z | 2021-02-02T20:24:24.723Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3416 | Task | 3305 | AVL Validation | <div>Aaron Hills - I think this group is just using the Street Maps Premium.&nbsp;</div><div><br></div><div>Approved by Aaron Hills on 2/2/21</div> |  |  |  | Aaron Miller | Done | 2021-01-15T14:18:30.603Z | 2021-02-02T20:24:38.657Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3417 | Task | 3305 | Banner Validation |  |  |  |  | Krejcirik, C_Vlad | Done | 2021-01-15T14:18:38.843Z | 2021-02-02T14:52:17.52Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3418 | Task | 3305 | Maximo Validation |  |  |  |  | Krejcirik, C_Vlad | Done | 2021-01-15T14:18:49.553Z | 2021-02-02T14:52:21.47Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3419 | Task | 3305 | Optimizer Validation | <div>Aaron Hills - I think this is another instance of a group using the Street Maps Premium service</div> |  |  |  | Aaron Miller | Done | 2021-01-15T14:19:03.937Z | 2021-02-02T20:22:50.86Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3421 | Task | 3305 | NMS Team | <div>Chris Remke SME/POC</div> |  |  |  | Bradley Painter | Done | 2021-01-15T14:19:39.66Z | 2021-01-26T17:14:25.14Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3422 | Task | 3305 | OnBase Validation - Doc Pop and Keyword Updater |  |  |  |  | Bradley Painter | Done | 2021-01-15T14:20:03.027Z | 2021-02-01T18:51:14.197Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3424 | Task | 3288 | Install Visual VB on VM |  |  |  |  | Aaron Miller | Done | 2021-01-15T14:20:28.85Z | 2021-01-20T14:17:55.37Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3425 | Task | 3371 | Conduct basic testing in DINOT with 10.6.1 SP1a installed |  |  |  |  | Aaron Miller | Done | 2021-01-15T14:23:23.263Z | 2021-02-01T15:05:28.24Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3426 | Task | 1007 | Research on how to use Map template in print |  |  |  |  | Christopher Thomas | Done | 2021-01-15T14:24:25.24Z | 2021-01-19T15:23:18.543Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3427 | Task | 3364 | Work with Jeff Chua to Remove Labor and OH rates from SAP - ArcFM Web Service for EIP |  |  |  |  | Christopher Thomas | Done | 2021-01-15T14:43:09.707Z | 2021-01-21T15:05:51.7Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3428 | Task | 3259 | Build FME Workbench to Generate Report |  |  |  |  | Bradley Painter | Done | 2021-01-15T14:43:52.96Z | 2021-01-21T14:16:31.437Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3429 | Task | 3260 | Identify Configuration Change needed to only set integer values in the Measured Length Fields in ArcFM |  |  |  |  | Kelsey Mobley | Done | 2021-01-15T14:44:45.947Z | 2021-01-25T22:14:42.077Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3430 | Task | 3260 | Test XMLs with changes to validate integers are only being sent to EAI for Linear CUs |  |  |  |  | Bradley Painter | Done | 2021-01-15T14:45:33.13Z | 2021-02-01T18:51:18.023Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3431 | Product Backlog Item | 3472 | Push pdf maps from map gallery to Portal | <div><span style="background-color:rgb(255, 255, 0);">High-priority&nbsp;</span></div> | HOU | Business | 90 | Chen Liang | Done | 2021-01-15T15:37:46.92Z | 2021-01-30T22:59:17.777Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3433 | Product Backlog Item |  | Fix outage tracker map pan issue on Android | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:11pt;">Saud:&nbsp;</span><span style="font-size:11pt;">First is switching the current version to the higher version. I have tested this and mostly impacts the TOC and books marks widget. Most of the other functionalities work fine with minor GUI issues. I can try to incorporate the newer version of TOC compatible with higher versions of API within the current framework. If that works we will have resolution to this issue sooner. I will need a week’s time to try it out.</span><br></p><br> | ELECTRIC; HOU | Outage | 80 | Saud Ahmad | Done | 2021-01-17T15:54:22.03Z | 2021-03-09T14:54:21.9Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | ELECTRIC
3434 | Product Backlog Item |  | 10.6.1 - Investigate the missing ElectricConnectivity Toolbar | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">The DLL name is CNPElecConnectivity1021.dll,&nbsp; which is already in the build folder. But JP doesn't see that DLL on citrix after the installation.&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;"><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">It is there at <a href="https://nam04.safelinks.protection.outlook.com/?url=https://dev.azure.com/centerpoint-GIS/CNP.GIS/_git/CNP.GIS.Desktop?path%3D%252FVB6%252FCNPElectricConnectivity&amp;data=04%7c01%7cchen.liang%40centerpointenergy.com%7c342d77bf706a4128072608d8b8d3175c%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637462564051347791%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=P3LFaO/jnPgQLuXovDC6nqTBuH5qUdq6JvEcl3K6xvk%3D&amp;reserved=0">https://dev.azure.com/centerpoint-GIS/CNP.GIS/_git/CNP.GIS.Desktop?path=%2FVB6%2FCNPElectricConnectivity</a></p><br></div></div> | ELECTRIC; HOU | 1061 Migration | 70 | Chen Liang | Done | 2021-01-17T16:16:08.73Z | 2021-01-27T19:51:04.287Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | ELECTRIC
3437 | Task | 3259 | Test Workbench and Validate Output with SAP Team | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="">&nbsp;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="">&nbsp;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><b><span style="">From:</span></b><span style=""> Forston, Dewayne &lt;Dewayne.Forston@centerpointenergy.com&gt; <br><b>Sent:</b> Wednesday, January 20, 2021 8:54 AM<br><b>To:</b> Painter, Bradley &lt;Brad.Painter@centerpointenergy.com&gt;; Magana, Gil &lt;gil.magana@accenture.com&gt;<br><b>Cc:</b> Otis, Lorraine D &lt;lorraine.otis@centerpointenergy.com&gt;<br><b>Subject:</b> RE: [External Email] GIS/Banner Data Quality Process (Post Go Live)</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">If you just provide the prem/service number/sap equipment number that’s perfect.</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><b>From:</b> Painter, Bradley &lt;<a href="mailto:Brad.Painter@centerpointenergy.com">Brad.Painter@centerpointenergy.com</a>&gt; <br><b>Sent:</b> Wednesday, January 20, 2021 8:31 AM<br><b>To:</b> Forston, Dewayne &lt;<a href="mailto:Dewayne.Forston@centerpointenergy.com">Dewayne.Forston@centerpointenergy.com</a>&gt;; Magana, Gil &lt;<a href="mailto:gil.magana@accenture.com">gil.magana@accenture.com</a>&gt;<br><b>Cc:</b> Otis, Lorraine D &lt;<a href="mailto:lorraine.otis@centerpointenergy.com">lorraine.otis@centerpointenergy.com</a>&gt;<br><b>Subject:</b> RE: [External Email] GIS/Banner Data Quality Process (Post Go Live)</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Ok.&nbsp; Do you just want Premise/Service/SAP_Equipment_Number written out then?&nbsp; Or do you want any/all customer information that was put into GIS for that record? </p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Thanks,</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Brad</p><br></div> |  |  |  | Bradley Painter | Done | 2021-01-18T18:05:02.337Z | 2021-01-22T20:34:37.027Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3438 | Product Backlog Item |  | 10.6.1 - Investigate the missing Stoner Export tool |  | HOU | 1061 Migration |  | C_Varalakshmi Srinivasan | Done | 2021-01-19T14:15:34.917Z | 2021-01-25T14:49:09.883Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3439 | Product Backlog Item |  | Research on Placing OK Gas Service Lines |  | GAS; HOU; UNPLANNED | Business |  | Goddard, Susan C. | Done | 2021-01-19T14:37:56.58Z | 2021-02-02T14:17:26.67Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | GAS |  | UNPLANNED
3441 | Task | 3401 | Code logic change | <div>Add logic to gsdp as the point for placing the gas meter in the gas meter fc and using new field</div> |  |  |  | Goddard, Susan C. | Done | 2021-01-19T14:51:14.217Z | 2021-01-26T14:20:57.03Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3442 | Task | 3401 | Test code change | <div>Test new placement using gsdp and new field use</div> |  |  |  | Goddard, Susan C. | Done | 2021-01-19T14:52:37.19Z | 2021-01-25T14:29:42.13Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3443 | Task | 3401 | Load Meters in OKQ | <div>Load Gas meters into OKQ</div> |  |  |  | Goddard, Susan C. | Done | 2021-01-19T14:53:56.797Z | 2021-01-25T14:30:18.12Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3449 | Task | 3401 | Add Field to FC | <div>Add field to feature class for superior number</div> |  |  |  | Goddard, Susan C. | Done | 2021-01-19T15:01:10.537Z | 2021-01-25T14:29:45.167Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3450 | Task | 3261 | Cleanup unused domains in Arkansas |  |  |  |  | William Robertson Jr | Done | 2021-01-19T15:19:48.083Z | 2021-01-26T13:33:04.18Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3451 | Task | 3438 | Provide the Installer to install in Citrix and test |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-19T15:20:31.973Z | 2021-01-21T14:22:19.84Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3452 | Task | 3436 | Install Service Pack |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-19T15:20:54.907Z | 2021-01-20T14:20:51.323Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3436 | Product Backlog Item |  | 10.6.1 - ArcFM 10.6.1a SP2 Sanity Check - HOU |  | HOU | 1061 Migration | 30 | C_Varalakshmi Srinivasan | Started | 2021-01-17T18:50:56.46Z | 2021-02-24T15:13:41.03Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3455 | Task | 3434 | Coordinate with JP on Installing the new build in Citrix |  |  |  |  | Chen Liang | Done | 2021-01-19T15:21:43.607Z | 2021-01-20T14:22:31.18Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3457 | Task | 3434 | Create a new build including the toolbar DLL |  |  |  |  | William Robertson Jr | Done | 2021-01-19T15:22:25.08Z | 2021-01-21T14:23:19.62Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3458 | Task | 3434 | Verify the toolbar working in Citrix |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-19T15:23:05.83Z | 2021-01-20T14:21:45.347Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3459 | Task | 3433 | Re code for TOC against higher API version |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:23:32.503Z | 2021-02-01T14:16:07.41Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3460 | Task | 3431 | Review the Portal settings with JP |  |  |  |  | Chen Liang | Done | 2021-01-19T15:24:13.113Z | 2021-01-20T14:24:38.947Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3464 | Task | 3431 | Create an interface to upload maps to Portal |  |  |  |  | Chen Liang | Done | 2021-01-19T15:25:11.9Z | 2021-01-29T14:22:03.197Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3467 | Task | 3431 | Review the uploaded map items with Mary |  |  |  |  | Chen Liang | Done | 2021-01-19T15:26:09.957Z | 2021-01-20T14:24:27.063Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3475 | Task | 3114 | Test with Prod Data |  |  |  |  | Hanh Tran | Done | 2021-01-19T15:31:05.833Z | 2021-02-01T14:22:26.587Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3479 | Task | 3409 | Rebuild the project in 10.6 and Unit test |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-01-19T15:33:14.273Z | 2021-01-22T14:22:05.327Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3480 | Task | 3353 | Contact site admin for access and verify if the new list is still and SP list |  |  |  |  | Hanh Tran | Done | 2021-01-19T15:34:25.48Z | 2021-01-21T14:26:07.283Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3353 | Product Backlog Item |  | Code SharePoint List Location Change | <div><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;"><b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">From:</span></b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"> Gastineau, David E &lt;<a href="mailto:david.gastineau@centerpointenergy.com">david.gastineau@centerpointenergy.com</a>&gt; <br style=""><br style=""></span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi Hanna,</p></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I just wanted to share with you that I am looking into migrating the Code SharePoint List from its current location to the Teams Site that I use for code clearance so I can use the new Microsoft Lists functionality and build Power BI dashboards with the data and not worry about messing up the backend code of the site (which I have done before).</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I am not ready to make the transition just yet, we are going to build a test list to see if it works. Once we know it works, we’ll make the migration. A few questions:</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><ul style="margin-bottom:0in;margin-top:0in;"> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">What would you need to make this transition? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Is this a big ask? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Or is it relatively simple?</span></li></ul><br></div> | HOU | Business | 13 | Hanh Tran | Started | 2021-01-05T16:10:41.21Z | 2021-03-04T14:27:38.07Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3484 | Task | 1251 | Confirm the request from Karen |  |  |  |  | Mary Torres | Removed | 2021-01-19T15:37:00.533Z | 2021-01-25T14:50:14.4Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
1251 | Product Backlog Item | 1343 | WOTS: Add FNDOCID to report | <p>HD0000523219 - Karen Matsuzewski</p><p><span>Please add FNDOCID to Orders Assigned by Employer report. It would be helpful for the editor to know what FNDOCID goes with the work order assigned. They would not have to do an order search just for that. </span></p> | HOU | WOTS | 3 | C_Varalakshmi Srinivasan | New | 2019-08-06T21:49:45.41Z | 2021-02-27T23:16:04.407Z | CNP.GIS | CNP.GIS
3485 | Task | 3364 | Remove code from project |  |  |  |  | Christopher Thomas | Done | 2021-01-19T15:38:40.96Z | 2021-01-21T15:05:44.417Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3486 | Task | 3364 | Test web service changes |  |  |  |  | Christopher Thomas | Done | 2021-01-19T15:40:08.477Z | 2021-01-21T15:05:46.94Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3487 | Task | 3025 | Add FGDB configuration to Production |  |  |  |  | Christopher Thomas | Done | 2021-01-19T15:41:58.837Z | 2021-02-01T14:29:13.06Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3488 | Task | 3436 | Install Service Pack |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-20T13:23:37.51Z | 2021-01-20T15:51:20.99Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3489 | Task | 3434 | Investigate DLL not registered |  |  |  |  | William Robertson Jr | Done | 2021-01-20T14:22:57.857Z | 2021-01-21T14:23:16.83Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3490 | Task | 3357 | Review Gas Leaks Project |  |  |  |  | Christopher Thomas | Done | 2021-01-20T14:25:41.21Z | 2021-01-29T14:25:08.393Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3357 | Product Backlog Item |  | Create an interface to store Electric Capital Work Orders from SAP into GIS | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-indent:.5in;"><span style="font-size:14.6667px;text-indent:0.5in;"></span></p><div><span style="font-size:14.6667px;text-indent:0.5in;">Load&nbsp; data from &quot;_SYS_BIC&quot;.&quot;system-local.bw.bw2hana/ZUI_01O&quot; nightly into GIS Metro table</span><br><ul><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Chen - Get the table info from SAP</span></li></ul><ol><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Create a FC for&nbsp;Electric Capital Work Orders</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Read data from SAP table and store data in GIS&nbsp;</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Geocode the address into Lat/Long&nbsp;</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Publish the <span style="display:inline !important;">FC<span>&nbsp;</span></span>as a map service</span></li></ol><span><div><span>SAP HANA connection string:&nbsp;</span></div><div><span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-autospace:none;"><span style="font-size:9.5pt;font-family:Consolas;">QA: Server=<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">hiqdb.mycenterpointenergy.com:32041</span>;UserID=BWGIS;Password=<span style="font-family:&quot;Segoe UI&quot;, sans-serif;font-size:14px;display:inline !important;">Vision@123</span></span></p></span></div><div><span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:10.5pt;font-family:&quot;Segoe UI&quot;,sans-serif;"></span></p><div style="box-sizing:border-box;"><span style="box-sizing:border-box;"><p style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p></span></div></span><p></p></div>Reuse the code from CNP.GIS.Utilities\CNP.Gas.Leaks</span><br></div><div><span><br></span></div> | HOU | SAP-GIS | 30 | Christopher Thomas | Done | 2021-01-06T20:04:09.113Z | 2021-02-27T22:28:16.85Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3492 | Task | 3025 | Wait for maintenance weekend (1/29) |  |  |  |  | Christopher Thomas | Done | 2021-01-20T14:26:54.257Z | 2021-02-01T14:28:59.833Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3494 | Task | 1007 | Add Map Scale combo box |  |  |  |  | Christopher Thomas | Done | 2021-01-20T15:49:11.233Z | 2021-01-25T14:20:34.19Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3495 | Task | 1007 | Create Schneider Ticket for Active Directory Access with Work Flow Manager |  |  |  |  | Christopher Thomas | Done | 2021-01-20T15:51:26.29Z | 2021-01-21T14:21:18.737Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3500 | Task | 3410 | CU Consolidation Tool - Work with SE to resolve Issues |  |  |  |  | Bradley Painter | Done | 2021-01-20T19:28:10.273Z | 2021-01-27T16:46:04.687Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3501 | Task | 1007 | Testing clearing cache on Chrome |  |  |  |  | Christopher Thomas | Done | 2021-01-21T14:19:33.667Z | 2021-01-25T14:21:48.527Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3503 | Task | 3438 | Wait for GSD to test | [5 empty] | Done | 2021-01-21T14:22:58.93Z | 2021-01-25T14:24:20.433Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3504 | Task | 3434 | Sys admin to verify | [5 empty] | Done | 2021-01-21T14:23:31.65Z | 2021-01-25T14:25:24.173Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3506 | Task | 3306 | Create Web method for data move |  |  |  |  | Saud Ahmad | Done | 2021-01-21T14:30:04.773Z | 2021-01-21T14:30:15.787Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3507 | Task | 3353 | Create IT request for svc-gisbatch to access sharepoint online | <div>Sharepoint link:&nbsp;<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"><a href="https://nam04.safelinks.protection.outlook.com/?url=https://centerpointenergy.sharepoint.com/sites/CodeClearance479-CodeInspectors&amp;data=04%7c01%7cdouglas.kjellander%40centerpointenergy.com%7c04dcaf2470b0417ce8d308d8bd7528ea%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637467658181195587%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=5pZqFgYbhyF1XSN%2BQYQBIutL%2BR6cqeCxW1rggSplZ64%3D&amp;reserved=0">https://centerpointenergy.sharepoint.com/sites/CodeClearance479-CodeInspectors</a></span></div> |  |  |  | Chen Liang | Done | 2021-01-21T14:37:24.86Z | 2021-01-25T15:31:13.14Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3512 | Task | 2944 | Suppress emails and finish configuration |  |  |  |  | Kelsey Mobley | Done | 2021-01-21T15:10:01.58Z | 2021-02-01T20:27:14.033Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3513 | Task | 3261 | Delete IGS domains from Arkansas |  |  |  |  | William Robertson Jr | Done | 2021-01-22T13:02:20.4Z | 2021-01-22T14:21:09.153Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3514 | Task | 3261 | Remove domains from CNP SOLD Facilities |  |  |  |  | William Robertson Jr | Done | 2021-01-22T13:03:27.273Z | 2021-01-22T14:21:16.863Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3515 | Task | 3261 | Remove domains from Deleted Features in Arkansas |  |  |  |  | William Robertson Jr | Done | 2021-01-22T13:05:02.42Z | 2021-01-22T14:21:24.693Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3516 | Task | 3409 | Unit Testing 10.6.1 |  |  |  |  | Hanh Tran | In Progress | 2021-01-22T14:22:10.69Z | 2021-02-01T14:23:30.307Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3517 | Task | 3306 | Deploy to prod and Have Jacob to review |  |  |  |  | Saud Ahmad | Done | 2021-01-25T14:19:00.01Z | 2021-02-02T14:15:02.427Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3519 | Task | 1007 | Add a Preview button |  |  |  |  | Christopher Thomas | Done | 2021-01-25T14:22:44.4Z | 2021-01-27T14:16:48.93Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3520 | Task | 3434 | Verify the URD connector tool with Nanda |  |  |  |  | Chen Liang | Done | 2021-01-25T14:26:05.06Z | 2021-01-25T14:52:20.827Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3521 | Product Backlog Item | 3544 | Database: Delete domains on Deleted and Sold assets (ETX) |  | GAS; HOU; UNPLANNED | System | 20 | William Robertson Jr | Done | 2021-01-25T14:28:21.503Z | 2021-02-01T20:02:43.283Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | GAS |  | UNPLANNED
3522 | Task | 3401 | Jacob to Review the loaded gas meter data |  |  |  |  | Goddard, Susan C. | Done | 2021-01-25T14:30:03.433Z | 2021-02-01T14:54:56.087Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3523 | Task | 3113 | Add ZIP options to exclude parent folders |  |  |  |  | Hanh Tran | Done | 2021-01-25T14:38:24.96Z | 2021-01-27T14:17:38.633Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3524 | Product Backlog Item |  | Production Issue: Troubleshoot the IVRWebService |  | HOU; UNPLANNED | Outage |  | Saud Ahmad | Done | 2021-01-25T14:47:48.91Z | 2021-01-26T22:15:28.603Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  |  | UNPLANNED
3525 | Task | 3524 | Troubleshoot the missing authentication |  |  |  |  | Saud Ahmad | Done | 2021-01-25T14:48:08.897Z | 2021-01-26T14:15:55.707Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3526 | Task | 3434 | Nanda to test the Connect Fuse tool | [5 empty] | In Progress | 2021-01-25T14:52:56.123Z | 2021-01-25T14:53:20.793Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3527 | Task | 3353 | Wait for IT request to be fulfilled |  |  |  |  | Chen Liang | Done | 2021-01-25T15:30:57.517Z | 2021-01-27T19:54:13.12Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3528 | Task | 3521 | Remove domains from Deleted Features in East Texas |  |  |  |  | William Robertson Jr | Done | 2021-01-25T15:50:48.447Z | 2021-01-26T14:22:41.2Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3529 | Task | 3521 | Remove domains from CNP SOLD Facilities |  |  |  |  | William Robertson Jr | Done | 2021-01-25T15:51:23.64Z | 2021-01-26T14:22:45.283Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3535 | Task | 3260 | Create AU to round measured length value |  |  |  |  | Kelsey Mobley | Done | 2021-01-25T22:15:10.12Z | 2021-01-27T21:51:58.06Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3536 | Task | 3439 | Install FME |  |  |  |  | Goddard, Susan C. | Done | 2021-01-25T22:58:27.053Z | 2021-01-27T14:23:27.797Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3537 | Task | 3439 | Review FME Workbench |  |  |  |  | Goddard, Susan C. | Done | 2021-01-25T22:58:50.263Z | 2021-01-27T14:23:30.01Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3538 | Task | 3439 | Start back bone code |  |  |  |  | Goddard, Susan C. | Done | 2021-01-25T22:59:34.533Z | 2021-02-01T14:26:56.243Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3539 | Task | 3521 | Export unassigned domains to a File Geodatabase |  |  |  |  | William Robertson Jr | Done | 2021-01-26T13:32:00.703Z | 2021-01-27T14:20:58.267Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3541 | Product Backlog Item | 3544 | Database: Delete domains on Deleted and Sold assets (LA) |  | GAS; UNPLANNED | System | 20 | William Robertson Jr | Done | 2021-01-26T16:48:30.487Z | 2021-02-01T20:02:43.283Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | GAS |  | UNPLANNED
3542 | Task | 3541 | Remove domains from CNP SOLD Facilities |  |  |  |  | William Robertson Jr | Done | 2021-01-26T16:59:20.497Z | 2021-01-27T14:20:09.027Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3543 | Task | 3541 | Remove domains from Deleted Features in East Texas |  |  |  |  | William Robertson Jr | Done | 2021-01-26T18:44:23.933Z | 2021-01-27T14:20:11.727Z | CNP.GIS | CNP.GIS\Sprint 21.01-B
3556 | Product Backlog Item |  | Add project name "UN DATA PREP' to all DBs |  | SYSTEM; UNPLANNED | System | 20 | William Robertson Jr | Done | 2021-01-28T13:47:46.113Z | 2021-01-29T13:28:36.337Z | CNP.GIS | CNP.GIS\Sprint 21.01-B |  |  | UNPLANNED
3557 | Task | 3556 | Add domain value UN DATA PREP to the PROJECT_NAME domain in all databases |  |  |  |  | William Robertson Jr | Done | 2021-01-28T13:56:46.427Z | 2021-01-28T14:19:38.59Z | CNP.GIS | CNP.GIS\Sprint 21.01-B