## current_iteration
Id | WorkItemType | Parent | Title | Description | Tags | ValueArea | BusinessValue | AssignedTo | State | CreatedDate | ChangedDate | AreaPath | IterationPath | Operation | Region | Planned
1271 | Product Backlog Item | 1343 | WOTS: CP Status Report - Rearrange columns | <p><span>HD0000111654 - Julie Beitler</span></p><p><span>In the CP STATUS REPORT of WOTS, it would be easier to use if the REVIEWED column was next to the WORK ORDER NUMBER column. This would allow the user to quickly associate the check box with the desired work order number. Perhaps other reports would benefit from this same format change. Thanks!</span></p> | GAS; HOU | WOTS | 1 | Subhankar, C_Baidya X | Removed | 2019-08-06T22:15:27.293Z | 2021-01-20T15:53:18.463Z | CNP.GIS | CNP.GIS\Sprint 21.02-A | GAS
2317 | Product Backlog Item |  | EIP - Leak Repair Point | <div><p style="margin:0in 0in 10pt;font-size:11pt;font-family:Calibri, sans-serif;"><a href="https://nam04.safelinks.protection.outlook.com/?url=https://dev.azure.com/centerpoint-GIS/CNP.GIS/_git/CNP.GIS.Utilities?path%3D%252FCNP.Gas.Leaks%252FCNP.Gas.Leaks&amp;data=04%7c01%7cBrad.Painter%40centerpointenergy.com%7ccf75c60b9688456f6c0508d8be35ab46%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637468485014017467%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=wPmP8SyvokEBnHpoqnwr8FfkL%2BH0LULjco/jjngjum0%3D&amp;reserved=0">https://dev.azure.com/centerpoint-GIS/CNP.GIS/_git/CNP.GIS.Utilities?path=%2FCNP.Gas.Leaks%2FCNP.Gas.Leaks</a></p><br></div><div><br></div><div><br></div><div><br></div> | EIP; INOH | EIP | 50 | Chen Liang | Done | 2020-10-21T13:09:45.883Z | 2021-02-18T15:14:19.697Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
2348 | Task | 2317 | Review Leak Repair Point Code | <div>walk through the code with Susan</div> |  |  |  | Chen Liang | Done | 2020-10-23T18:04:47.94Z | 2021-02-08T15:24:24.18Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3119 | Task | 3114 | Create a UI to guide the download | <div>Create UI:&nbsp;</div><div><ul><li>Display a service area for download&nbsp;</li><li>Present the users with a progress bar&nbsp;</li></ul></div><div><br></div> |  |  |  | Hanh Tran | Done | 2020-12-03T13:33:49.64Z | 2021-02-05T14:21:53.427Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3114 | Product Backlog Item |  | Allow multiple Fileservers to download the MIMSReplica | <div><span style="background-color:rgb(255, 255, 0);display:inline !important;">To be completed by Jan 18th</span><br></div><div>MIMSReplicaCopy copies the replica files from one file server. This is for the users to download data for GO!Sync.&nbsp;</div><div><ul><li>Change the config file to accommodate multiple download sources.&nbsp;</li><li>Add UI to select which file server they download files from.&nbsp;</li><li>Download one selected fileserver to the local drive&nbsp;&nbsp;<br></li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Started | 2020-12-03T13:12:50.887Z | 2021-03-10T14:33:13.913Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3196 | Product Backlog Item |  | Verify interface: cnp_sap_pole_update |  | HOU | 1061 Migration | 30 | Hanh Tran | Done | 2020-12-08T16:51:55.01Z | 2021-02-12T14:28:34.827Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3197 | Task | 3196 | Test and Verify |  |  |  |  | Hanh Tran | Done | 2020-12-08T16:52:31.477Z | 2021-02-12T14:28:26.197Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3331 | Task | 1271 | Modify code in CP Status web application |  |  |  |  | Subhankar, C_Baidya X | Removed | 2021-01-05T15:03:39.023Z | 2021-01-25T15:27:11.14Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3334 | Task | 1271 | Unit testing |  |  |  |  | Subhankar, C_Baidya X | Removed | 2021-01-05T15:04:16.293Z | 2021-01-25T15:27:16.38Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3380 | Product Backlog Item |  | Refresh MetroT based on SAP PRM Data Refresh | <div>Load SAP data into the test database. <span style="color:rgb(0, 0, 0);background-color:rgb(255, 255, 0);"><b>Scheduled on 1/29</b></span></div> | HOU | SAP-GIS | 20 | Saud Ahmad | Done | 2021-01-11T23:36:48.25Z | 2021-02-04T14:59:52.613Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3466 | Task | 3380 | Run GISFull Sync against MetroT Env and verify output |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:25:40.97Z | 2021-02-04T14:16:55.383Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3469 | Task | 3380 | Check on FTP for the file |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:26:18.14Z | 2021-02-04T14:16:58.233Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3481 | Task | 1007 | Create form that will call all child forms | <div>Create form that will call all child forms. There will be one main form that will call all child forms based on the template drop down selection<br></div> |  |  |  | Christopher Thomas | Done | 2021-01-19T15:34:51.123Z | 2021-02-08T14:17:36.153Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
1007 | Product Backlog Item |  | GViewer: Add Functionality to Autopopulate Print Templates | <p>Requestor: John K</p><p>This functionality was lost when G.Viewer moved from Silver Light to Geocortex.</p> | HOU | GViewer | 21 | Christopher Thomas | Done | 2020-09-30T13:47:58.18Z | 2021-02-18T17:14:30.063Z | CNP.GIS | CNP.GIS\Sprint 21.01-A
3491 | Task | 3380 | Wait until Tuesday (2/2) |  |  |  |  | Saud Ahmad | Done | 2021-01-20T14:25:46.29Z | 2021-02-04T14:16:44.103Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3496 | Product Backlog Item |  | EIP - FME Workbench for CU Data Loading | <div>Build FME Workbench to Update Material Numbers, Material Descriptions, and Cost data in ArcFM Tables.&nbsp; This will be used for the future Dry Run exercises and for the production go-live process</div> | EIP; INOH | EIP | 50 | Bradley Painter | Done | 2021-01-20T19:19:54.157Z | 2021-02-15T19:55:51.597Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
3498 | Product Backlog Item |  | EIP - Dry 1 Run DIP Prep |  | EIP; INOH | EIP | 50 | Kelsey Mobley | Done | 2021-01-20T19:21:48.503Z | 2021-02-15T20:31:20.74Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
3499 | Task | 3498 | Refine and Update DIP plan for Dry Run 1 |  |  |  |  | Kelsey Mobley | Done | 2021-01-20T19:22:11.62Z | 2021-02-15T20:30:00.17Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3510 | Task | 3509 | Validate Maximo Simple WO and add missing WO if needed | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Validate simple wo: working with Chris Huff to process missing work orders per Hanna on 2/1/21</p><br></div> |  |  |  | Hanh Tran | Done | 2021-01-21T14:39:49.477Z | 2021-02-02T15:49:29.153Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3509 | Product Backlog Item |  | EIP - WOTS WO validation for missing WOs from Maximo |  | EIP; HOU; INOH | EIP | 10 | Hanh Tran | Done | 2021-01-21T14:38:50.827Z | 2021-02-18T17:16:20.217Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3531 | Product Backlog Item |  | 10.6.1 - Batch Gas Pressure System Code Migration |  | INOH | 1061 Migration | 10 | Aaron Miller | Done | 2021-01-25T19:16:56.46Z | 2021-02-15T20:33:25.887Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
3532 | Product Backlog Item |  | Decade Modification to CNP GIS Gas Reports (Citrix Standalone) | <div><span style="font-size:small;font-weight:bold;">HD0000524896</span><br></div><div>Requestor: Nathan Winkley &amp; Data Quality</div><div><br></div><div>**We probably need to check the compliance reports and other stand alone reports for any DECADE output modifications that are potentially needed as well**</div><div><br></div><div><br></div><div><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>The GIS Gas Reporting Tool for Mains &amp; Services needs the following changes made to the “DECADE” of installation field:</font></p><font face="Times New Roman" size=3></font><ol type=1 style="margin-top:0in;" start=1><font face="Times New Roman" size=3> </font><li style="margin:0in 0in 0pt;"><strong><span>“2010 – RPT YR END” </span><span style="font-family:Wingdings;">à</span><span> needs <u>updated</u> to “2010 – 2019”</span></strong></li><font face="Times New Roman" size=3><strong> </strong></font><li style="margin:0in 0in 0pt;"><strong><u><span>ADD</span></u><span> a new decade of “2020 – RPT YR END”</span></strong></li><font face="Times New Roman" size=3></font></ol><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>&nbsp;</font></p><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>During the annual reporting process to PHMSA each year<span style="color:rgb(0, 0, 0);"> </span><span style="color:rgb(0, 0, 0);">(Jan 1 – Mar 15)</span><span style="color:rgb(0, 0, 0);">, t</span>his is a specific category of data we use to populate the annual form section asking for the “decade of installation” for mains and services.&nbsp; If we could get it updated asap for this year’s reporting process, it would save us extra work to work around the issue.</font></p><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>&nbsp;</font></p><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>Please contact Paul Meuth for questions and Ray Villarreal for testing.</font></p><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>&nbsp;</font></p><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>Below is one state’s example of what the (services) export currently looks like:</font></p><font face="Times New Roman" size=3></font><p style="margin:0in 0in 0pt;"><font face=Calibri size=3>&nbsp;</font></p><font face="Times New Roman" size=3></font><span style="font-family:&quot;Calibri&quot;,sans-serif;font-size:11pt;"><img width=437 height=193 style="width:4.552in;" src="data:image/png;base64,/9j/4AAQSkZJRgABAQEAYABgAAD/2wBDAAoHBwgHBgoICAgLCgoLDhgQDg0NDh0VFhEYIx8lJCIfIiEmKzcvJik0KSEiMEExNDk7Pj4+JS5ESUM8SDc9Pjv/2wBDAQoLCw4NDhwQEBw7KCIoOzs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozv/wAARCADBAbUDASIAAhEBAxEB/8QAHwAAAQUBAQEBAQEAAAAAAAAAAAECAwQFBgcICQoL/8QAtRAAAgEDAwIEAwUFBAQAAAF9AQIDAAQRBRIhMUEGE1FhByJxFDKBkaEII0KxwRVS0fAkM2JyggkKFhcYGRolJicoKSo0NTY3ODk6Q0RFRkdISUpTVFVWV1hZWmNkZWZnaGlqc3R1dnd4eXqDhIWGh4iJipKTlJWWl5iZmqKjpKWmp6ipqrKztLW2t7i5usLDxMXGx8jJytLT1NXW19jZ2uHi4+Tl5ufo6erx8vP09fb3+Pn6/8QAHwEAAwEBAQEBAQEBAQAAAAAAAAECAwQFBgcICQoL/8QAtREAAgECBAQDBAcFBAQAAQJ3AAECAxEEBSExBhJBUQdhcRMiMoEIFEKRobHBCSMzUvAVYnLRChYkNOEl8RcYGRomJygpKjU2Nzg5OkNERUZHSElKU1RVVldYWVpjZGVmZ2hpanN0dXZ3eHl6goOEhYaHiImKkpOUlZaXmJmaoqOkpaanqKmqsrO0tba3uLm6wsPExcbHyMnK0tPU1dbX2Nna4uPk5ebn6Onq8vP09fb3+Pn6/9oADAMBAAIRAxEAPwDv9T0y4XZFaW0ksSWhhh8uRV2P2MmSNydOPmHBypreXdtG7G7HOOmaxxrtqYEm+w3GDGZXARCY4wcbz83I4J4ycDpWsEjIBCKQehxQA60+/c/9dR/6AtWa5rV99nFc3w1nUrJFkWJLWxigczSEKFCiSNjuJIHUAYycDJqi1xdQWdxPfa94kspbcov2aW3sWkkLnEYTZEysWbgAHr1xQB2dFcRJqFxbWl/Lfa74ksprCETyW0sFgZGjPAZSsZQjII+9kEcgZGZtZuZNDadbnxRrzmCxkvW8uCyOUQqCBmEfN8wx296AOxorjRcXEslvFaeIvEF3LdWb3cSRw2KkqrIpU74lAbMg4OOh78UuhPqWvJLImr+JLSKN3j8y4j07DOjlGUBEY8EHtjjg0AdjRXDW+o3dxeiD+2fE0cLXklkl00WneW0qFgQAIy+CUbBKgeuKtQSXFwln5fiXX/Pu5Wi+zmCy8yEpneX/AHOAFxyQTnIxnIyAdfWLa/8AI76p/wBg2z/9GXVH9haj/wBDZq//AH6tP/jFc7fQ3Oj63rd9P4k1hktNLtZZGiitDI48y4+XBiC8YOOn3jknjAB3lFcNNqN1Zw3rahrXiWxls7R7wwTQ6ezSxL94oUjZSQcDBIPI7Gp1k1KKznvNR1bxLptvDHv8yePTn35OAqiNHJJyMDHNAHZUVymnRaleyvDca14k0+VUEgS6hsPmU8ZDJEy9exIPtVJNTaXw7LrcPiXxDJDHKsXkiCxEjFmUJgGIDDB0YZI4YH2oA7iiuGl1G5tba9e81rxNa3FmiSNayQ6eZHRm2qylYyhGcj72RjnHGdLT7HWr0yfaNV8R6fsxg3K6cd/08tG6e+OtAHT0Vi/2FqP/AENmr/8Afq0/+MUf2FqP/Q2av/36tP8A4xQBtUVi/wBhaj/0Nmr/APfq0/8AjFH9haj/ANDZq/8A36tP/jFAG1RWL/YWo/8AQ2av/wB+rT/4xR/YWo/9DZq//fq0/wDjFAG1RWL/AGFqP/Q2av8A9+rT/wCMUf2FqP8A0Nmr/wDfq0/+MUAbVFYv9haj/wBDZq//AH6tP/jFH9haj/0Nmr/9+rT/AOMUAbVFYv8AYWo/9DZq/wD36tP/AIxR/YWo/wDQ2av/AN+rT/4xQBtUVi/2FqP/AENmr/8Afq0/+MUf2FqP/Q2av/36tP8A4xQBtUVi/wBhaj/0Nmr/APfq0/8AjFH9haj/ANDZq/8A36tP/jFAG1RWL/YWo/8AQ2av/wB+rT/4xR/YWo/9DZq//fq0/wDjFAG1RWL/AGFqP/Q2av8A9+rT/wCMUf2FqP8A0Nmr/wDfq0/+MUAbVFYv9haj/wBDZq//AH6tP/jFH9haj/0Nmr/9+rT/AOMUAbVFYv8AYWo/9DZq/wD36tP/AIxR/YWo/wDQ2av/AN+rT/4xQBtVi+FP+QRP/wBhK/8A/SuWj+wtR/6GzV/+/Vp/8Yrm9OS507Rt3/CQ6081xql5BBa2sNozzOLmXJG+LA4VnJJCjnoMCgDvqK4x7m6ishLPr3iSK6a4Fsti1vY+c8hGQFxEUIK/NuDbQAckbThn26ZLeV7jxD4itp4bmG3mtpILHzI2lcKhyIipU7gcqx6HuCKAO2oridY1BtEa9W58TeIZDZRW8sghtrJiwmkMahR5OScg5Hp0z0qaWS8+1yWtl4g8QahKlrFdAW8en4eORmVSpeNR/AT16EYzQB2FFcjoA1HxBYLfR634itIJFDRNcx6f+9BzyAkbEfjjrWp/YWo/9DZq/wD36tP/AIxQAeK/+QRB/wBhKw/9K4q2q5HxBpN7b2NtLL4i1K6RdSscwzR2wVs3UQ52RKeOvB7fhXU+U/8Az8Sfkv8AhQBLRUXlP/z8Sfkv+FHlP/z8Sfkv+FAEtFReU/8Az8Sfkv8AhRQBg6vpSX0aQQJAi+V5Jl+0OhRDjjYow4x0DHGfxrYV4lUKHUADA5rFOrahLZNNbi23wQGabcrYf5mAUDOUJ2NnOcHgjrW3G4ljWRcgMoIz70AZuo6fPqVpIbKWNLq2u0uLcyZMbOqr8rY5AIyMjkZzg4wYbvS9e1a1lku5rS0nilhls7eJzNErxtuy7lFY7vukAcAZGTVXxFa6WqNe3Ph7TdWu5byG0i+2Rrxv2gZcoxABYnAB71jagfDuk292l/4J8PwXtrLbKysIxblJn2LJ5piBABDbspxt9waANu98N6lryalLqb2tnPc2JsreO2dpljBO4uzFUJJbHGBgL1OeIdV8Oa5r9tqMl8LC1uptLksYI4Z3kTLkFnZiikDKqMAHvzVCCHwxNpguI/Cvha9nmuVtbaPTniuEeQjOHfyl2YAJPB4HQnAq82i6DZ6Xe3Wp+CNHgltFyEht45UnyPlCMY1OScLyo59aANC28PXNr41bVo54v7PNpMgg53pLJJGzEdtp2FvXcx9eLnh7TJ9J06W2uGjZ3u7icGMkjbJK7qOQOcMM+9cxPaeH/wCzNKmtfBGhyXmoXZs3t5oo41gkVZC4LiJicGJh93nrxVa+bw1p1m/2vwZ4dt72G+S0nScRJbpvQusnm+V90rjqoOcjtkgF+x8IX9rrBuBY6Vbk6pNePqUMrfaniaRnERHljgghTlyMZ68V0NnpBtvEuo6rti2XcMKrjO4Mu4OTx3HljPfYM9BWRoWg+F9XsDdN4c8MOPMKq2nrFdRkAD+Py15znjHpzzWl/wAIZ4V/6FnSP/AGL/4mgDarkdb02fWNU8R6dbNGs1zo9oiGQkKCZLnqQCcfhWp/whnhX/oWdI/8AYv/AImsm28J+G28Y6lAfD2lmJNPtHWM2Ue1WMlwCQMcEhVyfYelADtX8Pax4ghv5L1LG0nfTJ7G1jhuHlXMuCzOxRSB8ijAU9z7Ah8Lyvpl1ZJoei6I8qxslxYP5haSNw6b18qPK5Hr6+uayr6LQ7ObVZV8C6BJp+k3CQ3EpVFlYFEYlI/JIJAk4BcZI7Us0GiQ/bLpvAvh/wDs6zvhaSS7U84kuqbhH5ODyw435P1oA6C6s/E2p2V1DcPZWXnW/wBnWK3naQZYgPKXaMEMq52qBjJ5PTGfe+EdUS3vYLLUBeJdLbOPtpSIrJDIpAHlRAbSi4zgkbV6jpmRnwvNr8+lr4Z8HxNDd/ZglzcRR3EnTlYvJOc54G7kitbxDpHhXQNNN3/whunXR3BdsdhEAuSBlmK4A5+p7A0AGq+HNX1221Ka9i0+K6uLaO2gt0neSLaH3sXcoD8xwMBeMd88avh/TX03z1/sDSNJR8H/AIl0u7zCM/eHlJ07detc7eweGLPWZ7X/AIQzRTZ2s1vb3Fw0ESuJJiAu2PYdyjcuSWHU4B20Xo8F2WrX9m3hLS2g0+wlu5rgWUWMx7d0ajbycMOc4zx1zgA7yiuQ0TRPDupPc2974M0azu7UoXjjt45UKuu5SG2LnuDx1HfrWr/whnhX/oWdI/8AAGL/AOJoA2qKxf8AhDPCv/Qs6R/4Axf/ABNH/CGeFf8AoWdI/wDAGL/4mgDaorF/4Qzwr/0LOkf+AMX/AMTR/wAIZ4V/6FnSP/AGL/4mgDaorF/4Qzwr/wBCzpH/AIAxf/E0f8IZ4V/6FnSP/AGL/wCJoA2qKxf+EM8K/wDQs6R/4Axf/E0f8IZ4V/6FnSP/AABi/wDiaANqisX/AIQzwr/0LOkf+AMX/wATR/whnhX/AKFnSP8AwBi/+JoA2qKxf+EM8K/9CzpH/gDF/wDE0f8ACGeFf+hZ0j/wBi/+JoA2qKxf+EM8K/8AQs6R/wCAMX/xNH/CGeFf+hZ0j/wBi/8AiaANqisX/hDPCv8A0LOkf+AMX/xNH/CGeFf+hZ0j/wAAYv8A4mgDaorF/wCEM8K/9CzpH/gDF/8AE0f8IZ4V/wChZ0j/AMAYv/iaANqisX/hDPCv/Qs6R/4Axf8AxNH/AAhnhX/oWdI/8AYv/iaANqisX/hDPCv/AELOkf8AgDF/8TR/whnhX/oWdI/8AYv/AImgDarkNP067utNgvdPaH7XYaxqEiRzkrHKrXE6MpYAleGyCAeQOCK1f+EM8K/9CzpH/gDF/wDE1y9roug2Ph2e8/4RfQ7gpqN6ry3qRQxRRrcygbnKMQAAqgAHt0AoA37jS9dvVt7+aazS/s7z7RbWquWgVPLaNozJtDEsHY7tvBI4IBzWu/DOp6lDqN7cSWkGpXL2zwxRuzwp9nfeis5UE7mLZIUYDdDjnHZ/Cr6hpdjH4S8OW82oWkV15eoeVbuvmHCoq+W298g8cdPerNrb+Fr3XrjTrfwjoEqQtImEFv8AaCU4LeSVGE3AqG3dcZAHIAL134b1bVDfXl39jt7u6kslSGKZ5ESOCYSklyiksctxtxwOeTVzR/D1zpfibUL7z43sJreOG1iGd8QDyOyntjdIcegwMcc52k6Lod1qdxpuo+CNDtLiGCOf9xFFOu1ywAY+WuGyh4wQexNbH/CGeFf+hZ0j/wAAYv8A4mgCbw3ps2j+HLDTbhkea2hCO0ZJUkemQK1Kxf8AhDPCv/Qs6R/4Axf/ABNH/CGeFf8AoWdI/wDAGL/4mgA8V/8AIIg/7CVh/wClcVbVcj4g8MeH7Cxtrmz0LTbadNSsdssNpGjLm6iBwQM8gkfjXU/Z4P8AnjH/AN8igCWiovs8H/PGP/vkUfZ4P+eMf/fIoAloqL7PB/zxj/75FFAGK2hQmERiW7XcGWZldMzhmLMG47knpjqcVqBiAAI2AHQcf41jx3l61nYyi6Xm58mcNEN7fOVwT0BGOcDr0OK26AOa8Q3elvGbO68QadpF5HeQ3cQvZEOdm0jKF1JBKkZB9ay7qfQr1J7m48daCdTluLaUTq8YiRYH3ogj83OCdxPz5+btgCt3X7q7trJVsrt7SS41O3t2ljVGZVcorYDgjOD3BrI1nV9b0pr3S4tQurqSOewMNysUAnKzzFHj5UR7vlO0lQPm56ZoAmuda0nULNVvfHPh77XbzrPaT2zJGsbgEfMrTNuBBIIyOCeh5EU9/oWooV1Xx7pUwknjklS2vBAmyPJRYwJiUO8hi24k7QOABi693rFtp9vbtcalb3N/fLbLNqS2rPCpRmLKIRsP3SBuzyeQRwbGo6lP4e0fUvtOuQ3M0YjEEt15aPEZDsQy7Qq7d+TnA4U9cE0AYMp8OQvGdM8daRCsOoC+hW8uxdbX8po3BZpgzA7t3Xg5654fNcaFLELj/hOtB/tQ36XslwzxmIlEKKgjEoIULj+MnOT3wLSa/d6ppOixWWtjzZdVawur2zEL+aEilbcMqyDdsRuBxnHFRalrGuWYl0uO9u7maDVYbcXMEUAnlikiMm3DgRbgeM4AxjvnIBr2Hi/Ro4WGpeL/AA/cy7vla3mSFQPQhpXyevOfwq1/wmfhX/oZtI/8Dov/AIqrGhC8FgTfNqBlMhIGofZ/MAwOP3HyY7+vJ9q0qAMX/hM/Cv8A0M2kf+B0X/xVZNt4s8Nr4x1Kc+IdLET6faIshvY9rMJLgkA55IDLke49a7CsFTMPF+sG2WN5hpdn5ayMVUt5l1jJAJA/A0AY9tL4Bj1u+1e61rw7eXVzcpcRSyywGS32oigKxYnqm7Ixgn8apTW3geSae+TxLoCaq1+b23vjJCXibsjfNl1xkYyOuRggEXItX1648N6fcSXVwC+o3MN9d2FkJJEjSSVU2RbX4yqL0Ygde5qjqHxBkh0LSx/aFraX8jxSXLTsikxfaBE21SerAOxIyFCt04NAF2z1nT9PvruS18d+Gvs93dG4eOUKzgkKCAwnA/h4+X86v63r/hXWdIn0/wD4SvSIfO2/P9sibGGB6bh6VDDrWpN4jikN5utJ9Vl08WhjQKqrAziQNjcW3Ie+MN0zzXS/2nYf2h/Z3263+27d/wBm81fM2+u3Oce9AHH6tceE9X1y3v7jxV4eMMTRsQWhNwNjFgqzbwVQtglSDn5uRnitNZ+ApL6eZPFllHBcWdxbSQHV94zM2WYbpCB/EcYxk56gV0tzf6pF42sbEvAun3FpcOsajLuyGL5mY9PvkAD0ySc4XntL8X32mNI3iGa6LDT3urmO5tlt1gmWRF8uJtqhkJkADEsOAd3WgC/oeteHtNe6uL7xpo15d3RTe6XEUSBUUKoC729yeepPQYFa3/CZ+Ff+hm0j/wADov8A4quYsfEmrappiSpqZkjXVJoru50m3W5eGIKxjCKFfKk7Ru2k454zkdZ4Z1GfVvDllfXIAmlj+fAxkgkE4GeuM0ARf8Jn4V/6GbSP/A6L/wCKo/4TPwr/ANDNpH/gdF/8VW1RQBi/8Jn4V/6GbSP/AAOi/wDiqP8AhM/Cv/QzaR/4HRf/ABVbVFAGL/wmfhX/AKGbSP8AwOi/+Ko/4TPwr/0M2kf+B0X/AMVW1RQBi/8ACZ+Ff+hm0j/wOi/+Ko/4TPwr/wBDNpH/AIHRf/FVtUUAYv8AwmfhX/oZtI/8Dov/AIqj/hM/Cv8A0M2kf+B0X/xVbVFAGL/wmfhX/oZtI/8AA6L/AOKo/wCEz8K/9DNpH/gdF/8AFVtUUAYv/CZ+Ff8AoZtI/wDA6L/4qj/hM/Cv/QzaR/4HRf8AxVbVFAGL/wAJn4V/6GbSP/A6L/4qj/hM/Cv/AEM2kf8AgdF/8VW1RQBi/wDCZ+Ff+hm0j/wOi/8AiqP+Ez8K/wDQzaR/4HRf/FVtUUAYv/CZ+Ff+hm0j/wADov8A4qj/AITPwr/0M2kf+B0X/wAVW1RQBi/8Jn4V/wChm0j/AMDov/iqP+Ez8K/9DNpH/gdF/wDFVtUUAYv/AAmfhX/oZtI/8Dov/iq53SvEulDR2W08X6NYTrqV7IRcyxyJIjXMpGV3q2CCGBDDt1BrvK5Swi1CTw1OdPuLiF01O/ZhapEZZP8ASpsKpl+Qc4JJ7DHfNAGQ7+Hv7Dg0KLx7o404QpFcRySws74bczRsHGwtnHIYDAwBg5kWfw1Fqwu4fGmhpDFcz3kERljLrPKjKxZxINyfOx24B6DdxUWpeP2t9J0RF1WyhvZRay30jkICjSqkior4PaQk4+VVPTINav8AaOtW3iG4jvjfRC5llj0uEi2NrNtj3KpYZlDHa7ckDt7EAj8P63oukrML3xp4evHmId5o5FikkfoWdjM+eAAAAAAAAAAANj/hM/Cv/QzaR/4HRf8AxVZnhHWdRutQew1Ce8nkFjFcSG8sxbtFMSwdFG1cpwMHB7/M3braAMX/AITPwr/0M2kf+B0X/wAVR/wmfhX/AKGbSP8AwOi/+KraooA5HxB4n8P39jbW1nrum3M76lY7YobuN2bF1ETgA54AJ/Cup+0wf89o/wDvoVleK/8AkEQf9hKw/wDSuKtqgCL7TB/z2j/76FH2mD/ntH/30KlooAi+0wf89o/++hRUtFAGZHYQxW8VukCiOJ96jzGJ3ZzknqTkk89asZk/ur/31/8AWrk3l0uXTrS1ma2ilIfyrmaQKsSCQ/PHk8Zx8oHYDJwBnrgQQCDkHoaAMPVl+2Cayn0DUdRh85JhJZXMcWx1ClcMZY3BBAPHHI5qmbKFrGWzbwZrzJNMkzyNqEJmZ0IKN5pud+RtGPm4xVnxK0n2COJJ54RPq1rFI0EzRMUZoww3KQRkHsaxNce+sZtQ0nT7y7lt1utNEfmX8odHlm2yRGbJkAKhD1JAfjqBQBqiEGxmspfCPiG4hmYMwudSimZSOQVZ7klCDyCpBBGaW2iW1MbR+Ddcd45vPEkt7BK7OFKgszXJLYBIAJIHao7uC90zS7a2uHl09L7UI4J5Y9WnuykRU9JJQDGWYBOOm7IOekupXcOh6bqdjY6lfTTkxRxo3m3Mls0vGVY7ncgBpNuSQB0AIoAZfW0eozNNceDddErTLOXhvoImEioUDApcgg7WI46jGegprWULaelifBmvCNJ/tIdb+ESmXn5zKLneTg4yW6YHQCqQv31LT9E01rzUU8rWTZ3DGSa2nljEErxlz8r5K+Wxz1I71FqMmoIZdJsru5uLeLW4YITJqEsbkNDveJp1y+AxzzkjOOwwAb9heXWmwtFB4W8QOrNuJuL+Cds+zSXLEDjp0q1/buo/9Cnq/wD39tP/AI/VjQrKexsDHcRGKRpCxU6hNedgOHlAbt0xgfia0qAMX+3dR/6FPV/+/tp/8frJttZvx4x1KQeGNULNp9opjElruUCS4wT++xg5IGDn5TkDjPYVgqsz+L9YW3kWKY6XZhHdN4U+ZdYJGRn6ZFAFB4lexSyHgzW44o5nnjMV7bxujuzMxDrchhku3Q9CR04qZ5DJpcWmHwTqos4TGY4UmtFC+WwZMYn7FQfw5rItm1S78NaWGu76+/4ml2lykV4sFzdIsk4UK+5Om1SVUr8qnHAxVMalqMuk2OuXk5urOzsRJPbw6tLbzkGVgsu2MYlyqDbuIDHdQBvoqx6w2rL4K1gXbEtu+0220MVClgn2jaGKgDcBnHGcVo/27qP/AEKer/8Af20/+P1hw311/wAJXFN9tuDLLrM1k9sZmMYgW2LjEedoOQjbsZ+frg4rrP7Qh/tD7BsuPN27t32aTy8f9dNuzPtnNAGPJfXEt/Bfv4O1c3FvG8cT+fa/Kr7Swx5+DnYvX0qvpo/smWSWy8GayjyKEy91bSbEBJCIGuDsUZPyrge1WLuS/i8fadGb9zaXFlclbZV2opQw4Zu7Nl256AYAAOS3KWU+u/Z5tNF/LDc3mku8t9dakHheYyIiSxMpbylYO+3AXoPl4oA6CaFJ4GhbwZriBrhrgtFewRuJGzuIdbkMM5PAOOavW2qXdnaxWtt4O1WKCFAkcaSWYCqBgAfv6wDLdTRR2EcN8ostReK+tbbWneWc+RvXyp5XRiBuUsuVxg9e/TeEry4v/CunXV25kmkhBLk53js2cDORg596AG/27qP/AEKer/8Af20/+P0f27qP/Qp6v/39tP8A4/W1RQBi/wBu6j/0Ker/APf20/8Aj9H9u6j/ANCnq/8A39tP/j9bVFAGL/buo/8AQp6v/wB/bT/4/R/buo/9Cnq//f20/wDj9bVFAGL/AG7qP/Qp6v8A9/bT/wCP0f27qP8A0Ker/wDf20/+P1tUUAYv9u6j/wBCnq//AH9tP/j9H9u6j/0Ker/9/bT/AOP1tUUAYv8Abuo/9Cnq/wD39tP/AI/R/buo/wDQp6v/AN/bT/4/W1RQBi/27qP/AEKer/8Af20/+P0f27qP/Qp6v/39tP8A4/W1RQBi/wBu6j/0Ker/APf20/8Aj9H9u6j/ANCnq/8A39tP/j9bVFAGL/buo/8AQp6v/wB/bT/4/R/buo/9Cnq//f20/wDj9bVFAGL/AG7qP/Qp6v8A9/bT/wCP0f27qP8A0Ker/wDf20/+P1tUUAYv9u6j/wBCnq//AH9tP/j9H9u6j/0Ker/9/bT/AOP1tUUAYv8Abuo/9Cnq/wD39tP/AI/XO6VJJqGjtHP4W1mXy9SvZEltruCF42NzLkB1nVgRkqccHB6jBrvK4cW1/e6Jb21hcRRs2t37SQtfyWjToLi4+RXjBbrhjgdFoA0C2dMt9N/4QnVVtLZo2iiWa1UIY2DJ0uOxUH371EkMcepNqA8E6yZ2LnDXVu0al+HZYzcbFLc5IAJyc9TnDn1uW8t1v7W6vLOO0020ns4jdu++R52Rw5z++ztVQWz97I5ar9pc6pa+MrdZHup/tmo3MTyi8Elu1uI3ZVWIMdjIVQMSoOcjJ3UAaOlk6P5psvButK0oUO0l3byttXO1QXuCQoycKOBk4HNX/wC3dR/6FPV/+/tp/wDH6reFZL432vwX9895JBfqodl2qoMETEIv8K5JwOT6knJPR0AYv9u6j/0Ker/9/bT/AOP0f27qP/Qp6v8A9/bT/wCP1tUUAcj4g1a9uLG2il8O6lao2pWOZppLYquLqI87JWPPTgd/xrqfNf8A595PzX/GsrxX/wAgiD/sJWH/AKVxVtUARea//PvJ+a/40ea//PvJ+a/41LRQBF5r/wDPvJ+a/wCNFS0UAZbahZJ5O7UYV88ZizKg8z/d9fwqzsb/AJ6N+n+Fc7KJm0SO28u7Ers5SEWzFZ8udvmHb8mep+ZcZPTpXS0Ac9rszRW9yt5YaHc6Z5imR9XvfJQPhcDaYnX0wc9e3rnpdW//AAjr7NG8Gf2J5nz41UfZt+R1/wBH25zj9K0fEqyfYI5UgnmEGrWssiwQtKwRWjLHaoJOAOwrE1y3uNQm1DVrO11G3tZbrTQGSycTkxTbpJliZCx2qyjlDnZ0IAoAt6dc2/8AZN6dM0XwZ/Z2P9M+zaqPJxj/AJabbfb09e1WdLkmbT459J0LwobK3kaSOS01Q+XG+CGYFbfAOCQT6E0y68y80y2mWTV9WhstQjuLmO908wyNGFPCJ5Ue/a218AE/Lxk4FP1OebVbS9h0vRJl/tKWKBprmOW389cEy7wU3RqI12ByOS2AOBkAi1a5Etil9rOi+EHtLpkZJ7zVcxynadhDNb4Y7S2PYnFRy3Vv/wAI5D52jeDP7D3nyd+qj7Luyc7c2+3Od3TvmoHGo6eumQX2lzpHputmUCyilukWB4Ziu0rGCQrPs+7xgeoJj1G2uZzLqlvBqVna3OtwzoYLJjOirDseXyijEZYY+ZMkAHHIoA1tAubr7E58OaL4W+y+Yd507VT5e/AznZb4zjHvjFaf2rxV/wBAbSP/AAay/wDyPU+hXAnsWxd6jdFXIMmoWZt5D042+XHke4X8a06AMX7V4q/6A2kf+DWX/wCR6yba58Sf8JjqRGk6WZTp9oGQ6nJtC+ZcYIPkckndkYGMDk547CsFYEufF+sQS7tkml2atscqcGS66EEEfUUAZl9cyDRmGoaL4TGl+c27z9V/ceZvO7Obfbu37s98570X1zJ52myahovhPzdw/s5rjVfmzkY8om365242+1UrXS5dP8M6XIlvPZy6dql28Krpz3CRq0k4UtChDlSrDBXplT0zWZ/ZevafaW7GC6M02mxxQWwslnjeTzpHMM3ysI02vGCcqPl4b5aAOmS6vf8AhIJPL0bwx/bPk/vNuqt9p8vjr/o+7b09ulaP2rxV/wBAbSP/AAay/wDyPWHDZ3f/AAlcUH2K4EkWszX0lyYWERga2KDEmNpOWVduc/J0wM11nmX/APaGz7Nb/YtufO+0N5m708vZjHvu/CgDIkude+3QGXRdB+17H8ktqr+Zt+Xft/0fOPuZx7Z7VnWVw0ianHYaL4SZGLDUlg1XIJOd3nAW/wDvZ3e9X7vSwvj/AE3UYraQ+ZZXUc9wNxA5h2Ln+EcOQBjncepJrkY9D1Z7CW0s47h7Ww0z7Ksc2nmBz++jbYQxKzMEjfLL8rbhjrQBsNd2x8Opu0fwZ/Ygk+XOrD7Nvyen+j7c5zW7Fd+JjChh0fRTGVGzZq0m3HbH+j9K5sRXpQao320ta6m72t1NozPLMrQBC80EYjfrlFYAHCrnjk9R4Ss7mw8K6da3iMk8cI3I2Mpk5CnHGQCBxxxQA37V4q/6A2kf+DWX/wCR6PtXir/oDaR/4NZf/ketqigDF+1eKv8AoDaR/wCDWX/5Ho+1eKv+gNpH/g1l/wDketqigDF+1eKv+gNpH/g1l/8Akej7V4q/6A2kf+DWX/5HraooAxftXir/AKA2kf8Ag1l/+R6PtXir/oDaR/4NZf8A5HraooAxftXir/oDaR/4NZf/AJHo+1eKv+gNpH/g1l/+R62qKAMX7V4q/wCgNpH/AINZf/kej7V4q/6A2kf+DWX/AOR62qKAMX7V4q/6A2kf+DWX/wCR6PtXir/oDaR/4NZf/ketqigDF+1eKv8AoDaR/wCDWX/5Ho+1eKv+gNpH/g1l/wDketqigDF+1eKv+gNpH/g1l/8Akej7V4q/6A2kf+DWX/5HraooAxftXir/AKA2kf8Ag1l/+R6PtXir/oDaR/4NZf8A5HraooAxftXir/oDaR/4NZf/AJHo+1eKv+gNpH/g1l/+R62qKAMX7V4q/wCgNpH/AINZf/keuZtbi6Hhqf8AtnSfDj2H9pXhY6jqZWMSfapcjDQEcHIB6kc4GcD0CuDaOZtMsZVjuVig1zUXkurSBpprb99cAMqANnOdpyjABug+8ADSl/tCQ2FzN4e8MuYiFsZX1JjsJHAjP2bjIA+76Uu7UrPU5r3+wPDUF/LEXmn/ALTZZXjGMlm+zZKjC9eOBVGLRZf7I8JSvpRgubO5iUxIHYW8e1+xZtv8OSST0BJxWtHpgg8ftfRWzhZ9OYSzkEgv5i4XcfYcD68UAVNL1681Ce4/si18L3MrEST/AGTWy7E4Chm22/oAMn0FaX2rxV/0BtI/8Gsv/wAj0/QbeVje6ldRNHdXk7jDqQVhRmWJee235vq7eta9AGL9q8Vf9AbSP/BrL/8AI9H2rxV/0BtI/wDBrL/8j1tUUAcj4guPED2Nst5pmmwwHUrHc8OoySMP9KixhTCoPOO4/HpXU7p/+ecf/fw/4VleK/8AkEQf9hKw/wDSuKtqgCLdP/zzj/7+H/CjdP8A884/+/h/wqWigCLdP/zzj/7+H/CipaKAMSTVrSGxiu5BMolkEax5y+7dgjrjjByc44rQ8tfVv++jXPyaDNLZqP7SaKcDasaMpijTzN+1dyk8AAds7R2GK6ASIAAZASB1JHNAGLqxFkJr2XX9S06DzkhEVpbxzb3YKBgGJ3JJIHHHA4qkb6BbKW7bxprqrDKkMkTWEImV3ICKYjbb8tkY+XnNXtetrq7sVaxtXu3t9Tt7gxRuisyoUZsFiBnA7kVk6zouq6wb3U/7KuojNPYKtmtzGk7RwSl3bcr7Vb52Aw+flByCeAC4JsWEt9L4u8Q28ETBSbnToYWZjwAqvbBmJJAAUHJ461Jb/wCk2dzdr4z1qOO0BacT2ltE8QA3ZZHtww455HIpj6fdvYW8tnpOpRSWF8l0LbUr5Z3uBtZSEcyybSA2QCQMgdMk1LqMWu61aywJpsenxXU0SH7QEkdUXLO0oSTDK2FQKrZwSSeeACGedLfTbPUG8Z649vfsq23k2MEryEqWACLbFs4VjyOMc0xr2BbBb3/hM9dMbXH2bYthCZRL12GIW28HAzgr0IPQioZNK1+xNmr2P9pJY6ybxWs9kIaOSKXcFSSTjbJIeC3QjHoGalomp36yalJpV2GudVhuGsoLpI50ijiMed6yKoYnn5X6Ec9aANewsrvUoGmg8U+IEVW2kXFhBA2cA/dktlJHPXGPyqz/AGFqP/Q2av8A9+rT/wCMVPoSGOxaM2Oo2YVzhNQuhcSN053eZJx7E9uladAGL/YWo/8AQ2av/wB+rT/4xWRBo98PF+pKfFGqKU060ZpfLtckGS44P7nGBgngA/Mck8Y7GsKOGK58Y6vBPEksUml2aujqGVgZLrIIPUUAZhvbY6bBqMfjjWJ7a5laGBoLW3laZ1LAhFW3LN91uQCMDPTmmXd/DZW8dxL4w8RNbyxrIs0OmRSx4Y4GWS1IBz2Jz7UJoeoW/h+zBs7wXtrqN1Ohsp4RNGsksxDKJMxtlXGQxGAc9RirWlaDfW9joNheKHitTJc3XzhgJc5ROeWwzkg+sYPpQAiESau2kr411g3akqV+zW23cFDFQ/2faWCkNtBzjnGK0P7C1H/obNX/AO/Vp/8AGKyotG1P/hJIka0xaQarLqP2wyKQytAUEYXO4Nuc9RjC9cnFdL5d/wD2hv8AtNv9i248n7O3mbvXzN+Me238aAMV7Z01WPSm8bap9uliMywCK0LbAQCx/ccDJxz1wcdDVG2vob2Gaa18Za9OsKh/3enwsZFLbd0YFtmRc/xJkVrXWku3jDTtRhtUEC21ytzKNoJd/JCZ7txGRnnAUe1Y3h7QtU03UTdC1u4obDTpLW1tbm4ikBJZWCxsmDsHlgBpMMd3PSgAGp27QGb/AITLxCP3/wBnER0yIStIF3FRH9l3nC8nA4Fa1rpl1e2sV1beMdVlhmQPG6xWmGB6H/UVTu9CubTQ9J+zwXs1/ZuZJJrKWFJvMdW8x8Sjy23Mxzn1yORWt4Z06fSfDllY3JBnij/eYYsAxJJAJ64zjPtQBF/YWo/9DZq//fq0/wDjFH9haj/0Nmr/APfq0/8AjFbVFAGL/YWo/wDQ2av/AN+rT/4xR/YWo/8AQ2av/wB+rT/4xW1RQBi/2FqP/Q2av/36tP8A4xR/YWo/9DZq/wD36tP/AIxW1RQBi/2FqP8A0Nmr/wDfq0/+MUf2FqP/AENmr/8Afq0/+MVtUUAYv9haj/0Nmr/9+rT/AOMUf2FqP/Q2av8A9+rT/wCMVtUUAYv9haj/ANDZq/8A36tP/jFH9haj/wBDZq//AH6tP/jFbVFAGL/YWo/9DZq//fq0/wDjFH9haj/0Nmr/APfq0/8AjFbVFAGL/YWo/wDQ2av/AN+rT/4xR/YWo/8AQ2av/wB+rT/4xW1RQBi/2FqP/Q2av/36tP8A4xR/YWo/9DZq/wD36tP/AIxW1RQBi/2FqP8A0Nmr/wDfq0/+MUf2FqP/AENmr/8Afq0/+MVtUUAYv9haj/0Nmr/9+rT/AOMUf2FqP/Q2av8A9+rT/wCMVtUUAYv9haj/ANDZq/8A36tP/jFYGl276b4bvNRvfF+o2Npb3175j+Xa7Ri6lGeYSSWPOB1LYA6Cu5rjxprar4B1q0ht0nuZJ9VW2VsZEjTXCjBPAPzEZ46mgCS7kSxube3ufGusJJcKGTFrbMqgkKpZhb4QEkAFiMngUJLHJqkmmjxtrAuIywYta2wjJUAsokNvsLAHJAJI5z0NQa3oeqz3ky2tmZ01GxtbV5DIgW2MUrMxYE5IKucbQeV5xnNLa6RrMfig3DWK7Vu7iV7h3j8iWFkYRqiDLLJkqGfaCdrZZhgUAEV/bzW006eNdc2wlNyNYQLI2/hNqG23OGwcFQc4OOlXtNtZtWtftNl4x1h4w7RsGt7VGRlOCrK1uGUg9iAapQjX7S91PVrTQblJLmKJBaz3UUrNKGbc4Jk4jVW4TcuTnATJNbvh63a300iS1ureaSVpJvtbRmSRyclj5bMoB7AHgADFAEP9haj/ANDZq/8A36tP/jFH9haj/wBDZq//AH6tP/jFbVFAHI+INJvbextpZfEWpXSLqVjmGaO2Ctm6iHOyJTx14Pb8K6nyn/5+JPyX/CsrxX/yCIP+wlYf+lcVbVAEXlP/AM/En5L/AIUeU/8Az8Sfkv8AhUtFAEXlP/z8Sfkv+FFS0UAcy+s3QhtJXkigjdWMsxtZJEBDBQDgjy+5O48dD0Nb1ZbaOrWgtPtF2IGLGZMx/v8AcctuOM85P3SODWjvb/nm36f40Ac94iiiiRrwR3c1xLeQ2kcceq3FpHl9qgt5ZxwW67SfyFY2oXFrpNvdpf299Be2stsrK3ia8FuUmfYsnmkggAht2U42+4NbHiG70t4zZ3XiDTtIvI7yG7iF7Ihzs2kZQupIJUjIPrWXdT6FepPc3HjrQTqctxbSidXjESLA+9EEfm5wTuJ+fPzdsAUAOgNjNpguI5Jb2ea5W1to9O8V3dwjyEZw75XZgAk8HgdCcCrzabDZ6Xe3Wp22rQS2i5CQ+ILyVJ8j5QjF1JJOF5Uc+tR3OtaTqFmq3vjnw99rt51ntJ7ZkjWNwCPmVpm3AgkEZHBPQ8iKe/0LUUK6r490qYSTxySpbXggTZHkosYExKHeQxbcSdoHAAwANnjt/wCzNKmtbfUpLzULs2b283iO8jWCRVkLguGYnBiYfd568VWvrqz06zf7XFe297DfJaTpP4nvEt03oXWTzd33SuOqg5yO2S6U+HIXjOmeOtIhWHUBfQreXYutr+U0bgs0wZgd27rwc9c8PmuNCliFx/wnWg/2ob9L2S4Z4zESiFFQRiUEKFx/GTnJ74ABqaFpFhq9gbprydx5hVW0/wATXl1GQAP49y85zxj055rS/wCEU07/AJ+dX/8ABzd//Haq2Hi/Ro4WGpeL/D9zLu+VreZIVA9CGlfJ685/CrX/AAmfhX/oZtI/8Dov/iqAD/hFNO/5+dX/APBzd/8Ax2sUaBp0HinVt8usNHBptrJiLU7tpGy9zkcSbm+6MLzg5wOTna/4TPwr/wBDNpH/AIHRf/FVk23izw2vjHUpz4h0sRPp9oiyG9j2swkuCQDnkgMuR7j1oAz4pLW603Tpraz1YXeo3k9rFb3HiK7RUMTSAl3V25xGThQ3Jxk9ahkvbAx6dNa2urzR3aBm3eILxWJ37WSEBiJXGGYjK8AHPPFp7jwv/wAI+mlL4t8OThbua4YXvkzwyCSR32tGXB438EMOVHYkVRlsvCn2VbS28caRHDLZpZ3hknid5FDs5aMhwI3JducMPu8ccgGjHHYProsjFqws3u3so7ka/eFmmWPzCCm/hcBhndnK9MHNb/8Awimnf8/Or/8Ag5u//jtYEd34YTXlvj400c2cd297Hai5iDCdo/LJL7+VwWONuct1wMVrf8JH4P8A7Q+3/wDCU2Hm7du3+2B5eP8Arnv2Z98ZoApS2Wmx+J4NE8vXsS28kxuW1i8VMpsyqjzMtxIMkcdsk5C5Fle2d1Ytcmx1jdPYG/soYfEN5I80YYL84DDYcsmQN2MnnjFbtxr3hW416x1X/hLNIX7HBPD5f2yI7/MMZzndxjy/TnPtWB9j8Iyi9efxf4fE9xF5cctt5EPPmLIXlAfEjMyJu+6CARgZoAmhkguYLNLe1v5bu8unt4SPE159mkCRmQyJNnLLgY4TqCO2a3NH0fSdZ0i21GGfWFS4QNtOt3Z2nuMiXBwc1iSSeHZrK6Sfxj4ZuLi8u/tU4uEhktmIQIAIjJkYCqc785BzwcVuaR4g8I6PpNtp8XinSpFt0C73vosue7HnqTk/jQBc/wCEU07/AJ+dX/8ABzd//HaP+EU07/n51f8A8HN3/wDHaP8AhM/Cv/QzaR/4HRf/ABVH/CZ+Ff8AoZtI/wDA6L/4qgA/4RTTv+fnV/8Awc3f/wAdo/4RTTv+fnV//Bzd/wDx2j/hM/Cv/QzaR/4HRf8AxVH/AAmfhX/oZtI/8Dov/iqAD/hFNO/5+dX/APBzd/8Ax2j/AIRTTv8An51f/wAHN3/8do/4TPwr/wBDNpH/AIHRf/FUf8Jn4V/6GbSP/A6L/wCKoAP+EU07/n51f/wc3f8A8do/4RTTv+fnV/8Awc3f/wAdo/4TPwr/ANDNpH/gdF/8VR/wmfhX/oZtI/8AA6L/AOKoAP8AhFNO/wCfnV//AAc3f/x2j/hFNO/5+dX/APBzd/8Ax2j/AITPwr/0M2kf+B0X/wAVR/wmfhX/AKGbSP8AwOi/+KoAP+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8do/4TPwr/0M2kf+B0X/AMVR/wAJn4V/6GbSP/A6L/4qgA/4RTTv+fnV/wDwc3f/AMdo/wCEU07/AJ+dX/8ABzd//HaP+Ez8K/8AQzaR/wCB0X/xVH/CZ+Ff+hm0j/wOi/8AiqAD/hFNO/5+dX/8HN3/APHaP+EU07/n51f/AMHN3/8AHaP+Ez8K/wDQzaR/4HRf/FUf8Jn4V/6GbSP/AAOi/wDiqAD/AIRTTv8An51f/wAHN3/8do/4RTTv+fnV/wDwc3f/AMdo/wCEz8K/9DNpH/gdF/8AFUf8Jn4V/wChm0j/AMDov/iqAD/hFNO/5+dX/wDBzd//AB2j/hFNO/5+dX/8HN3/APHaP+Ez8K/9DNpH/gdF/wDFUf8ACZ+Ff+hm0j/wOi/+KoAP+EU07/n51f8A8HN3/wDHaP8AhFNO/wCfnV//AAc3f/x2j/hM/Cv/AEM2kf8AgdF/8VR/wmfhX/oZtI/8Dov/AIqgA/4RTTv+fnV//Bzd/wDx2uXtdMt7Dw7PeRm8fZqN6JHn8QXNrDEi3Mo3Mwc8nAH3SSTknqa6j/hM/Cv/AEM2kf8AgdF/8VXO6V4l0oaOy2ni/RrCddSvZCLmWORJEa5lIyu9WwQQwIYduoNABey6TZ6XpF35WuGbVGgxbNrd2rQpIyKWb95/CXUY7kgepEz6ZNFr66a1lfSQskkvmQeJr1pFjXhSyttUFiQAN/ryQpNZs+m+BJdKs7RfGFkk9sIFa4TVtnmLHJ5mNiSKoyS2DjK7sjoK34/EHhmG+1G+j8WaL594iJGzXUREQRTtB+f5huZm7fex70AY8o+xpfR3um6ot1awQzhIPEl5Km2RynztuBTbtLMdpAUEgnFa2haRY6xpi3kh1aAl2UbNdvJI3AJAdH3jcjDBDYGQax45tFfTJbW88deHZpnniuhcoUVpJkYMGl3TNvHyqNo2gAALgAAa+ia74Y0m1nSXxbo089zcPcTOl1FGm9jztXecD6knOTnmgDS/4RTTv+fnV/8Awc3f/wAdo/4RTTv+fnV//Bzd/wDx2j/hM/Cv/QzaR/4HRf8AxVH/AAmfhX/oZtI/8Dov/iqAMvxB4esrOxtriKfUmddSscCbVLmVebqIcq8hB69xx1rqfIT+9J/38b/GuW8QeJ/D9/Y21tZ67ptzO+pWO2KG7jdmxdRE4AOeACfwrqftMH/PaP8A76FAB5Cf3pP+/jf40eQn96T/AL+N/jR9pg/57R/99Cj7TB/z2j/76FAB5Cf3pP8Av43+NFH2mD/ntH/30KKAOXOr3bCGMyXOIYpJbmSCOPeNrlcNu44wc7QST93jr0gIIBByD0NZ7aNZtFHEbfCxhlGJ3G4McsGI+8CeSDnNXsyf3V/76/8ArUAZWs6jeabZlrAwLPcajBbhp4y6qJNik7Qyk4z6iszVfFOsaOt5ZTmzkvbeWz2XEVpIyNFPIUz5IcsWUq3AY54x1xVrXJbG4SSxvH1WCRLmO5jm0+wln2Mm0r8widc5XoR/Os+ZNHuLaZZ7rxNJdTTwzteto8/mhomDRgD7PsABHTbzk560AaC69qg06LbJFcXl5dra27S6ZPZJGSpYsySMWcBVJ4IyRjI6i/Pfatpek3s1+trc3EeFtXgRo1ndsKilCzFfnIX7xznPHSseS60+5smtr2+8TXbiRZYbh9FmSS3dejIUt1H/AH0CD0PBIqFo9AucnURr+pNJKkk5utEnYThAwRHUQBdiliwAA55OecgF+fX9WfTtIjtzZwahdagbG6aWF5I43RJSxVQ6nBMYIy3Rh1qrqHirV9Phks5fsv26DUY7WSeKzlmR45Iy6usKtv3diu49M98CtJaeHF2/2cuvaUqXa3caWWhzKkcgjaMlVa3K8q3PHUA8c5kkXR5LRY/tPiYXQvBeNff2POZnkC7RkG32YC4AAUDAHfJIB02hXV1eWBmu5hM5kIUjT5rPAwODHKxbrnnofwrSrm7DxBa2cLRz3HiC/YtkSXGiThlHoPLgUY/DPNWv+Er07/n21f8A8E13/wDGqANqsFZHi8X6xJFC07rpdmViQgFz5l1wCSB+ZqT/AISvTv8An21f/wAE13/8arJtvEtgPGOpTG31Ta+n2igDSbotkSXBOV8vIHzDBIwecdDgAY3i7Uf7A0+8nOnadJdX9xbT3U+57e1WN5VBPK5z5YUElQSe3SqV18Q7mG2hvGNjawpZfaXSdWL3jLIyyRw/MMFQmeQxG9cjHJvx3Wl22mJZWVx4ltPLuJbhZotIud+ZHdmBDQFWXLnAKnGAeozUMiaC9nb2CP4kisYoliktV0q6Mdwqtu+fdCTknOSpUtnknjABoReI79vECRNHbnTpdQk05FVW81XWIyby2cEEoy7dvoc9q6euNSXQk1z+1NviBsTNcJbHSLrykmZAhkA8ndnbkYzjknGTmr/9seH/AO0P7R/sm/8Atu3Z9p/sC68zb6bvKzj2oAsz6xexeLrXSfsaLZz200omZ8vIyGP7oHAX95jJ5JB4AALcxb/EG/fTriVvsE12bFroQRI4+wFZER0n+YklBIGbAQ4VuBkGtubWNHn1e01NodbE1pFLEijR7vaRIULZ/dZz+7GOfWqMMmkxtPK934omnkh8iGeTS7rzLZM7sIwgGecEl9xO0ZyKAIj43uWhWJdQ0lVW+NtJq7Rt9k2+SJVYDzOCSdnMmMg88gV1Ggaoda0K01FoxG86ZdBnAYHBxnnGQetc5HNpkNo8cF74nhupZzPNeppE/mysV2/MPs+wjaAANvG0Ec81pafrmjaXp8Fja2msLBboEQHR7wnA9T5XJ96AOiorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDaorF/4SvTv+fbV//BNd/wDxqj/hK9O/59tX/wDBNd//ABqgDariY9bm0jRIY7ZkSa81m/jDvbSXG0C5nYkRR4ZzwBgEYySeAa3P+Er07/n21f8A8E13/wDGq5rTtQ0290objrdrc2+qXs0Fxa6VcM0e64m9YWU5ViCpBwewI4ALk3jC/KRz2psJ4bayt7u7KK7CYSyFMRkkbMBGPzA9QOOTVmw8UzXniWSzae0itVuJrdYnglVyYgckTf6tmypPl8EL82eMVmtZ+GzHaxIviKOGGGOGWNdJusXSI+9RITDn7xY/KVzuYHg4qwDoH9p/bHj16SESyTLZPo1yYFlkUq748ncSQzcFiPmPFADj4yvZv7R8i2hjUT2kOntKGO8TvsEjgH7v8QAwduM4J439B1C51Czm+2LGLi2uZbeRogQj7GwGAJJGRg4ycdMnrXLiw8IRNetZ6Xqti12IubXQbiPyWjbcjJiDg7gDzkEgcVqaVq+kaRZm3hi1yUvI8sks2j3ZeR2JLMcRAck9gAOwoA6eisX/AISvTv8An21f/wAE13/8ao/4SvTv+fbV/wDwTXf/AMaoAPFf/IIg/wCwlYf+lcVbVcj4g8Q2V5Y21vFBqSu2pWODNpdzEvF1EeWeMAdO556V1Pnp/dk/79t/hQBLRUXnp/dk/wC/bf4Ueen92T/v23+FAEtFReen92T/AL9t/hRQByiWdjqGl2Fu9pBI80rxJK0YOIlZiShxlVIHyjtuHXrXTgBQFUAADAA7VVe+s40hd9QhVZ/9UTIgEn+769R0qxsb/no36f4UAYXiVpPsEcSTzwifVrWKRoJmiYozRhhuUgjIPY1ia499YzahpOn3l3LbrdaaI/Mv5Q6PLNtkiM2TIAVCHqSA/HUCui1C2vr37RaLoulapZs6s66hclPmCr/B5Lggcc5/D1rjS9QXTm01fB/hoWLNuNsL1vKJ652/ZsZ4HagCvdwXumaXbW1w8unpfahHBPLHq092UiKnpJKAYyzAJx03ZBz0l1K7h0PTdTsbHUr6acmKONG825ktml4yrHc7kANJtySAOgBFPt9L1CztZ7S18H+GoLe4GJoYr1lSUdPmAtsH8afbWOrWUUUVp4U8O28cMhkiSK/ZRG5BBZQLbg4JGR2NAGOL99S0/RNNa81FPK1k2dwxkmtp5YxBK8Zc/K+Svlsc9SO9RajJqCGXSbK7ubi3i1uGCEyahLG5DQ73iadcvgMc85IzjsMbl7p+qakGF94S8OXQdlZvPvmfcVBCk5tuoDED0yfWmvpeoyacmmv4Q8NNYxtuS1N6xiU5JyE+zYByT27mgDX0KynsbAx3ERikaQsVOoTXnYDh5QG7dMYH4mtKubsLXWdKhaHTfC/h+yiZtzJb6g8ak9MkLbDngVa+1eKv+gNpH/g1l/8AkegDarm7pYm8S64Li7ks4f7Ks/MnjfYyL5lznDfw8cZHI7EHBq19q8Vf9AbSP/BrL/8AI9YbJrd/4n1W3u9A0W6WTT7QS289+7RlRJcFTzbnJzngjjAOTngAYIb2P7BazXWpW+l6nqjCNZruRbiOEW7sqtIW8xd0ibtpO4AhTg5UZbaxqNxpUN5LqdyJLPSYLm2kSUoLiVp2Ql1BAkyEjGCCPnOBzXRJo97HYyWEfgzwwlpKweS3W8YRuw6Er9mwTwOfap5rXWbiS2ln8L+H5ZLM5tmfUHYw9PuE23y9B09BQBmw311/wlcU3224MsuszWT2xmYxiBbYuMR52g5CNuxn5+uDius/tCH+0PsGy483bu3fZpPLx/1027M+2c1jLBri6g2or4Z0AXrp5bXI1F/MK/3S32bOOBx7VZ+1eKv+gNpH/g1l/wDkegCpcWsk3imBtPvr95objzL4m4Y28UXlnEPl/c3HKtgDcB8xIyu7loNX1GLRWuF1K6M19pK3V3vnLfZ5GmCsyZJEYAZxgYA2dOK6QaTfjUf7RHg7wyL3dv8AtP2xvN3eu77NnPvUsVnrEH2ryfC3h6P7YS1zsv3Hnk5yXxbfNnJ6+poAxWN87y2MNzfXdhZaxJD5MOoGO5mj+zq+1ZXdWbbIzZ+cHA7hcV0/hK8uL/wrp11duZJpIQS5Od47NnAzkYOfes9tM1J9NTTG8I+G2sUO5bU3rGJTknIT7Ngcknp3q6tx4oRQq6Jo6qowANVlAA/8B6ANuisX7V4q/wCgNpH/AINZf/kej7V4q/6A2kf+DWX/AOR6ANqisX7V4q/6A2kf+DWX/wCR6PtXir/oDaR/4NZf/kegDaorF+1eKv8AoDaR/wCDWX/5Ho+1eKv+gNpH/g1l/wDkegDaorF+1eKv+gNpH/g1l/8Akej7V4q/6A2kf+DWX/5HoA2qKxftXir/AKA2kf8Ag1l/+R6PtXir/oDaR/4NZf8A5HoA2qKxftXir/oDaR/4NZf/AJHo+1eKv+gNpH/g1l/+R6ANqisX7V4q/wCgNpH/AINZf/kej7V4q/6A2kf+DWX/AOR6ANqisX7V4q/6A2kf+DWX/wCR6PtXir/oDaR/4NZf/kegDaorF+1eKv8AoDaR/wCDWX/5Ho+1eKv+gNpH/g1l/wDkegDaorF+1eKv+gNpH/g1l/8Akej7V4q/6A2kf+DWX/5HoA2qKxftXir/AKA2kf8Ag1l/+R6PtXir/oDaR/4NZf8A5HoA2q4m6a9i+HGuT2N69nLBPqkvmxrl8LPOcKf4SSBzgnGcYOGG59q8Vf8AQG0j/wAGsv8A8j1jaA+vz6JdW50TSLi3lvr5ZEm1GTDZuZd6lfIIK5JHuOSBnAAK/iC/vI76aUX1xbmw0+zntVSZlWWSSZlbcoOHztRcNnG7jk1JLr91N8Qbe2kkvrK0SK6hSN7WVI22iP8AfFiuxhndg5IAAOQXxWpNba1cz29xP4Y8PyzWpzBI+oOzQ/7pNtleg6elSs3iN54530DRGmiBCSHU5CyA4yAfs/GcDP0FAHPSLfxyaro1lqpDXEVpLaS3GqSOrI0pVj52CyPIBgKoKjgqTkgTylL7w2YYxf21/DfPp8Yj1e5kUTMwBcyb1aRVHzYbkbWAAq/FpmpQWs9rD4Q8NR29yczxJesEl/3gLbB/Gp4YNctreC3g8M6BFDbtuhjTUXVYjzyoFtgHk9PU0Ablpbi0tIbZZJZREgQSTOXdsDGWY8k+pqasX7V4q/6A2kf+DWX/AOR6PtXir/oDaR/4NZf/AJHoAPFf/IIg/wCwlYf+lcVbVcj4guPED2Nst5pmmwwHUrHc8OoySMP9KixhTCoPOO4/HpXU7p/+ecf/AH8P+FAEtFRbp/8AnnH/AN/D/hRun/55x/8Afw/4UAS0VFun/wCecf8A38P+FFAHHSRXQthm1uF328yR7IGYzkuSFkGDsDDBP3fvHBXGB1qklQWXaxHIznFZL63bJEsgt7p/kMkoXGYVDFSW+bnkH7uehrUCKQCCxB6HcaAOb8ZfY/7IT+0PI+x/2vaef9ox5ezdHndnjGOua5zWl0s2epf2TJp6eH2vNNAbar2Sy+d+9O0EKV2+XvAIB5yQc11urXt9pYmuotTtLS1MyRbJdNmu5HkYKAB5cik5yBjafr6Uj4h1FbKW7bxBpyrDKkMkTeH7oTK7kBFMRm35bIx8vOaAKDJpEegottdaHc6b/aEZ1RtFt1hiEG08ShXfI3bdxJxtzkYzVm5vdGj0i+sfC8JkjvpY7aMWDxiF2cHzBB8wUOsasx6DOOc5xaGsawLCW+l1uxt4ImCk3Ph27hZmPACq8wZiSQAFByeOtSW+p6zc2dzdrr+lRx2gLTifRLiJ4gBuyyPOGHHPI5FAHPXlxp66fo+la7axWlrputiJ4NSMRVIDbzNDu+ZkwAQoOTynrUGqJpracwtJtOi8PtrsX2V7mMSWS/uj5m1dyqY9+ehA3bveukn1rVbfTbPUG1/TXt79lW28nQbmV5CVLABFmLZwrHkcY5pjeINSWwW9/wCEg04xtcfZti+H7oyiXrsMQm3g4GcFehB6EUAavhNdNj0p00y50a4j84l20eBYod2B1VXb5sY5z0xW5XOWE3iPUoGmg1axRVbaRcaBcwNnAP3ZJlJHPXGPyqz9l8Vf9BnSP/BVL/8AJFAG1XK6rNpkGt6/LrLqunrpNn5+5iAy+bc/KcdQemO+cd60Psvir/oM6R/4Kpf/AJIrBml1zTfEer3l1rWlxLBptq80p0uVl2eZcYwonzkHdk5OcjgY5AMyNdEFjaXDy6YNAuNXMl5aQzRy2tov2dhGj7SUBMgRiB8u9hjPBN6O3mbw74RuLie7DJdwKsUjkZU52lx1J2gfe6fWtS/1HWNLaVbzxFpERitnu3/4k07YiQgM3E/bI46+1Rz6zqdvBHcSeJdG8qSze+R10edg0CBSzjE/YMvHU54FAGbbmL/hO0CY/tj+1pvtGP8AWfYvs527u/l7vLx/Du9812v2qb+0Psv9n3Hlbd32vdH5ef7uN+/P/Ace9c3ea1qdgLg3HiPSVW2g+0TsuiXDiJOxYrOQCeoU8nsKn+3az5scf/CSaIDJbG7VjpUoUwjGX3faMAfMO/egDlNb09p77xVdLo2nyhL6NW1Rzm5sV8iHMiKEJIQfNwwPXird3oT+I9e8RfYbHSp2leAQ6rNL++tswRkPFtjOcfeGHXn861YPEWoXEU8q+ItNRYLc3J83QLqMvEBkugaYGRR6rnqPUZtfb9Z/tGPT/wDhItH+0yW/2lU/sibHl5xuz9owO/Gc8H0NAED+H9FPxFjkbSLFpGsHuGc2yZMvnL+8Jx97k89aueKY5bJ7fVrB1hvZJItPdyuQ0c0gRSR3KOwcf8CHG4mqVrr9/ex3L2/ibR2FrbJdTA6LcKVidd6tgz5OV545rThi8TTwxzRa3pDRyKGU/wBkyjIIyP8Al4oA5rV9DhtvES2lj4a07Wks9HUpb3zgEnzH5UlGDOx6k4yTknmrN8Yj8GJlS8W7WPTdjTEHqBggg8jBBBB5GOea3/svir/oM6R/4Kpf/kij7L4q/wCgzpH/AIKpf/kigDjb200OTwtqdvZXvhu5M0tosg0S2W3YKbhAd5WRyevHTHP4R69PI02v2upfNLZ6XbQzSyD5ZlFwxEnTHzKQT2B3DtXbfZfFX/QZ0j/wVS//ACRR9l8Vf9BnSP8AwVS//JFAGX4fGj/8JVMfDBs/7MFl/pIsNvkedvGz7vy79u7OOcbc9q66sX7L4q/6DOkf+CqX/wCSKPsvir/oM6R/4Kpf/kigDaorF+y+Kv8AoM6R/wCCqX/5Io+y+Kv+gzpH/gql/wDkigDaorF+y+Kv+gzpH/gql/8Akij7L4q/6DOkf+CqX/5IoA2qKxfsvir/AKDOkf8Agql/+SKPsvir/oM6R/4Kpf8A5IoA2qKxfsvir/oM6R/4Kpf/AJIo+y+Kv+gzpH/gql/+SKANqisX7L4q/wCgzpH/AIKpf/kij7L4q/6DOkf+CqX/AOSKANqisX7L4q/6DOkf+CqX/wCSKPsvir/oM6R/4Kpf/kigDaorF+y+Kv8AoM6R/wCCqX/5Io+y+Kv+gzpH/gql/wDkigDaorF+y+Kv+gzpH/gql/8Akij7L4q/6DOkf+CqX/5IoA2q861AB9Dso7mSyisG13UPtEl/GZLZcT3G3zF3KCM8AFgN209QAer+y+Kv+gzpH/gql/8AkisTQzr1noF5dvrek29tBe3zyvLpsjbcXMu9siccZBIHYYGTjJAOcubot/Zd1d2Vkipp9q2nWdz5jPLJ5rbltXLBkcjyjn5iB5fGM1ubtBu/FztolzYw6nam48xxcqbm7mKMDFtzuZFPzc8AooUYBxal8R38K27v4k0ry7iOOVZF0K5ZESQ4RpGE2Iwe28jv6VINZ1g6ommNrNnHcO7onmeG7tEYqCWxIZQpGB1BwfxoAwvD50RdL1Gf7FBe6ZbaPbTX0Dxh0a7QSNJuDA/vcBd2efu55xXa+GtFh0DRIbOOGGKRsyziFAiGVuW2gcAZ4A7AAVl6Vqesa2JDp/iHSZfLClt2izplWztYbpxuU4OGGQcHB4qXTLrXNZsEv9O8Q6NcW0jMqSrpM2G2sVOM3HTIPPegDpaKxfsvir/oM6R/4Kpf/kij7L4q/wCgzpH/AIKpf/kigA8V/wDIIg/7CVh/6VxVtVyPiC38QJY2zXmp6bNANSsdyQ6dJGx/0qLGGMzAc47H8OtdTtn/AOekf/fs/wCNAEtFRbZ/+ekf/fs/40bZ/wDnpH/37P8AjQBLRUW2f/npH/37P+NFAHKz6X9osI7ZpbQOVdGlW7dfKRmyECgDeqjgBiBx0xxXQLc2qqFE8QAGB84rkD4oElqk1vZ+awt2uJlMuPLVW2nBwc8g+nFbkMqzwpKmdsihlz6GlcmM4y2IdZWXUrDzNLi/tBrXVbeV44JUyRGUZgCzBcgDoSKzdZ0XVdYN7qf9lXURmnsFWzW5jSdo4JS7tuV9qt87AYfPyg5BPFbTLS3Ww1jUJbbV7oxanOrR6fqL2+1AASxXzY1P15bkdhxbj/sp9Ntbw2PidZL1lW0tTrMxluAV3bhi4KqoXJJZlxj1IBEEXzK5bfT7t7C3ls9J1KKSwvkuhbalfLO9wNrKQjmWTaQGyASBkDpkmpdRi13WrWWBNNj0+K6miQ/aAkjqi5Z2lCSYZWwqBVbOCSTzxnzHSYdLur4WfiaRrBmW9tl1mYS221d5LbrgAjaQQVLZyMVJPFpNnoLaxeW3iW2TcoS3bWJ3lkBxgqEnYdyeueDxTKGSaVr9ibNXsf7SSx1k3itZ7IQ0ckUu4KkknG2SQ8FuhGPQM1LRNTv1k1KTSrsNc6rDcNZQXSRzpFHEY871kVQxPPyv0I561pDS9FbVrfTkuNaeS5tXuo5F1m72FFZFPPm5yfMGOPWr3/CKad/z86v/AODm7/8AjtAE+hIY7FozY6jZhXOE1C6FxI3Tnd5knHsT26Vp1i/8Ipp3/Pzq/wD4Obv/AOO0f8Ipp3/Pzq//AIObv/47QBtVyOuabNq+p+JNPtigmuNGtUj3nC7vMusZPatT/hFNO/5+dX/8HN3/APHaybbwzYHxjqUJuNU2pp9owI1a6DZMlwDlvMyR8owCcDnHU5AIda03WfEUGqXP9kTWUjaLNZQwTzRF5ZZCDwUYqFG0DJI69OKr6x4W1h7u+hsrZZbKTRb2G3/eKCk82z91gkcFlJB6DcRwAK6T/hFNO/5+dX/8HN3/APHaP+EU07/n51f/AMHN3/8AHaAMC58OarZeHNU0GytnvIL22MkUzyp5izkAOkhYgtkjIbnHIOAFo1Dwlqdzq2oWkCxLps2lzw2srsCI3kkRvKZeu0FWIxwFOO3O/wD8Ipp3/Pzq/wD4Obv/AOO0f8Ipp3/Pzq//AIObv/47QBVjh1HW9asbq+0iTTYLGKXzBNNG5maRdu1djHKDBJLbSfl464wz4U1s6G64I1GOYWsTiRc/ZhEYA5OfR2lx16cZ4rpv+EU07/n51f8A8HN3/wDHaP8AhFNO/wCfnV//AAc3f/x2gDB1jwxqLtr1zplqguHiWKzUuoE0RhCSR5/hGQCM4+ZFPSuv02J4NMtYZV2yRworDOcEKAazv+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2qKxf+EU07/n51f/AMHN3/8AHaP+EU07/n51f/wc3f8A8doA2q4tNIvtY8MSQ2V1DD5eq38jRzQGVZiLmbaDh1xhsMOeqitr/hFNO/5+dX/8HN3/APHa5zTNKsrXRnlEOvXkraleosVnqtwpwtxL8xzMqjgcknJJ7k0AWIbXXI9F0jQ77Rrm4tILSEXbWjQDzGUD90d8oIUYG4jO7tgddx9Mnu9W1K5uBsVrUWlo2QdqkbpGGORlioOf+eYrBdtDW2s7yOPxLNZ3UcMn2pdVugkQlYKm7dMCSSRkKGIyCcAjLoP7Bn1J7TPiCKITS26XcmsXIilljBLov77dkBX5KgfI2D0yAR2H | GAS; HOU | Business | 70 | Goddard, Susan C. | Done | 2021-01-25T20:20:49.633Z | 2021-02-22T13:39:13.287Z | CNP.GIS | CNP.GIS\Sprint 21.02-A | GAS
3548 | Task | 3496 | Create FME Workbench to Update Material Numbers |  |  |  |  | Bradley Painter | Done | 2021-01-27T14:25:02.263Z | 2021-02-15T14:09:21.4Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3549 | Task | 3496 | Create FME Workbench to Update Material Descriptions |  |  |  |  | Bradley Painter | Done | 2021-01-27T14:25:17.49Z | 2021-02-15T14:09:18.153Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3551 | Task | 3531 | Migrate Updated BGPS Code to 10.6.1 |  |  |  |  | Aaron Miller | Done | 2021-01-27T14:30:30.183Z | 2021-02-15T20:33:20.907Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3558 | Product Backlog Item |  | GIS Report Tool Enhancement: Delimit CEIP Features from Distribution Main Summaries | <div><div><span style="font-size:small;font-weight:bold;">HD0000524918</span></div><div>Nathan Winkley</div><div><br></div><div>&quot;I do not think that the GIS Gas Reporting Tool is set up to separately <br>extract CEIP service lines (Transmission or Distribution). So, you may need to contact Susan Goddard for <br>another change in the GIS Gas Reporting Tool. Perhaps, a DOT AREA called CEIP might need to be created.&quot;</div><br></div> | GAS; HOU | Business | 90 | Goddard, Susan C. | Done | 2021-01-29T13:49:13.867Z | 2021-02-22T13:39:10.06Z | CNP.GIS | CNP.GIS\Sprint 21.02-A | GAS
3559 | Task | 3353 | Waiting on access to site |  |  |  |  | Hanh Tran | Done | 2021-01-29T14:20:42.63Z | 2021-02-02T15:27:17.223Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3353 | Product Backlog Item |  | Code SharePoint List Location Change | <div><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;"><b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">From:</span></b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"> Gastineau, David E &lt;<a href="mailto:david.gastineau@centerpointenergy.com">david.gastineau@centerpointenergy.com</a>&gt; <br style=""><br style=""></span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi Hanna,</p></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I just wanted to share with you that I am looking into migrating the Code SharePoint List from its current location to the Teams Site that I use for code clearance so I can use the new Microsoft Lists functionality and build Power BI dashboards with the data and not worry about messing up the backend code of the site (which I have done before).</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I am not ready to make the transition just yet, we are going to build a test list to see if it works. Once we know it works, we’ll make the migration. A few questions:</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><ul style="margin-bottom:0in;margin-top:0in;"> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">What would you need to make this transition? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Is this a big ask? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Or is it relatively simple?</span></li></ul><br></div> | HOU | Business | 13 | Hanh Tran | Started | 2021-01-05T16:10:41.21Z | 2021-03-04T14:27:38.07Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3560 | Task | 3357 | Pull data from SAP HANA |  |  |  |  | Christopher Thomas | Done | 2021-01-29T14:23:40.73Z | 2021-02-03T14:18:21.98Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3357 | Product Backlog Item |  | Create an interface to store Electric Capital Work Orders from SAP into GIS | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-indent:.5in;"><span style="font-size:14.6667px;text-indent:0.5in;"></span></p><div><span style="font-size:14.6667px;text-indent:0.5in;">Load&nbsp; data from &quot;_SYS_BIC&quot;.&quot;system-local.bw.bw2hana/ZUI_01O&quot; nightly into GIS Metro table</span><br><ul><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Chen - Get the table info from SAP</span></li></ul><ol><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Create a FC for&nbsp;Electric Capital Work Orders</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Read data from SAP table and store data in GIS&nbsp;</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Geocode the address into Lat/Long&nbsp;</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Publish the <span style="display:inline !important;">FC<span>&nbsp;</span></span>as a map service</span></li></ol><span><div><span>SAP HANA connection string:&nbsp;</span></div><div><span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-autospace:none;"><span style="font-size:9.5pt;font-family:Consolas;">QA: Server=<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">hiqdb.mycenterpointenergy.com:32041</span>;UserID=BWGIS;Password=<span style="font-family:&quot;Segoe UI&quot;, sans-serif;font-size:14px;display:inline !important;">Vision@123</span></span></p></span></div><div><span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:10.5pt;font-family:&quot;Segoe UI&quot;,sans-serif;"></span></p><div style="box-sizing:border-box;"><span style="box-sizing:border-box;"><p style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p></span></div></span><p></p></div>Reuse the code from CNP.GIS.Utilities\CNP.Gas.Leaks</span><br></div><div><span><br></span></div> | HOU | SAP-GIS | 30 | Christopher Thomas | Done | 2021-01-06T20:04:09.113Z | 2021-02-27T22:28:16.85Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3561 | Task | 3357 | Geocode Addresses into LAT/LONG |  |  |  |  | Christopher Thomas | Done | 2021-01-29T14:24:14.753Z | 2021-02-05T14:19:42.993Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3562 | Task | 3357 | Publish feature class as Map Service |  |  |  |  | Christopher Thomas | Done | 2021-01-29T14:24:42.877Z | 2021-02-23T14:26:54.33Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3566 | Task | 3496 | Create FME Workbench to Update UOM Table |  |  |  |  | Bradley Painter | Done | 2021-02-01T14:23:27.797Z | 2021-02-15T14:09:15.27Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3568 | Product Backlog Item |  | Verify the ACK process for the EAI ack filename changes | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">As part of the task#REQ1033339 - Multiple data sets in one Acknowledge file , to </span><span style="color:rgb(32, 56, 100);background-color:rgb(255, 255, 0);">minimize the occurrence of multiple headers</span><span style="color:#203864;"> in one Nack file, we have added Thread value to file name and file name looks like below.</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">&nbsp;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">Could you please confirm if below filename will be accepted by GIS .</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">&nbsp;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">&nbsp;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">Before Change in Filename :</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">Network_20201211_0300_ACK.txt</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">Network_20201214_0300_ACK.txt</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">&nbsp;</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">After Change in FileName :</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">Network_<span style="background:lime;">000258</span>-20210129_0427_ACK.txt</span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">Network_<span style="background:lime;">000333</span>-20210129_0448_ACK.txt </span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="color:#203864;">&nbsp;</span></p><br></div> | ELECTRIC; HOU | SAP-GIS |  | Saud Ahmad | Done | 2021-02-01T14:42:17.123Z | 2021-02-04T14:59:57.46Z | CNP.GIS | CNP.GIS\Sprint 21.02-A | ELECTRIC
3570 | Product Backlog Item |  | Add New Domain Value to Pole_Pt & DDS_Pole_pt | <div><span><span style="color:steelblue;font-size:12px;font-weight:bold;">HD0000524915</span> </span></div><div><span>Requestor: Karen M</span></div><div><span><br></span></div><div><span>Add domain values for YEARMANUFACTURED attribute for Pole_pt and DDS_Pole_pt. Probably will also be needed for the deleted pole feature classes. Electric Data Management digitizers are getting the attached validation error. </span><br></div> | ELECTRIC; HOU | Business | 20 | William Robertson Jr | Done | 2021-02-01T17:52:38.887Z | 2021-02-03T14:33:17.263Z | CNP.GIS | CNP.GIS\Sprint 21.02-A | ELECTRIC
3574 | Product Backlog Item |  | EIP - CU Admin Tool - Dev Testing Link | <div>Create CU Admin Tool link for DINOD2 so that CU administrators can adjust data without affecting the UAT environment.&nbsp;</div> | EIP; INOH | EIP | 10 | Chen Liang | Done | 2021-02-01T20:40:33.36Z | 2021-02-15T14:13:03.97Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
3585 | Task | 3357 | Add Logging |  |  |  |  | Christopher Thomas | Done | 2021-02-02T15:18:02.12Z | 2021-02-12T14:19:38.793Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3586 | Task | 3569 | Add a Subtype to MetroT |  |  |  |  | Chen Liang | Done | 2021-02-02T15:18:03.053Z | 2021-02-18T17:11:16.1Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3569 | Product Backlog Item |  | Add New Switch Subtype to METROT | <div><font face="Times New Roman" size=3></font></div><div><p style="margin:0in 0in 0pt;"><span><font face=Calibri size=3>Subtype Specifics added Switch_PT Feautre class</font></span></p><font face="Times New Roman" size=3></font><ul><li style="font-weight:normal;"><p style="margin-top:0in;margin-bottom:0pt;vertical-align:middle;"><span>Manually Operated = 'No'</span></p></li><li style="font-family:&quot;Calibri&quot;,sans-serif;font-size:11pt;font-weight:normal;"><p style="margin-top:0in;margin-bottom:0pt;vertical-align:middle;"><span>Service Code = 'UG'</span></p></li><li style="font-family:&quot;Calibri&quot;,sans-serif;font-size:11pt;font-weight:normal;"><p style="margin-top:0in;margin-bottom:0pt;vertical-align:middle;"><span>Potentially name subtype 'UG RTAC'</span></p></li></ul><font face="Times New Roman" size=3></font><br></div> | ELECTRIC; HOU | Business | 20 | C_Varalakshmi Srinivasan | Done | 2021-02-01T16:16:12.98Z | 2021-02-24T14:17:01.6Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC
3587 | Task | 3571 | Export list of unassigned domains for each geodatabase |  |  |  |  | William Robertson Jr | Done | 2021-02-02T15:18:23.347Z | 2021-02-03T14:22:34.173Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3571 | Product Backlog Item |  | Database: Unused domains cleanup (2nd Pass) |  | HOU | System |  | William Robertson Jr | Started | 2021-02-01T18:12:47.007Z | 2021-03-05T13:08:54.397Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3588 | Task | 3532 | Send to Nanda/GIS Support for testing |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:18:40.78Z | 2021-02-12T03:22:35.63Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3591 | Task | 3532 | documentation of changes |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:19:22.443Z | 2021-02-22T13:38:32.763Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3592 | Task | 2970 | Add jurisdiction dropdown list |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-02-02T15:19:36.14Z | 2021-02-19T14:20:59.707Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
2970 | Product Backlog Item |  | WOTS: Add Jurisdiction functionality to the Electric Orders | <div><span style="color:steelblue;font-size:12px;font-weight:bold;">HD0000524622</span> - Karen M</div><div><br></div><div><span>Please add jurisdiction like gas for WOTS Data Corrections submittal and usage. We need to include Indiana like we do Houston for Electric. Thanks.</span> <br></div> | ELECTRIC; HOU; WOTS | WOTS | 90 | Subhankar, C_Baidya X | Done | 2020-11-17T19:51:07.37Z | 2021-02-27T22:28:52.41Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC
3593 | Task | 3569 | Research the QA/QC Code and provide the impact estimation |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-02-02T15:19:48.35Z | 2021-02-23T14:29:07.067Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3594 | Task | 2970 | Unit test |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-02-02T15:19:58.383Z | 2021-02-22T14:21:52.17Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3596 | Task | 3558 | code logic change |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:21:07.82Z | 2021-02-03T14:24:08.23Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3597 | Task | 3558 | Testing code change |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:21:59.73Z | 2021-02-10T18:37:15.993Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3598 | Task | 3357 | Insert Rows into Oracle Table |  |  |  |  | Christopher Thomas | Done | 2021-02-02T15:22:10.04Z | 2021-02-18T14:19:19.227Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3599 | Task | 3558 | Nanda/GIS Support Testing Code Change |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:22:26.717Z | 2021-02-15T14:26:10.54Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3602 | Task | 3357 | Add Configuration File |  |  |  |  | Christopher Thomas | Done | 2021-02-02T15:23:10.507Z | 2021-02-03T14:18:29.947Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3606 | Task | 3574 | Create CU_ADMIN website for DINOD2 |  |  |  |  | Chen Liang | Done | 2021-02-02T15:24:40.06Z | 2021-02-04T15:09:49.51Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3616 | Task | 3114 | Meeting with Jacob/Mary |  |  |  |  | Hanh Tran | Done | 2021-02-02T15:32:10.123Z | 2021-02-03T14:18:49.88Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3617 | Task | 3509 | Maximo Simple WO: process missing WO with new mapping type | <div><div style="box-sizing:border-box;font-family:&quot;Segoe UI&quot;, system-ui, &quot;Apple Color Emoji&quot;, &quot;Segoe UI Emoji&quot;, sans-serif;">LSSL - LEAK SURVEY<br> WOSUP - MISC<br> GASDIST - SERVICE<br> GMTRRPR - MISC<br> LEAKDISC - OTHER REPAIR-SERVICE</div><br></div> |  |  |  | Hanh Tran | Done | 2021-02-02T15:33:44.547Z | 2021-02-16T14:37:38.127Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3619 | Task | 3570 | Research which domain to add value to |  |  |  |  | William Robertson Jr | Done | 2021-02-02T15:35:30.723Z | 2021-02-02T17:41:13.553Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3621 | Task | 3568 | Verify the ACK process for the filename change |  |  |  |  | Saud Ahmad | Done | 2021-02-02T15:41:54.53Z | 2021-02-04T14:17:21.06Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3622 | Task | 3357 | Testing |  |  |  |  | Christopher Thomas | Done | 2021-02-02T15:47:02.61Z | 2021-02-18T14:19:21.323Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3627 | Task | 3570 | Add value 2020 to the PoleYearManufactured domain |  |  |  |  | William Robertson Jr | Done | 2021-02-02T17:41:55.23Z | 2021-02-03T14:26:30.427Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3628 | Task | 3498 | Refine and Update DIP for Dry Run 1 |  |  |  |  | Bradley Painter | Done | 2021-02-02T23:40:28.693Z | 2021-02-15T19:56:11.997Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3630 | Task | 1007 | Update 11x17 templates to match letter templates |  |  |  |  | Christopher Thomas | Done | 2021-02-03T14:17:48.41Z | 2021-02-08T14:17:31.847Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3632 | Task | 3114 | Change process to grab Zipped file |  |  |  |  | Hanh Tran | Done | 2021-02-03T14:19:53.163Z | 2021-02-03T14:20:28.98Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3633 | Task | 3353 | Meeting w/ David & Bala - to develop a plan |  |  |  |  | Hanh Tran | Done | 2021-02-03T14:22:08.54Z | 2021-02-04T14:21:13.477Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3635 | Product Backlog Item |  | EIP - 1118 - Enhancement/Defect - Create trigger on the UOM conversion table | <div><b><span style="font-size:10.0pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;">Create trigger on the UOM conversion table</span></b><br></div><div><b><span style="font-size:10.0pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"><br></span></b></div><div><b><span style="font-size:10.0pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;">Low priority</span></b></div><div><b><span style="font-size:10.0pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"><br></span></b></div><div><b><span style="font-size:10.0pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"><br></span></b></div><div><b><span style="font-size:10.0pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:8.0pt;font-family:&quot;Arial&quot;,sans-serif;color:black;">Per Nat's request:</span><span style="font-size:8.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"> </span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:8.0pt;font-family:&quot;Arial&quot;,sans-serif;color:black;">Please go ahead and create the following low priority defects to the respective team as per the defect identified by April.</span><span style="font-size:8.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"> </span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:8.0pt;font-family:&quot;Arial&quot;,sans-serif;color:black;">ArcFM Team:</span><span style="font-size:8.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"> </span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:8.0pt;font-family:&quot;Arial&quot;,sans-serif;color:black;">&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Need to create a trigger on the UOM conversion table so that whenever the table gets updated an AQ message will be triggered which will be consumed by EAI and updated the UOM Conversion table so that the data will be in sync always and no manual copy.</span><span style="font-size:8.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"> </span></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:8.0pt;font-family:&quot;Arial&quot;,sans-serif;color:black;">EAI Team:</span><span style="font-size:8.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"> </span></p><span style="font-size:8.0pt;font-family:&quot;Arial&quot;,sans-serif;color:black;">&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Implement a process to consume a AQ message from ArcFM and update the UOM conversion table in PWO schema.</span><span style="font-size:8.5pt;font-family:&quot;Verdana&quot;,sans-serif;color:black;"> </span><br></span></b></div> | EIP; INOH | EIP | 3 | Kelsey Mobley | Done | 2021-02-03T16:56:23.79Z | 2021-02-09T15:16:53.55Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
3636 | Product Backlog Item |  | Fiber Data Model Change | <div><span><a style="color:black;" href="http://gishqweb.mycenterpointenergy.com/gtrak/helpdesk/view.aspx?mn=MD0000000035&amp;tc=16216f3d-3359-4d7b-8068-8004a9e25d6d"><u>HD0000524925</u></a></span></div><div><span><br></span></div><div><span><br></span></div><div><span>3 related requests:<br>1. Edits to Existing:<br>Work Flow Status<br>Remove ‘Replace’ from integer 2<br>Should now be ‘2 – Blue Wire’ instead <br>of ‘Replace Blue Wire’<br><br>2. New Domains as follows:<br>Site Work Flow Status - (Long Integer, Coded <br>Values, Duplicate, Default Value):<br>0 - Planned<br>1 - Constructed<br>2 – In Service<br><br><br>3. The scz.F_PatchLocation_PT feature class needs to be updated. The field is a brand new field that is to be added to the Patch Location feature. Brand New Field name = “StatusInstallation” (Data Type: Long Integer). <br>Move this field beneath the “COMMENTS” field under “Field Display” via ArcFM Properties Manager.<br>Set-Up:<br>Alias = StatusInstallation<br>Allow NULL values = Yes<br>Default Value = 0<br>Domain = Site Work Flow Status <br>Precision = 10</span><br></div> | ELECTRIC; HOU | Business |  | William Robertson Jr | Done | 2021-02-03T19:13:53.93Z | 2021-02-09T15:00:52.947Z | CNP.GIS | CNP.GIS\Sprint 21.02-A | ELECTRIC
3637 | Task | 3636 | Create new domain Site Work Flow Status in Metro SCZ schema |  |  |  |  | William Robertson Jr | Done | 2021-02-04T13:37:19.983Z | 2021-02-04T14:23:40.95Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3638 | Task | 3636 | Change domain value for coded value 2 in the Work Flow Status domain | <div><span><span>Remove <b>Replace</b> from integer 2.<br></span><span>Should now be <b>Blue Wire</b> instead of <b>Replace Blue Wire</b>.</span><br></span></div> |  |  |  | William Robertson Jr | Done | 2021-02-04T13:38:21.393Z | 2021-02-04T14:23:48.287Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3639 | Task | 3636 | Add field StatusInstallation to SCZ.F_PatchLocation_PT | <span style="display:inline !important;">Must be done on DB weekend or when a schema lock can be obtained.</span> |  |  |  | William Robertson Jr | Done | 2021-02-04T13:39:47.037Z | 2021-02-08T14:22:59.827Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3642 | Task | 3636 | Assign domain Site Work Flow Status to field StatusInstallation in SCZ.F_PatchLocation_PT | <span style="display:inline !important;">Must be done on DB weekend or when a schema lock can be obtained.</span> |  |  |  | William Robertson Jr | Done | 2021-02-04T13:55:57.867Z | 2021-02-08T14:23:00.87Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3646 | Task | 3635 | Create Trigger for UOM Conversion Table |  |  |  |  | Kelsey Mobley | Done | 2021-02-04T14:28:43.353Z | 2021-02-09T14:56:02.377Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3650 | Product Backlog Item |  | Restart mechanism for web services for Tibco |  | INOH | 1061 Migration | 3 | Krejcirik, C_Vlad | Done | 2021-02-04T15:17:33.5Z | 2021-02-15T20:33:47.257Z | CNP.GIS | CNP.GIS\Sprint 21.02-A |  | INOH
3651 | Task | 3574 | Wait for user feedbacks |  |  |  |  | Bradley Painter | Done | 2021-02-04T15:17:45.603Z | 2021-02-12T15:05:09.003Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3652 | Task | 3650 | Research |  |  |  |  | Krejcirik, C_Vlad | Done | 2021-02-04T16:05:20.527Z | 2021-02-12T14:57:20.757Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3653 | Task | 3650 | Implementation |  |  |  |  | Krejcirik, C_Vlad | Done | 2021-02-04T16:05:31.893Z | 2021-02-15T20:33:41.097Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3654 | Task | 3650 | Testing |  |  |  |  | Krejcirik, C_Vlad | Done | 2021-02-04T16:05:40.217Z | 2021-02-15T20:33:35.68Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3656 | Task | 3357 | Install Oracle Client |  |  |  |  | Christopher Thomas | Done | 2021-02-05T14:19:58.23Z | 2021-02-10T18:34:10.75Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3662 | Task | 1007 | GSD & User Testing | [5 empty] | Done | 2021-02-08T14:17:52.727Z | 2021-02-10T18:31:57.413Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3663 | Task | 2317 | Make the layer and field names configurable |  |  |  |  | Chen Liang | Done | 2021-02-08T15:24:56.247Z | 2021-02-10T17:37:32.56Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3664 | Task | 2317 | Consolidate the layer and field difference between INOH and HOU |  |  |  |  | Chen Liang | Done | 2021-02-08T15:26:21.883Z | 2021-02-12T15:08:33.63Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3665 | Task | 2317 | Test run Gas Leak on INOH DINOD2 |  |  |  |  | Chen Liang | Done | 2021-02-08T15:26:51.85Z | 2021-02-18T15:13:13.227Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3673 | Task | 3558 | Verify the report on LA |  |  |  |  | Goddard, Susan C. | Done | 2021-02-10T17:40:31.67Z | 2021-02-12T03:23:28.657Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3675 | Task | 1007 | Push it to the production |  |  |  |  | Christopher Thomas | Done | 2021-02-10T18:33:24.03Z | 2021-02-18T14:19:01.22Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3676 | Task | 3353 | Wait for data migration | [5 empty] | Done | 2021-02-10T18:40:31.06Z | 2021-02-23T14:25:57.247Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3679 | Task | 3353 | CoH Rest service - hardcode -> configuable |  |  |  |  | Hanh Tran | Done | 2021-02-10T19:28:38.923Z | 2021-02-15T14:24:37.58Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3681 | Task | 3114 | copy pdf : not able to replicate |  |  |  |  | Hanh Tran | Done | 2021-02-10T19:30:23.13Z | 2021-02-15T14:23:14.357Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3682 | Task | 3114 | ot download when changing selection: modify logic to check date |  |  |  |  | Hanh Tran | Done | 2021-02-10T19:31:28Z | 2021-02-15T14:21:42.67Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3686 | Task | 2970 | Review existing code |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-02-15T13:49:28.223Z | 2021-02-15T14:27:58.33Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3695 | Task | 3558 | documentation of changes |  |  |  |  | Goddard, Susan C. | Done | 2021-02-15T14:26:22.583Z | 2021-02-22T13:38:52.343Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3710 | Task | 3353 | ON HOLD: COH Servers Down & IT Working on Creating Separate List | [5 empty] | Done | 2021-02-18T14:23:20.487Z | 2021-02-23T14:24:39.747Z | CNP.GIS | CNP.GIS\Sprint 21.02-A
3728 | Task | 3357 | Set Up Interface on GISECDC Batch01 |  |  |  |  | Christopher Thomas | Done | 2021-02-19T14:19:23.517Z | 2021-02-23T14:27:01.04Z | CNP.GIS | CNP.GIS\Sprint 21.02-A