## current_iteration
Id | WorkItemType | Parent | Title | Description | Tags | ValueArea | BusinessValue | AssignedTo | State | CreatedDate | ChangedDate | AreaPath | IterationPath | Operation | Region | Planned
379 | Task | 3552 | GSD Testing |  |  |  |  | Aaron Miller | Done | 2020-10-01T20:22:57.353Z | 2021-02-18T15:05:08.96Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
380 | Task | 3552 | USIC Testing | <div>USIC currently does not use portal</div> |  |  |  | Aaron Miller | Done | 2020-10-01T20:23:05.657Z | 2021-02-19T15:01:22.25Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
381 | Task | 3552 | OCC Testing | <div>OCC will use multiple accounts</div> |  |  |  | Aaron Miller | Done | 2020-10-01T20:23:12.76Z | 2021-03-01T15:05:46.727Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
382 | Task | 3552 | OTS Testing | <div>OTC just needs one account</div> |  |  |  | Aaron Miller | Done | 2020-10-01T20:23:19.61Z | 2021-03-01T15:05:48.427Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
387 | Product Backlog Item |  | 10.6.1 - Finalize 10.6.1 Custom Installer | <div>10.6.1 - Fix Fonts and Styles in 10.6.1 Installer - 10.6.1 VS EIP Installer<br></div> | INOH | 1061 Migration | 1 | Kelsey Mobley | Done | 2020-10-01T20:33:32.267Z | 2021-02-24T16:11:57.887Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
388 | Task | 387 | Identify issue with Electric Font file in Installer |  |  |  |  | Kelsey Mobley | Done | 2020-10-01T20:33:58.407Z | 2021-02-19T15:04:28.283Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
389 | Task | 387 | Clean Up Installer Environments |  |  |  |  | Kelsey Mobley | Done | 2020-10-01T20:34:16Z | 2021-02-17T15:08:54.997Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
390 | Task | 387 | Clean-up add-in folder location |  |  |  |  | Kelsey Mobley | Done | 2020-10-01T20:34:36.203Z | 2021-02-17T15:08:49.27Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
2943 | Product Backlog Item |  | 10.6.1 - ArcFM G.Viewer Map Setup | <div>ArcFM Web Maps for INOH 10.6.1</div><div><ol><li>Gas</li><li>Electric</li><li>DSO</li><li>Gas Control</li><li>New Service Center</li><ol style="list-style:lower-alpha;"><li style="box-sizing:border-box;outline:none;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="box-sizing:border-box;outline:none;">Please add Service Locations to the map so they can identify customer details on Electric Service drops</span></li><li style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="box-sizing:border-box;">When identifying poles, they receive the error message below.</span></li><ol style="box-sizing:border-box;padding-left:40px;list-style:lower-alpha;"><li style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="box-sizing:border-box;">&quot;The requested operation failed. Try again later or inform your administrator&quot;</span></li></ol></ol></ol><div><br></div></div><div><p style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">All sites use this locator:<span>&nbsp;</span><a href="https://nam04.safelinks.protection.outlook.com/?url=https://geocode.arcgis.com/arcgis/rest/services/World/GeocodeServer&amp;data=04%7c01%7cBrad.Painter%40centerpointenergy.com%7c0bb1c6145a4648e26e6b08d89c82ecb9%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637431433426726505%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=jMexrPYcb9mEu80P0AwAfItxM7cO6k%2Bdi3tWKgUaGZI%3D&amp;reserved=0" style="box-sizing:border-box;text-decoration:underline;cursor:pointer;">https://geocode.arcgis.com/arcgis/rest/services/World/GeocodeServer</a></p><p style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Houston also uses this locator but is only for the Houston area:<span>&nbsp;</span><a href="https://nam04.safelinks.protection.outlook.com/?url=https://cnpgviewer.cnp.int/arcgis2/rest/services/Locators/SCZ_SingleAddress_10_SDE/GeocodeServer&amp;data=04%7c01%7cBrad.Painter%40centerpointenergy.com%7c0bb1c6145a4648e26e6b08d89c82ecb9%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637431433426736504%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=L4Vvj%2BgfYSPcXkJ2iWVdqq1PstajjPGpCSrldHoSHTs%3D&amp;reserved=0" style="box-sizing:border-box;text-decoration:underline;cursor:pointer;">https://cnpgviewer.cnp.int/arcgis2/rest/services/Locators/SCZ_SingleAddress_10_SDE/GeocodeServer</a></p><br></div> | INOH | 1061 Migration | 30 | Kelsey Mobley | Done | 2020-11-16T15:24:42.947Z | 2021-02-26T13:37:11.617Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
2970 | Product Backlog Item |  | WOTS: Add Jurisdiction functionality to the Electric Orders | <div><span style="color:steelblue;font-size:12px;font-weight:bold;">HD0000524622</span> - Karen M</div><div><br></div><div><span>Please add jurisdiction like gas for WOTS Data Corrections submittal and usage. We need to include Indiana like we do Houston for Electric. Thanks.</span> <br></div> | ELECTRIC; HOU; WOTS | WOTS | 90 | Subhankar, C_Baidya X | Done | 2020-11-17T19:51:07.37Z | 2021-02-27T22:28:52.41Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC
3114 | Product Backlog Item |  | Allow multiple Fileservers to download the MIMSReplica | <div><span style="background-color:rgb(255, 255, 0);display:inline !important;">To be completed by Jan 18th</span><br></div><div>MIMSReplicaCopy copies the replica files from one file server. This is for the users to download data for GO!Sync.&nbsp;</div><div><ul><li>Change the config file to accommodate multiple download sources.&nbsp;</li><li>Add UI to select which file server they download files from.&nbsp;</li><li>Download one selected fileserver to the local drive&nbsp;&nbsp;<br></li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Started | 2020-12-03T13:12:50.887Z | 2021-03-10T14:33:13.913Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3306 | Product Backlog Item |  | Migrate RED Approval to HTML5 | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Jacob:&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Here are my review comments.</p><ol style="margin-bottom:0in;margin-top:0in;" start=1 type=1> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Outage RED Production Layers are not turned on by default</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">“Push to PROD” button missing within Outage RED widget.</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Change “Red” to “RED”</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Unable to test due to lack of Substation and Circuit Restoration data</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Legend Widget should be always on. May be split half way thru between Layers and Legend widgets?</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Report widget not working correctly. Outage numbers are not showing by City.</span></li></ol><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I will setup a meeting to go over these in detail.</p><br></div> | HOU | Outage | 40 | Saud Ahmad | Done | 2021-01-04T23:18:37.827Z | 2021-03-10T17:19:45.677Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3353 | Product Backlog Item |  | Code SharePoint List Location Change | <div><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;"><b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">From:</span></b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"> Gastineau, David E &lt;<a href="mailto:david.gastineau@centerpointenergy.com">david.gastineau@centerpointenergy.com</a>&gt; <br style=""><br style=""></span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi Hanna,</p></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I just wanted to share with you that I am looking into migrating the Code SharePoint List from its current location to the Teams Site that I use for code clearance so I can use the new Microsoft Lists functionality and build Power BI dashboards with the data and not worry about messing up the backend code of the site (which I have done before).</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I am not ready to make the transition just yet, we are going to build a test list to see if it works. Once we know it works, we’ll make the migration. A few questions:</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><ul style="margin-bottom:0in;margin-top:0in;"> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">What would you need to make this transition? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Is this a big ask? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Or is it relatively simple?</span></li></ul><br></div> | HOU | Business | 13 | Hanh Tran | Started | 2021-01-05T16:10:41.21Z | 2021-03-04T14:27:38.07Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3357 | Product Backlog Item |  | Create an interface to store Electric Capital Work Orders from SAP into GIS | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-indent:.5in;"><span style="font-size:14.6667px;text-indent:0.5in;"></span></p><div><span style="font-size:14.6667px;text-indent:0.5in;">Load&nbsp; data from &quot;_SYS_BIC&quot;.&quot;system-local.bw.bw2hana/ZUI_01O&quot; nightly into GIS Metro table</span><br><ul><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Chen - Get the table info from SAP</span></li></ul><ol><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Create a FC for&nbsp;Electric Capital Work Orders</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Read data from SAP table and store data in GIS&nbsp;</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Geocode the address into Lat/Long&nbsp;</span></li><li><span style="font-family:Calibri, sans-serif;font-size:14.6667px;text-indent:48px;">Publish the <span style="display:inline !important;">FC<span>&nbsp;</span></span>as a map service</span></li></ol><span><div><span>SAP HANA connection string:&nbsp;</span></div><div><span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;text-autospace:none;"><span style="font-size:9.5pt;font-family:Consolas;">QA: Server=<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">hiqdb.mycenterpointenergy.com:32041</span>;UserID=BWGIS;Password=<span style="font-family:&quot;Segoe UI&quot;, sans-serif;font-size:14px;display:inline !important;">Vision@123</span></span></p></span></div><div><span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:10.5pt;font-family:&quot;Segoe UI&quot;,sans-serif;"></span></p><div style="box-sizing:border-box;"><span style="box-sizing:border-box;"><p style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p></span></div></span><p></p></div>Reuse the code from CNP.GIS.Utilities\CNP.Gas.Leaks</span><br></div><div><span><br></span></div> | HOU | SAP-GIS | 30 | Christopher Thomas | Done | 2021-01-06T20:04:09.113Z | 2021-02-27T22:28:16.85Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3420 | Task | 3567 | Finalize Synergi Workflow with GSD | <div>Work with Jim Davis and Adam Svendsen</div> |  |  |  | Bradley Painter | Done | 2021-01-15T14:19:21.85Z | 2021-02-19T15:01:58.017Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3436 | Product Backlog Item |  | 10.6.1 - ArcFM 10.6.1a SP2 Sanity Check - HOU |  | HOU | 1061 Migration | 30 | C_Varalakshmi Srinivasan | Started | 2021-01-17T18:50:56.46Z | 2021-02-24T15:13:41.03Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3461 | Task | 3433 | Json file for map source |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:24:41.62Z | 2021-02-24T12:38:20.933Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3433 | Product Backlog Item |  | Fix outage tracker map pan issue on Android | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:11pt;">Saud:&nbsp;</span><span style="font-size:11pt;">First is switching the current version to the higher version. I have tested this and mostly impacts the TOC and books marks widget. Most of the other functionalities work fine with minor GUI issues. I can try to incorporate the newer version of TOC compatible with higher versions of API within the current framework. If that works we will have resolution to this issue sooner. I will need a week’s time to try it out.</span><br></p><br> | ELECTRIC; HOU | Outage | 80 | Saud Ahmad | Done | 2021-01-17T15:54:22.03Z | 2021-03-09T14:54:21.9Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | ELECTRIC
3465 | Task | 3436 | Rebuild and test Interfaces |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-19T15:25:20.063Z | 2021-03-01T14:20:22.207Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3474 | Task | 3433 | Adjust GUI on FIND widget |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:30:42.737Z | 2021-02-19T14:15:42.57Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3476 | Task | 3433 | Adjust Planned/UnPlanned widget |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:31:25.82Z | 2021-02-19T14:15:29.79Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3477 | Task | 3436 | Rebuild and test Utilities, Windows Service etc |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-01-19T15:31:38.13Z | 2021-03-01T14:20:12.507Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3478 | Task | 3433 | General GUI - color |  |  |  |  | Saud Ahmad | Done | 2021-01-19T15:31:44.793Z | 2021-02-19T14:15:36.68Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3508 | Task | 3353 | Update/Test COHPermits with new list ( Test List ) | <div>2New URL:&nbsp;<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"><a href="https://nam04.safelinks.protection.outlook.com/?url=https://centerpointenergy.sharepoint.com/sites/CodeClearance479-CodeInspectors/_vti_bin/lists.asmx&amp;data=04%7c01%7cdouglas.kjellander%40centerpointenergy.com%7c04dcaf2470b0417ce8d308d8bd7528ea%7c88cc5fd7fd7844b6ad75b6915088974f%7c0%7c0%7c637467658181205583%7cUnknown%7cTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7c1000&amp;sdata=ofOkwEKnNUuFTw1p1EP90/mjCzkZILm9HdnpPAqaNGM%3D&amp;reserved=0">https://centerpointenergy.sharepoint.com/sites/CodeClearance479-CodeInspectors/_vti_bin/lists.asmx</a></span></div><div><br></div><div>might need to re-map new column names in the new sharepoint list</div> |  |  |  | Hanh Tran | Done | 2021-01-21T14:38:14.51Z | 2021-02-26T14:28:30.43Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3509 | Product Backlog Item |  | EIP - WOTS WO validation for missing WOs from Maximo |  | EIP; HOU; INOH | EIP | 10 | Hanh Tran | Done | 2021-01-21T14:38:50.827Z | 2021-02-18T17:16:20.217Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3511 | Task | 3509 | Validate Maximo Complex WO and add missing WO if needed | <br><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Validate complex wo: waiting for wo list from Robert Liver per Hanna on 2/1/21</p> |  |  |  | Hanh Tran | Done | 2021-01-21T14:40:30.17Z | 2021-02-18T15:15:45.093Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3533 | Product Backlog Item |  | Add domains to Pipe_Xing_pt feature class | <div><span>Requestor: Aaron Jacobs</span></div><div><span>HD 524887</span></div><div><span><br></span></div><div><span>This request applied to the MN database only as others doe not have this Pipe_Xing_pt feature class. Please add the list of RR agencies to the UC_License Agency attribute. See attachment. </span><br></div> | GAS; HOU | Business | 20 | William Robertson Jr | Done | 2021-01-25T21:31:51.033Z | 2021-02-27T22:28:26.91Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | GAS
3552 | Product Backlog Item |  | 10.6.1 - Portal Validation - Explorer for Field Crews and Locators | <div>Verify that current production maps are loaded into test portal site</div><div><br></div><div>GSD Tracking Final Validation and Sign-off by Locators.&nbsp; (Adam Svendsen)</div> | INOH | 1061 Migration | 50 | Aaron Miller | Done | 2021-01-27T14:51:12.99Z | 2021-03-01T15:06:22.873Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3564 | Task | 3433 | Wiring up the TOC w/ Layers |  |  |  |  | Saud Ahmad | Done | 2021-02-01T14:16:44.94Z | 2021-02-24T12:38:26.063Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3565 | Task | 3433 | Repair bookmark widget |  |  |  |  | Saud Ahmad | Done | 2021-02-01T14:17:00.407Z | 2021-02-24T12:38:30.617Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3567 | Product Backlog Item |  | 10.6.1 - Synergi Workflow | <div>Work with Gas system planning and GSD to develop new Synergi Workflow that fits with 10.6.1</div> | INOH | 1061 Migration | 20 | Bradley Painter | Done | 2021-02-01T14:25:55.03Z | 2021-02-24T16:11:47.083Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3569 | Product Backlog Item |  | Add New Switch Subtype to METROT | <div><font face="Times New Roman" size=3></font></div><div><p style="margin:0in 0in 0pt;"><span><font face=Calibri size=3>Subtype Specifics added Switch_PT Feautre class</font></span></p><font face="Times New Roman" size=3></font><ul><li style="font-weight:normal;"><p style="margin-top:0in;margin-bottom:0pt;vertical-align:middle;"><span>Manually Operated = 'No'</span></p></li><li style="font-family:&quot;Calibri&quot;,sans-serif;font-size:11pt;font-weight:normal;"><p style="margin-top:0in;margin-bottom:0pt;vertical-align:middle;"><span>Service Code = 'UG'</span></p></li><li style="font-family:&quot;Calibri&quot;,sans-serif;font-size:11pt;font-weight:normal;"><p style="margin-top:0in;margin-bottom:0pt;vertical-align:middle;"><span>Potentially name subtype 'UG RTAC'</span></p></li></ul><font face="Times New Roman" size=3></font><br></div> | ELECTRIC; HOU | Business | 20 | C_Varalakshmi Srinivasan | Done | 2021-02-01T16:16:12.98Z | 2021-02-24T14:17:01.6Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC
3577 | Product Backlog Item |  | GViewer: Research on creating Preview Graphic |  | HOU | GViewer | 12 | Christopher Thomas | New | 2021-02-02T14:07:16.307Z | 2021-03-05T16:51:14.407Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3578 | Product Backlog Item |  | Place OK Gas Service Lines | <div><span style="display:inline !important;">Discussion Topics:&nbsp;</span><br style="box-sizing:border-box;"><ul style="box-sizing:border-box;padding:0px 0px 0px 40px;"><li style="box-sizing:border-box;">Require attributes from Gas Meters?&nbsp; - Not at the first run&nbsp; </li><li style="box-sizing:border-box;">Need abandoned service line or main? - No at this time </li><li style="box-sizing:border-box;">Need bell hole, redundant features? - No at this time </li><li style="box-sizing:border-box;">Use features from DOT report. They are actual assets. - YES!&nbsp; </li> </ul><br> </div> | GAS; HOU | Business | 60 | Goddard, Susan C. | Started | 2021-02-02T14:10:16.98Z | 2021-03-02T16:13:16.91Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | GAS
3579 | Task | 3306 | Fix bug - Initial extent is not correct |  |  |  |  | Saud Ahmad | Done | 2021-02-02T14:12:37.72Z | 2021-02-24T12:37:43.947Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3581 | Task | 3306 | Fix bug - not all the “Red” words are changed to “RED” |  |  |  |  | Saud Ahmad | Done | 2021-02-02T14:13:34.99Z | 2021-02-24T12:37:52.927Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3582 | Task | 3306 | Load some sample data to validate the Outage RED functionality |  |  |  |  | Saud Ahmad | Done | 2021-02-02T14:13:56.74Z | 2021-02-24T12:38:00.43Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3583 | Task | 3357 | Create a map in portal |  |  |  |  | Mary Torres | Done | 2021-02-02T14:39:44.49Z | 2021-02-27T21:59:25.623Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3603 | Task | 3578 | install .NET sdk 10.6.1 |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:23:11.657Z | 2021-02-24T12:38:40.977Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3620 | Task | 3533 | Research |  |  |  |  | William Robertson Jr | Done | 2021-02-02T15:35:41.93Z | 2021-02-24T12:39:08.1Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3626 | Product Backlog Item |  | 10.6.1 - Migrate GSD 811 Process & Create USIC Process | <div>Work with Adam to Migrate and Test his work benches in Houston</div> | INOH | 1061 Migration | 10 | Bradley Painter | Done | 2021-02-02T16:48:22.823Z | 2021-02-24T16:11:49.587Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3631 | Task | 3114 | Testing |  |  |  |  | Mary Torres | Done | 2021-02-03T14:19:15.827Z | 2021-02-24T14:24:50.767Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3640 | Task | 3533 | Create domain UC_LICENSE_AGENCY_RR_CD in Minnesota |  |  |  |  | William Robertson Jr | Done | 2021-02-04T13:45:10.06Z | 2021-02-24T12:39:13.33Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3641 | Task | 3533 | Assign domain UC_LICENSE_AGENCY_RR_CD to the field UC_LICENSE_AGENCY for subtype RAILROAD CROSSING | <div><span>Must be done on DB weekend or when a schema lock can be obtained.<br></span></div> |  |  |  | William Robertson Jr | Done | 2021-02-04T13:50:14.777Z | 2021-02-27T22:28:37.277Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3643 | Product Backlog Item |  | 10.6.1 - Detailed Implementation Plan with Sys Admin Group and GSD | <div>Need to work out a Detailed Implementation Plan for the 10.6.1 Migration effort from Evansville to Houston.&nbsp;</div><div><br></div><div>Freeze?&nbsp;</div><div>Who is doing what?&nbsp;</div><div>New Log in information - VPN then hit Citrix for INOH users - communication will need to go out ASAP for this</div><div>Interface repointing</div><div><br></div> | INOH | 1061 Migration | 50 | Bradley Painter | Done | 2021-02-04T14:15:33.333Z | 2021-02-18T19:12:04.337Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3644 | Task | 3114 | Troubleshooting Not working on users machine |  |  |  |  | Hanh Tran | Done | 2021-02-04T14:19:54.19Z | 2021-02-24T14:24:48.913Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3647 | Task | 3626 | Migrate GSD 811 Process Data Pull |  |  |  |  | Bradley Painter | Done | 2021-02-04T14:32:13.463Z | 2021-02-19T15:02:04.7Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3655 | Task | 3306 | Grid & Map Refresh |  |  |  |  | Saud Ahmad | Done | 2021-02-05T14:18:28.727Z | 2021-02-24T12:38:05.32Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3657 | Task | 3533 | Waiting for DB Weekend (2/26) | [5 empty] | Done | 2021-02-05T14:25:25.263Z | 2021-02-27T22:28:43.743Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3685 | Task | 3436 | Wait for SE hot fix | [5 empty] | Done | 2021-02-12T14:15:23.817Z | 2021-02-22T13:42:16.743Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3688 | Task | 2943 | INOH Gas |  |  |  |  | Kelsey Mobley | Done | 2021-02-15T14:23:33.73Z | 2021-02-25T17:05:15.313Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3689 | Task | 2943 | INOH Electric |  |  |  |  | Kelsey Mobley | Done | 2021-02-15T14:23:42.043Z | 2021-02-25T17:05:17.67Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3691 | Task | 2943 | INOH DSO |  |  |  |  | Kelsey Mobley | Done | 2021-02-15T14:23:54.99Z | 2021-02-25T17:05:12.793Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3692 | Task | 2943 | INOH New Service Center | <div><ol style="box-sizing:border-box;outline:none;padding-left:40px;"><li style="box-sizing:border-box;">New Service Center</li><ol style="box-sizing:border-box;outline:none;padding-left:40px;list-style:lower-alpha;"><li style="box-sizing:border-box;outline:none;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="box-sizing:border-box;outline:none;">Please add Service Locations to the map so they can identify customer details on Electric Service drops</span></li><li style="box-sizing:border-box;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="box-sizing:border-box;">When identifying poles, they receive the error message below.</span></li><ol style="box-sizing:border-box;outline:none;padding-left:40px;"><li style="box-sizing:border-box;outline:none;margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="box-sizing:border-box;outline:none;">&quot;The requested operation failed. Try again later or inform your administrator&quot;</span></li></ol></ol></ol><br></div> |  |  |  | Kelsey Mobley | Done | 2021-02-15T14:24:02.757Z | 2021-02-25T17:05:10.353Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3694 | Task | 3643 | Meeting with GSD, Sys Admin, Dev Team |  |  |  |  | Bradley Painter | Done | 2021-02-15T14:25:41.373Z | 2021-02-18T14:23:30.03Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3699 | Task | 3768 | Discussion with Supply Chain on Final Plant List for ArcFM |  |  |  |  | Bradley Painter | Done | 2021-02-16T14:53:52.033Z | 2021-02-26T13:32:32.34Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3700 | Product Backlog Item |  | EIP - F/LOC Interface Description Update - 1102 | <div>Update FLOC interface to send FeederID data to SAP for the Circuit Description</div> | EIP; INOH | EIP | 10 | Bradley Painter | Done | 2021-02-17T00:11:15.1Z | 2021-02-26T21:49:55.233Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3701 | Task | 3700 | Update FLOC Interface to include FeederID |  |  |  |  | Bradley Painter | Done | 2021-02-17T00:11:29.443Z | 2021-02-19T15:23:20.72Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3703 | Product Backlog Item |  | EIP - Update CU Account Code Information | <div>Work with Property Accounting to make sure that all FERCs, Account Codes, Property Groups, and Retirement Units are in ArcFM for EIP Go-Live</div> | EIP; INOH | EIP | 10 | Bradley Painter | Done | 2021-02-17T00:13:20.197Z | 2021-02-26T13:36:28.81Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3704 | Task | 3703 | Work with Property Accounting Group and CU Administrators to identify changes/additions to Account Code Table |  |  |  |  | Bradley Painter | Done | 2021-02-17T00:13:44.263Z | 2021-02-26T13:32:24.22Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3706 | Product Backlog Item |  | EIP - Electric CU Labor Cost Issue |  | EIP; INOH | EIP | 30 | Bradley Painter | Done | 2021-02-17T16:36:07.417Z | 2021-02-26T13:36:25.173Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3707 | Task | 3706 | Identify the Electric CU labor costs to remove in order to support Crew Type Hourly Rate Mapping | <div>Need to identify and clear the individual labor costs on Electric CUs in the CU items table so that the Crew Type Hourly Rate will be sent for this value.&nbsp;</div><div><br></div><div>Create two files, one for before changes and one after updates in case we need to revert the change in the future</div> |  |  |  | Bradley Painter | Done | 2021-02-17T16:36:40.36Z | 2021-02-24T14:22:15.76Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3709 | Task | 3577 | Create ticket with SE |  |  |  |  | Christopher Thomas | Done | 2021-02-18T14:18:04.947Z | 2021-03-05T16:51:53.753Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3711 | Product Backlog Item |  | 10.6.1 - DINOP GDBM Configuration and Setup | <div><ol style="margin-bottom:0in;"><li>DINOP Configuration (Sys Admin/DEV)</li><ol style="margin-bottom:0in;"><li>DINOP GeoServer (GISECDCGEO01)</li><ol style="margin-bottom:0in;"><li>Configure GDBM for INOH (Kelsey)</li><li>Configure TIBCO for INOH (Vlad)</li><li>Validate PAM access (Kelsey/Vlad)</li></ol></ol></ol><br></div> | INOH | 1061 Migration | 50 | Kelsey Mobley | Done | 2021-02-18T15:20:24.777Z | 2021-03-01T15:04:46.567Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3712 | Task | 3711 | Configure GDBM for INOH |  |  |  |  | Kelsey Mobley | Done | 2021-02-18T15:20:53.897Z | 2021-02-19T20:08:34.18Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3713 | Task | 3725 | Configure TIBCO for INOH |  |  |  |  | Krejcirik, C_Vlad | Done | 2021-02-18T15:21:12.897Z | 2021-03-01T15:58:18.847Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3714 | Product Backlog Item |  | 10.6.1 - DINOP FME Configuration and Setup | <div><ol style="margin-bottom:0in;"><li>FME Production Server (GISECDCFME01)</li><ol style="margin-bottom:0in;"><li>Setup and configure INOH production batch Jobs (Brad)</li></ol></ol><br></div> | INOH | 1061 Migration | 50 | Bradley Painter | Done | 2021-02-18T15:21:58.18Z | 2021-02-26T20:59:18.087Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3715 | Task | 3714 | Setup and configure INOH production batch Jobs |  |  |  |  | Bradley Painter | Done | 2021-02-18T15:22:21.447Z | 2021-02-26T20:59:14.037Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3716 | Product Backlog Item |  | 10.6.1 - G.Viewer Production Site (8) Setup | <div><span style="text-align:left;display:inline !important;">Setup and configure INOH production batch Jobs</span><br></div> | INOH | 1061 Migration | 50 | Kelsey Mobley | Done | 2021-02-18T15:23:30.353Z | 2021-03-10T13:46:50.333Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3718 | Product Backlog Item |  | Modify Pole Attachment Script for Reporting | <div><img src="https://dev.azure.com/centerpoint-GIS/dd41b79d-1665-4c55-9863-175bd4cd1d78/_apis/wit/attachments/af959d2a-7991-45bd-8688-4b92937c34ea?fileName=image.png" alt=Image><br></div> | ELECTRIC; PAGIS; UNPLANNED | Business | 20 | Christopher Thomas | Done | 2021-02-18T15:51:11.99Z | 2021-02-24T00:06:12.42Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC |  | UNPLANNED
3720 | Task | 3716 | INOH Gas |  |  |  |  | Kelsey Mobley | Done | 2021-02-18T19:15:04.753Z | 2021-03-10T13:46:44.61Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3721 | Task | 3716 | INOH Electric |  |  |  |  | Kelsey Mobley | Done | 2021-02-18T19:15:23.75Z | 2021-03-10T13:46:38.233Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3722 | Task | 3716 | INOH New Service Center |  |  |  |  | Kelsey Mobley | Done | 2021-02-18T19:15:35.183Z | 2021-03-10T13:46:22.677Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3723 | Task | 3716 | INOH DSO |  |  |  |  | Kelsey Mobley | Done | 2021-02-18T19:15:43.97Z | 2021-03-10T13:46:29.523Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3725 | Product Backlog Item |  | 10.6.1 - DINOP TIBCO Configuration and Setup | <div>10.6.1 - DINOP GDBM Configuration and Setup<br></div> | INOH | 1061 Migration | 50 | Krejcirik, C_Vlad | Done | 2021-02-18T19:20:15.523Z | 2021-03-01T15:58:33.713Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3727 | Task | 3626 | Create Model to Extract USIC Data for GSD |  |  |  |  | Bradley Painter | Done | 2021-02-19T14:14:19.58Z | 2021-02-19T15:02:12.037Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3730 | Task | 3711 | Configure Add-In Folder |  |  |  |  | Kelsey Mobley | Done | 2021-02-19T18:04:55.947Z | 2021-03-01T15:04:43.51Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3732 | Task | 2970 | User Testing - Karen | [5 empty] | Done | 2021-02-22T14:21:59.14Z | 2021-02-25T14:24:19.607Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3736 | Task | 3433 | Positioning of Info Pop up Window and UI |  |  |  |  | Saud Ahmad | Done | 2021-02-23T14:02:08.917Z | 2021-02-26T14:17:43.323Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3737 | Task | 3433 | Loading layers slow |  |  |  |  | Saud Ahmad | Done | 2021-02-23T14:02:32.853Z | 2021-02-25T14:16:28.453Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3738 | Task | 3433 | Run ADA compatibility |  |  |  |  | Saud Ahmad | Done | 2021-02-23T14:02:52.623Z | 2021-03-01T14:16:05.52Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3741 | Task | 3743 | Emergency Change Ticket for field Length change |  |  |  |  | Saud Ahmad | Done | 2021-02-23T14:17:40.707Z | 2021-02-24T14:16:16.103Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3742 | Task | 3357 | Updating user & password for script add configuration for table |  |  |  |  | Christopher Thomas | Done | 2021-02-23T14:19:49.73Z | 2021-02-24T14:20:48.153Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3743 | Product Backlog Item |  | Production Issue: Premise registry error |  | HOU; UNPLANNED | Business |  | Saud Ahmad | Done | 2021-02-23T14:20:53.57Z | 2021-02-24T14:29:57.53Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  |  | UNPLANNED
3745 | Task | 3569 | User Testing - Karen & Joe | [5 empty] | Done | 2021-02-23T14:29:22.04Z | 2021-03-02T15:03:03.407Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3748 | Product Backlog Item |  | EIP - CU Admin Tool - UAT Feedback | <div>Work with CU administrators on CU Admin tool UAT</div> | EIP; INOH | EIP | 30 | Bradley Painter | Done | 2021-02-23T14:48:49.37Z | 2021-02-26T21:50:09.337Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3749 | Task | 3748 | Discuss and Compile UAT results and Action items |  |  |  |  | Bradley Painter | Done | 2021-02-23T14:49:06.737Z | 2021-02-26T21:50:05.867Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3751 | Task | 3357 | Re-Publish Service |  |  |  |  | Chen Liang | Done | 2021-02-24T14:21:10.607Z | 2021-02-24T19:11:41.71Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3753 | Task | 3577 | Investigate proposed Schneider approach on new installer |  |  |  |  | Christopher Thomas | Done | 2021-02-24T14:28:43.44Z | 2021-03-01T14:21:40.743Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3755 | Product Backlog Item |  | Underground Locator Extraction Automation | <div>Automate&nbsp;Underground Locator Extraction </div> | GAS; HOU | Data Extraction |  | William Robertson Jr | Done | 2021-02-24T14:33:28.803Z | 2021-03-01T18:08:41.483Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | GAS
3758 | Task | 3755 | Add IN/OH UG Locator Export |  |  |  |  | William Robertson Jr | Done | 2021-02-24T15:01:21.923Z | 2021-02-26T14:29:59.4Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3759 | Task | 3755 | Automate UG Locator Export for other regions |  |  |  |  | William Robertson Jr | Done | 2021-02-24T15:06:50.593Z | 2021-02-25T14:23:45.673Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3760 | Product Backlog Item |  | EIP - Crew Type Cleanup | <div>Clean up Crew Type Values per CU Administrators</div> | EIP; INOH | EIP | 10 | Bradley Painter | Done | 2021-02-24T16:09:25.833Z | 2021-02-25T15:03:13.02Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3761 | Task | 3760 | Clean up Crew Type Table in DINOQ | <div>File provided by Ed Cooper on 2/24/2021</div> |  |  |  | Bradley Painter | Done | 2021-02-24T16:09:40.91Z | 2021-02-25T15:03:06.84Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3768 | Product Backlog Item |  | EIP - Multiple CU Material costs and Plants in ArcFM | <div>Work with Supply chain and CU Administrators to decide how to handle the Plant/Material Costs in ArcFM.&nbsp;</div> | EIP; INOH | EIP | 50 | Bradley Painter | Done | 2021-02-24T17:25:00.913Z | 2021-02-26T13:36:26.967Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3769 | Task | 3768 | Verify how plant is used by EAI | <div>Nat verified via attached email that EAI is not using any plant information that is sent from ArcFM.&nbsp; Therefore, the only function of the Plant in ArcFM is to carry the cost for the material to send to EAI.&nbsp;</div> |  |  |  | Bradley Painter | Done | 2021-02-24T17:26:21.313Z | 2021-02-24T20:39:06.52Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3772 | Task | 3768 | Validate path to move forward with only one plant in ArcFM | <div>Set Default plant to 7001 for all EDM fields.&nbsp;&nbsp;</div><div><br></div><div>Set Default in Cost Factor Table</div><div><br></div><div>Update DIP</div> |  |  |  | Bradley Painter | Done | 2021-02-24T17:31:58.377Z | 2021-02-26T13:32:52.64Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3774 | Product Backlog Item |  | Production Issue: SAP Substation Validation and Missing Address |  | ELECTRIC; HOU; UNPLANNED | SAP-GIS |  | Goddard, Susan C. | Done | 2021-02-24T17:37:42.727Z | 2021-02-27T22:28:16.85Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC |  | UNPLANNED
3775 | Task | 3774 | Investigate missing meter numbers |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T17:39:16.647Z | 2021-02-24T18:05:14.693Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3776 | Task | 3774 | Investigate missing address | <div>Karen reported the missing address in Address_DB, which was required for GLN tie<span style="">.&nbsp;&nbsp;</span></div><div><ul><li><span style="">18610 Fern St 3 / Data Correction<br></span></li></ul><span style=""></span></div> |  |  |  | Goddard, Susan C. | Done | 2021-02-24T17:41:06.023Z | 2021-02-24T18:05:22.69Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3777 | Product Backlog Item |  | DDS - Test Map Package Extraction from SDE | <div>Test GSI DDS Extraction directly from SDE</div><div><ul><li>Extract System <span style="display:inline !important;">data</span></li><li>Extract Regional data (<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">Baytown)</span></li><li>Create Mobile Map Package&nbsp;</li></ul></div> | ELECTRIC; HOU | Data Extraction |  | Goddard, Susan C. | Started | 2021-02-24T17:49:53.193Z | 2021-03-10T19:34:21.13Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC
3778 | Task | 3777 | Extract System data |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T17:50:15.447Z | 2021-02-24T18:04:23.503Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3779 | Task | 3777 | Extract Regional data for Baytown |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T17:54:46.83Z | 2021-02-24T18:04:28.423Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3780 | Product Backlog Item |  | Test the Gas Report changes for DOT report | <div>assist testing&nbsp;&nbsp;the Gas Report changes for DOT report in Citrix&nbsp;</div> |  | Business |  | Goddard, Susan C. | Done | 2021-02-24T17:56:24.107Z | 2021-02-24T18:04:15.633Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3782 | Product Backlog Item |  | Investigate Rec & Post Special Version on 1061 | <div>Rec &amp; Post Special Version threw an error on database connections.&nbsp;<br></div> |  | 1061 Migration |  | Goddard, Susan C. | Done | 2021-02-24T18:01:28.513Z | 2021-02-24T18:03:41.683Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3783 | Task | 3782 | Investigate the db connection error |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T18:01:43.51Z | 2021-02-24T18:03:34.713Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3785 | Task | 3774 | Investigate the meter number failed to update |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T18:06:50.28Z | 2021-02-27T22:27:57.9Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3786 | Product Backlog Item |  | Production Issue: AL04: GLN# not being updated in T_EMD_ESI table |  |  | SAP-GIS |  | Goddard, Susan C. | Done | 2021-02-24T18:09:17.477Z | 2021-02-25T14:41:34.623Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3787 | Task | 3786 | Investigate missing meter numbers |  |  |  |  | Saud Ahmad | Done | 2021-02-24T18:10:27.55Z | 2021-02-25T14:30:46.257Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3788 | Task | 3786 | Investigate missing meter numbers |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T18:10:37.133Z | 2021-02-25T14:30:48.67Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3793 | Task | 3578 | Create gas meter Data Model |  |  |  |  | William Robertson Jr | Done | 2021-02-25T14:18:50.923Z | 2021-02-25T14:19:02.28Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3794 | Task | 3774 | Verify Nightly file |  |  |  |  | Goddard, Susan C. | Done | 2021-02-25T14:19:34.887Z | 2021-03-02T15:02:47.113Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3795 | Task | 2970 | Deploy during maintenance weekend | [5 empty] | Done | 2021-02-25T14:24:36.707Z | 2021-02-27T22:29:00.51Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3796 | Task | 3755 | Run extract against Landbase |  |  |  |  | William Robertson Jr | Done | 2021-02-25T14:28:22.813Z | 2021-03-01T14:21:04.947Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3797 | Task | 3774 | investigate invalid GLN |  |  |  |  | Goddard, Susan C. | Done | 2021-02-25T14:30:31.967Z | 2021-03-02T15:02:50.533Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3799 | Task | 3578 | Install Hana SAP on 10.6 machine |  |  |  |  | Goddard, Susan C. | Done | 2021-02-25T18:02:45.447Z | 2021-03-01T14:18:15.05Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3806 | Task | 3577 | Install new components from SE |  |  |  |  | Christopher Thomas | Done | 2021-02-26T14:30:52.203Z | 2021-03-02T14:53:38.477Z | CNP.GIS | CNP.GIS\Sprint 21.02-B