## current_iteration
Id | WorkItemType | Parent | Title | Description | Tags | ValueArea | BusinessValue | AssignedTo | State | CreatedDate | ChangedDate | AreaPath | IterationPath | Operation | Region | Planned
2331 | Product Backlog Item |  | EIP - User Migration to New SAP Employee Numbers | <div>New to develop &nbsp;a process to migrate our users from their current IDs to the new SAP IDs for EIP go live<br></div> | EIP; INOH | EIP | 3 | Kelsey Mobley | Done | 2020-10-21T13:33:43.853Z | 2021-03-12T15:15:25.377Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
2544 | Product Backlog Item |  | Production Issue: Unable to move the Construction Site map on android phone |  | HOU | Mobile | 40 | Christopher Thomas | Started | 2020-10-26T16:51:10.68Z | 2021-03-08T15:05:58.943Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3370 | Product Backlog Item |  | GIS-SAP data cleanup: Remove blank space around ESIID, meter No and Account No. | <div>Remove blank space around ESIID, meter No and Account No. from SAP_&lt;tables&gt; and the downstream versioned/non-versioned tables.&nbsp;<br></div> | HOU | System | 20 | Saud Ahmad | Done | 2021-01-09T00:00:16.69Z | 2021-03-12T16:01:14.97Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3404 | Product Backlog Item | 3941 | Add the Vendor field to WOTS Complete QC turnaround | <div>Add the VENDOR field to WOTS QC complete turnaround interface<br></div><div> </div><div><br> </div> | HOU; WOTS | WOTS | 26 | Hanh Tran | Started | 2021-01-13T21:31:55.28Z | 2021-03-10T23:13:06.063Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3413 | Task | 3698 | ArcFM Mobile Validation | <div><ol style="margin-bottom:0in;"><li>ArcFM Mobile Testing and Configuration</li><ol style="margin-bottom:0in;"><li>User Acceptance Testing to be conducted in early March - (DEV/GSD)</li><ol style="margin-bottom:0in;"><li>Test OnBase on ArcFM Mobile (DEV/GSD)</li><li>Review Multiuser setting in ArcFM Mobile – (DEV)</li></ol></ol></ol></div> |  |  |  | Kelsey Mobley | Done | 2021-01-15T14:17:57.033Z | 2021-03-10T20:05:50.43Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3456 | Task | 3436 | Rebuild and test the build Items(Auto Updater, Validation Rules, Login, Editor Extension Context Menus etc) |  |  |  |  | C_Varalakshmi Srinivasan | In Progress | 2021-01-19T15:22:01.027Z | 2021-03-02T14:49:29.01Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3436 | Product Backlog Item |  | 10.6.1 - ArcFM 10.6.1a SP2 Sanity Check - HOU |  | HOU | 1061 Migration | 30 | C_Varalakshmi Srinivasan | Started | 2021-01-17T18:50:56.46Z | 2021-02-24T15:13:41.03Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3463 | Task | 3436 | Rebuild and test .Net Tools and Addin |  |  |  |  | C_Varalakshmi Srinivasan | In Progress | 2021-01-19T15:24:50.907Z | 2021-03-12T15:34:22.13Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3473 | Task | 3436 | Rebuild and test Standalones |  |  |  |  | Subhankar, C_Baidya X | In Progress | 2021-01-19T15:30:41.563Z | 2021-03-02T14:49:43.667Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3497 | Task | 3697 | Create FME Workbench to Update Material Costs |  |  |  |  | Bradley Painter | In Progress | 2021-01-20T19:20:00.93Z | 2021-03-10T18:46:05.257Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3571 | Product Backlog Item |  | Database: Unused domains cleanup (2nd Pass) |  | HOU | System |  | William Robertson Jr | Started | 2021-02-01T18:12:47.007Z | 2021-03-05T13:08:54.397Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3575 | Task | 2331 | Connect with Rakesh on User Migration | <div>Rakesh - DBA</div> |  |  |  | Kelsey Mobley | Done | 2021-02-01T20:54:21.027Z | 2021-03-12T15:12:01.57Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3590 | Task | 3571 | Delete unassigned domains that are duplicates |  |  |  |  | William Robertson Jr | In Progress | 2021-02-02T15:19:21.447Z | 2021-02-24T17:32:07.093Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3604 | Task | 3578 | Code change to complete data loading | <br><div><br> </div> |  |  |  | Goddard, Susan C. | In Progress | 2021-02-02T15:23:46.867Z | 2021-03-12T15:32:51.597Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3578 | Product Backlog Item |  | Place OK Gas Service Lines | <div><span style="display:inline !important;">Discussion Topics:&nbsp;</span><br style="box-sizing:border-box;"><ul style="box-sizing:border-box;padding:0px 0px 0px 40px;"><li style="box-sizing:border-box;">Require attributes from Gas Meters?&nbsp; - Not at the first run&nbsp; </li><li style="box-sizing:border-box;">Need abandoned service line or main? - No at this time </li><li style="box-sizing:border-box;">Need bell hole, redundant features? - No at this time </li><li style="box-sizing:border-box;">Use features from DOT report. They are actual assets. - YES!&nbsp; </li> </ul><br> </div> | GAS; HOU | Business | 60 | Goddard, Susan C. | Started | 2021-02-02T14:10:16.98Z | 2021-03-02T16:13:16.91Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | GAS
3607 | Task | 3578 | Testing |  |  |  |  | Goddard, Susan C. | To Do | 2021-02-02T15:24:45.347Z | 2021-03-02T14:46:36.44Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3608 | Task | 3578 | Testing GIS support/Nanda? |  |  |  |  | Goddard, Susan C. | To Do | 2021-02-02T15:25:15.497Z | 2021-03-02T14:46:41.103Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3609 | Task | 3578 | documentation |  |  |  |  | Goddard, Susan C. | To Do | 2021-02-02T15:25:24.64Z | 2021-03-02T14:46:45.94Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3623 | Task | 3436 | Verify Gas Leaks |  |  |  |  | Goddard, Susan C. | Done | 2021-02-02T15:51:17.23Z | 2021-03-12T17:59:27.83Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3624 | Task | 3436 | Verify SectionTrace interfaces |  |  |  |  | Hanh Tran | In Progress | 2021-02-02T15:51:19.097Z | 2021-03-12T15:35:58.52Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3629 | Task | 3436 | Verify AIS_Missing_50_Plus interface |  |  |  |  | Christopher Thomas | Done | 2021-02-03T13:20:44.277Z | 2021-03-02T19:14:35.187Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3645 | Task | 3353 | Update in Production March 12 |  |  |  |  | Hanh Tran | To Do | 2021-02-04T14:21:27.153Z | 2021-03-12T22:53:49.14Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3353 | Product Backlog Item |  | Code SharePoint List Location Change | <div><div style="margin:0px 0in 0.000133333px;font-size:11pt;font-family:Calibri, sans-serif;"><b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">From:</span></b><span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;"> Gastineau, David E &lt;<a href="mailto:david.gastineau@centerpointenergy.com">david.gastineau@centerpointenergy.com</a>&gt; <br style=""><br style=""></span><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Hi Hanna,</p></div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I just wanted to share with you that I am looking into migrating the Code SharePoint List from its current location to the Teams Site that I use for code clearance so I can use the new Microsoft Lists functionality and build Power BI dashboards with the data and not worry about messing up the backend code of the site (which I have done before).</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I am not ready to make the transition just yet, we are going to build a test list to see if it works. Once we know it works, we’ll make the migration. A few questions:</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><ul style="margin-bottom:0in;margin-top:0in;"> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">What would you need to make this transition? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Is this a big ask? </span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Or is it relatively simple?</span></li></ul><br></div> | HOU | Business | 13 | Hanh Tran | Started | 2021-01-05T16:10:41.21Z | 2021-03-04T14:27:38.07Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3667 | Task | 3404 | Meet with Jacob (3/4) to clarify the requirements |  |  |  |  | Hanh Tran | Done | 2021-02-09T15:07:01.923Z | 2021-03-05T14:25:01.89Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3671 | Task | 3436 | Windows Service testing: CNP.Electric.CustomerService |  |  |  |  | Goddard, Susan C. | Done | 2021-02-10T16:28:43.987Z | 2021-03-12T15:34:48.103Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3672 | Task | 3306 | Wait for Jacob's approval |  |  |  |  | Chen Liang | Done | 2021-02-10T17:38:57.603Z | 2021-03-10T14:26:37.637Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3306 | Product Backlog Item |  | Migrate RED Approval to HTML5 | <div><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Jacob:&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><br></p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">Here are my review comments.</p><ol style="margin-bottom:0in;margin-top:0in;" start=1 type=1> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Outage RED Production Layers are not turned on by default</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">“Push to PROD” button missing within Outage RED widget.</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Change “Red” to “RED”</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Unable to test due to lack of Substation and Circuit Restoration data</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Legend Widget should be always on. May be split half way thru between Layers and Legend widgets?</span></li> <li style="margin:0in 0in 0.0001pt 0.5in;font-size:11pt;font-family:Calibri, sans-serif;margin-left:0in;"><span style="">Report widget not working correctly. Outage numbers are not showing by City.</span></li></ol><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">&nbsp;</p><p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;">I will setup a meeting to go over these in detail.</p><br></div> | HOU | Outage | 40 | Saud Ahmad | Done | 2021-01-04T23:18:37.827Z | 2021-03-10T17:19:45.677Z | CNP.GIS | CNP.GIS\Sprint 21.02-B
3674 | Task | 3436 | Interface Testing - TreeTrim: CautionPointsGeocoder |  |  |  |  | Christopher Thomas | Done | 2021-02-10T18:07:39.733Z | 2021-03-08T14:24:05.693Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3677 | Task | 3353 | Add New Field - URD consultant |  |  |  |  | Hanh Tran | Done | 2021-02-10T19:27:39.8Z | 2021-03-12T15:37:08.457Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3678 | Task | 3353 | Populate SP List: zipcode and URD consultant |  |  |  |  | Hanh Tran | In Progress | 2021-02-10T19:28:20.107Z | 2021-03-02T14:51:10.447Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3680 | Task | 3353 | GChange Documentation |  |  |  |  | Hanh Tran | Done | 2021-02-10T19:29:21.29Z | 2021-03-12T15:37:53.507Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3697 | Product Backlog Item |  | EIP - CU Material Cost Updates |  | EIP; INOH | EIP | 30 | Bradley Painter | Started | 2021-02-15T19:54:53.03Z | 2021-03-10T15:03:44.437Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3698 | Product Backlog Item |  | 10.6.1 - ArcFM Mobile Testing and Validation | <div><ol style="margin-bottom:0in;"><li>ArcFM Mobile Testing and Configuration</li><ol style="margin-bottom:0in;"><li>User Acceptance Testing to be conducted in early March - (DEV/GSD)</li><ol style="margin-bottom:0in;"><li>Test OnBase on ArcFM Mobile (DEV/GSD)</li><li>Review Multiuser setting in ArcFM Mobile – (DEV)</li></ol></ol></ol><br></div> | INOH | 1061 Migration | 50 | Kelsey Mobley | Done | 2021-02-15T20:38:49.45Z | 2021-03-12T13:59:06.23Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3726 | Product Backlog Item |  | Migrate Gas Report tool to 1061 |  | GAS; HOU | 1061 Migration |  | Subhankar, C_Baidya X | Done | 2021-02-18T22:39:04.207Z | 2021-03-10T14:32:00.41Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS
3734 | Task | 3726 | Migrate Gas Report tool code from 10.2.1 to to 1061 |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-02-23T13:16:02.543Z | 2021-03-05T14:26:33.407Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3735 | Task | 3726 | Unit test |  |  |  |  | Subhankar, C_Baidya X | Done | 2021-02-23T13:16:33.977Z | 2021-03-08T14:25:07.283Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3744 | Product Backlog Item |  | Rectify Test environment to match Prod for outage apps |  | HOU; UNPLANNED | System |  | Saud Ahmad | Done | 2021-02-23T14:21:50.387Z | 2021-03-10T14:31:47.883Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  |  | UNPLANNED
3746 | Task | 3744 | Identify the gaps between test env and prod env |  |  |  |  | Saud Ahmad | Done | 2021-02-23T14:36:56.837Z | 2021-03-10T14:16:30.22Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3752 | Task | 3114 | Meet with Jacob on deploying MimsReplica on production machines |  |  |  |  | Hanh Tran | Done | 2021-02-24T14:23:08.18Z | 2021-03-02T15:17:59.843Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3114 | Product Backlog Item |  | Allow multiple Fileservers to download the MIMSReplica | <div><span style="background-color:rgb(255, 255, 0);display:inline !important;">To be completed by Jan 18th</span><br></div><div>MIMSReplicaCopy copies the replica files from one file server. This is for the users to download data for GO!Sync.&nbsp;</div><div><ul><li>Change the config file to accommodate multiple download sources.&nbsp;</li><li>Add UI to select which file server they download files from.&nbsp;</li><li>Download one selected fileserver to the local drive&nbsp;&nbsp;<br></li></ul></div> | EIP; HOU; INOH | Data Extraction | 70 | Hanh Tran | Started | 2020-12-03T13:12:50.887Z | 2021-03-10T14:33:13.913Z | CNP.GIS | CNP.GIS\Sprint 21.02-B |  | INOH
3754 | Product Backlog Item |  | EIP - Transition to Approval Pending | <div>Designers would like for the design to close in ArcFM when they transition a design from In Design to Approval pending.&nbsp; Once the transition is complete they want the design to automatically close, which is how it is currently configured in Process Framework today.&nbsp;</div> | EIP; INOH | EIP | 10 | Kelsey Mobley | Done | 2021-02-24T14:29:59.463Z | 2021-03-08T15:04:30.977Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3756 | Task | 3754 | Update Process Framework Transition in DINOQ |  |  |  |  | Kelsey Mobley | Done | 2021-02-24T14:34:56.07Z | 2021-03-02T19:05:47.123Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3762 | Product Backlog Item |  | EIP - Send for Cost Report | <div>Change Process Framework Transition from Send for Report to Send for Cost Report and update EIP DIP accordingly.&nbsp;</div> | EIP; INOH | EIP | 3 | Kelsey Mobley | Done | 2021-02-24T17:15:15.247Z | 2021-03-08T15:04:33.15Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3763 | Task | 3762 | Update Process Framework Transition in DINOQ |  |  |  |  | Kelsey Mobley | Done | 2021-02-24T17:15:52.313Z | 2021-03-02T19:05:59.933Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3771 | Task | 3697 | Update Material Incremental Workbench | <div>Update workbench to ignore plants/consolidate plants</div> |  |  |  | Bradley Painter | Done | 2021-02-24T17:29:58.253Z | 2021-03-12T13:58:33.567Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3789 | Task | 3726 | Verify the Tool |  |  |  |  | Goddard, Susan C. | Done | 2021-02-24T19:20:29.84Z | 2021-03-10T14:23:09.33Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3790 | Product Backlog Item |  | WOTS: Test FileNET SO Interface | <div>Test FileNET Interfaces: SO&nbsp;<br></div> | HOU; WOTS | System |  | Subhankar, C_Baidya X | Started | 2021-02-24T19:22:26.867Z | 2021-03-10T19:23:03.433Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3791 | Task | 3777 | Retesting with Nasir to investigate database performance |  |  |  |  | Goddard, Susan C. | Done | 2021-02-25T14:17:04.877Z | 2021-03-09T14:26:48.39Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3777 | Product Backlog Item |  | DDS - Test Map Package Extraction from SDE | <div>Test GSI DDS Extraction directly from SDE</div><div><ul><li>Extract System <span style="display:inline !important;">data</span></li><li>Extract Regional data (<span style="font-size:11.0pt;font-family:&quot;Calibri&quot;,sans-serif;">Baytown)</span></li><li>Create Mobile Map Package&nbsp;</li></ul></div> | ELECTRIC; HOU | Data Extraction |  | Goddard, Susan C. | Started | 2021-02-24T17:49:53.193Z | 2021-03-10T19:34:21.13Z | CNP.GIS | CNP.GIS\Sprint 21.02-B | ELECTRIC
3792 | Task | 3578 | Load Gas Meters in OKT | <div>Loaded the same data as QA to TEST.&nbsp; </div> |  |  |  | Goddard, Susan C. | Done | 2021-02-25T14:18:30.903Z | 2021-03-04T14:21:48.603Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3801 | Task | 3697 | Update DIP to Clean Up Plant Affecting Items | <div><div style="box-sizing:border-box;">Set Default plant to 7001 for all EDM fields.&nbsp;&nbsp;</div><div style="box-sizing:border-box;"><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;">Set Default in Cost Factor Table</div><div style="box-sizing:border-box;"><br style="box-sizing:border-box;"></div><div style="box-sizing:border-box;">Update DIP</div><br></div> |  |  |  | Bradley Painter | Done | 2021-02-26T13:33:50.733Z | 2021-03-10T18:46:07.677Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3802 | Task | 3436 | Verify Gas Meter |  |  |  |  | Goddard, Susan C. | Done | 2021-02-26T14:04:33.84Z | 2021-03-12T15:34:51.77Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3803 | Task | 3433 | Deploy the new outage tracker to the TEST environment for GSD to verify |  |  |  |  | Saud Ahmad | Done | 2021-02-26T14:19:54.903Z | 2021-03-09T14:16:22.63Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3433 | Product Backlog Item |  | Fix outage tracker map pan issue on Android | <p style="margin:0in 0in 0.0001pt;font-size:11pt;font-family:Calibri, sans-serif;"><span style="font-size:11pt;">Saud:&nbsp;</span><span style="font-size:11pt;">First is switching the current version to the higher version. I have tested this and mostly impacts the TOC and books marks widget. Most of the other functionalities work fine with minor GUI issues. I can try to incorporate the newer version of TOC compatible with higher versions of API within the current framework. If that works we will have resolution to this issue sooner. I will need a week’s time to try it out.</span><br></p><br> | ELECTRIC; HOU | Outage | 80 | Saud Ahmad | Done | 2021-01-17T15:54:22.03Z | 2021-03-09T14:54:21.9Z | CNP.GIS | CNP.GIS\Sprint 21.01-B | ELECTRIC
3804 | Task | 3114 | Test Mobile Copy on user machine in OK 3/11 |  |  |  |  | Mary Torres | Done | 2021-02-26T14:27:51.657Z | 2021-03-11T14:23:17.473Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3805 | Task | 3353 | Service call receives permission error |  |  |  |  | Hanh Tran | Done | 2021-02-26T14:29:31.333Z | 2021-03-04T14:27:33.89Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3807 | Product Backlog Item |  | 10.6.1 - Operational 811/Locate Tables | <div>Follow-up with Aaron Hills about required Operational Locate tables that will be needed in DINOP</div> | INOH | 1061 Migration | 50 | Kelsey Mobley | Started | 2021-02-26T22:14:16.073Z | 2021-03-10T15:03:16.207Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3809 | Product Backlog Item |  | WOTS: Test FileNET Interface |  | HOU; WOTS | WOTS |  | Aaron Miller | Started | 2021-02-27T22:49:16.213Z | 2021-03-05T16:55:53.57Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3812 | Product Backlog Item |  | 10.6.1 - GSD DINOP Installer Testing and Validation | <div>Validate Installer</div><div>Validate Add-In Folder</div> | INOH | 1061 Migration | 10 | Aaron Miller | Started | 2021-03-01T15:04:30.567Z | 2021-03-10T20:59:38.96Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3813 | Product Backlog Item |  | EIP - Test WOTS/ODIP Connection | <div>Hanna will provide WOTS test connection, need to have someone on the SAP side test sending Work Orders over and Validate in WOTS</div> | EIP; INOH | EIP | 50 | Hanh Tran | Done | 2021-03-01T15:14:16.153Z | 2021-03-12T13:58:16.437Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3814 | Task | 3813 | Provide WOTS test connection for SAP/ODIP/WOTS Work Order Testing |  |  |  |  | Hanh Tran | Done | 2021-03-01T15:14:56.88Z | 2021-03-12T13:57:58.133Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3816 | Task | 3812 | Validate Add-in folder is in correct directory |  |  |  |  | Aaron Miller | In Progress | 2021-03-01T15:23:19.687Z | 2021-03-10T14:56:27.577Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3817 | Task | 3807 | Add necessary table | <div>TIBCO_811_LOCATE tables.&nbsp; Talk with Vlad to see if there are any other tables that need to be built in DINOP </div> |  |  |  | Kelsey Mobley | In Progress | 2021-03-01T15:23:59.09Z | 2021-03-12T15:12:32.377Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3819 | Task | 3812 | Have new Installer Run on Test Version of Citrix |  |  |  |  | Aaron Miller | Done | 2021-03-01T15:44:11.44Z | 2021-03-10T14:56:30.53Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3821 | Task | 3114 | Add logic to delete Zip folder after extracting (Data Copy) |  |  |  |  | Hanh Tran | Done | 2021-03-01T17:23:14.637Z | 2021-03-05T14:21:07.34Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3822 | Product Backlog Item |  | EIP - SAP Equipment Number Loading for Gas Assets | <div>SAP will be converting several gas assets into SAP Equipment.&nbsp; These Equipment numbers must be bulk populated in GIS.&nbsp; &nbsp;We will need to make sure that we have a process to do this and that the new equipment has the appropriate SAP_EQUIPMENT_NUMBER Field, Text 18 </div><div><br> </div><div><span>IN FILE BUT NO FEATURE CLASS<br></span><div>SEPARATOR - NO FEATURE CLASS IN GIS<br> </div><div>STRAINER - NO FEATURE CLASS IN GIS<br> </div><div>FILTER - NO FEATURE CLASS IN GIS<br> </div><div>FILTER SEPARATOR - NO FEATURE CLASS IN GIS<br> </div><div><br> </div><div>GAS FEATURE CLASSES<br> </div><div>PRESSURE MONITOR - GAS.Chart<br> </div><div>ODORIZERSY - GAS.Odorizer<br> </div><div>HEATER - GAS.LineHeater<br> </div><div>RECTIFIER - GAS.CPRectifier<br> </div><div>CURB VALVE - GAS.GasService<br> </div><div>CP DECOUPLER - GAS.CPDecoupler<br> </div><div>BOND NON-CRT - GAS.CPBondJunction<br> </div><div>BOND CRT - GAS.CPBondJunction<br> </div><div>CASING - GAS.GasPipeCasing<br> </div><div>OVER PRESSURE DEVICE - GAS.ReliefValve<br> </div><div>ODORIZER - GAS.Odorizer<br> </div><div>REGULATOR - GAS.GasRegulator<br> </div><div>TEST POINT - GAS.CPTestPoint<br> </div><span>VALVE - GAS.GasValve</span><br> </div> | EIP; INOH | EIP | 30 | Bradley Painter | Done | 2021-03-02T14:02:24.523Z | 2021-03-12T13:59:04.043Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3824 | Task | 3822 | Create FME Workbench create the data necessary for the bulk loading |  |  |  |  | Bradley Painter | Done | 2021-03-02T14:03:16.553Z | 2021-03-03T21:42:22.767Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3825 | Task | 3578 | Request for Jacob to review a portion of service line |  |  |  |  | Goddard, Susan C. | Done | 2021-03-02T14:38:06.357Z | 2021-03-09T14:18:49.113Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3827 | Product Backlog Item |  | Knowledge Transfer: Facility Buffer Polygon |  | GAS; HOU | Data Extraction |  | William Robertson Jr | Done | 2021-03-02T15:15:52.853Z | 2021-03-12T15:47:10.023Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS
3833 | Task | 3744 | Outage Tracker | <div><span lang=EN><p align=LEFT dir=LTR>OUTAGE_TRACKER_OEP_ALL service not drawing features - JP </p><p align=LEFT dir=LTR>Once Gene resolves the issue can switch to tgis.centerpointenergy.com </p></span><span lang=EN><p align=LEFT dir=LTR><br> </p></span><br> </div> |  |  |  | Saud Ahmad | Done | 2021-03-02T15:31:09.97Z | 2021-03-09T14:17:56.73Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3834 | Task | 3744 | Red Approval | <div><span lang=EN>OUTAGE_RED_COMPARISON_FLEX map service to be created in test environment by GIS Sys admin group. </span><br> </div> |  |  |  | Saud Ahmad | Done | 2021-03-02T15:33:06.76Z | 2021-03-03T14:18:19.55Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3835 | Task | 3827 | Demo the Python scripts that are used to create Buffer Polygons. |  |  |  |  | William Robertson Jr | Done | 2021-03-02T15:33:25.01Z | 2021-03-12T15:46:59.723Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3836 | Task | 3571 | Create updated spreadsheet of Unassigned Domains in all DBs |  |  |  |  | William Robertson Jr | Done | 2021-03-02T15:34:40.8Z | 2021-03-03T14:21:40.747Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3837 | Task | 3744 | Outage Reporting |  |  |  |  | Saud Ahmad | Done | 2021-03-02T15:34:43.983Z | 2021-03-09T14:18:04.28Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3838 | Task | 3370 | Verify GIS Full Syn process |  |  |  |  | Saud Ahmad | Done | 2021-03-02T15:36:36.703Z | 2021-03-11T14:17:00.873Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3839 | Task | 3370 | Verify GIS NRT process |  |  |  |  | Saud Ahmad | Done | 2021-03-02T15:36:59.11Z | 2021-03-12T15:31:20.2Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3840 | Task | 3790 | Modify code to fix the mismatch in result with production |  |  |  |  | Subhankar, C_Baidya X | In Progress | 2021-03-02T15:37:17.747Z | 2021-03-10T14:23:33.013Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3841 | Task | 3433 | ADA - Label for TOC |  |  |  |  | Saud Ahmad | Done | 2021-03-02T15:37:35.977Z | 2021-03-08T14:16:48.873Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3842 | Task | 3790 | Unit test and verify result with production |  |  |  |  | Subhankar, C_Baidya X | To Do | 2021-03-02T15:37:37.53Z | 2021-03-02T15:39:47.487Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3845 | Task | 3809 | Troubleshoot/Update Code |  |  |  |  | Aaron Miller | In Progress | 2021-03-02T15:41:25.707Z | 2021-03-09T14:23:06.053Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3846 | Task | 3433 | ADA - Alternate text for IMG tags |  |  |  |  | Saud Ahmad | Done | 2021-03-02T15:41:37.98Z | 2021-03-05T14:16:25.647Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3847 | Task | 3809 | Unit test/verify results |  |  |  |  | Aaron Miller | In Progress | 2021-03-02T15:41:54.083Z | 2021-03-10T14:22:10.117Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3850 | Task | 2544 | Add new library to site |  |  |  |  | Christopher Thomas | Done | 2021-03-02T15:51:39.843Z | 2021-03-05T14:23:49.78Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3851 | Task | 2544 | Test UI after adding library |  |  |  |  | Christopher Thomas | In Progress | 2021-03-02T15:52:28.103Z | 2021-03-05T14:24:05.573Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3854 | Task | 2544 | Code walk-through |  |  |  |  | Saud Ahmad | Done | 2021-03-02T16:07:18.387Z | 2021-03-05T14:23:42.15Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3855 | Task | 2544 | Code walk-through |  |  |  |  | Christopher Thomas | Done | 2021-03-02T16:07:35.213Z | 2021-03-05T14:23:40.883Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3857 | Product Backlog Item |  | G.Viewer: Add Surcharge Project Poly to MN G.Viewer | <div><span style="color:steelblue;font-size:12px;font-weight:bold;">HD0000525056</span> </div><div>Kellie Berryhill </div><div><br> </div><div>Add Surchargeproject_py to G.Viewer within the Active Facilities Service </div><div>Layer file can be found below </div><div><a href="\\ecdceng02\BU\ENG\dgn\gis\techsup\Layers\MGCP\G_Land_Prod">\\ecdceng02\BU\ENG\dgn\gis\techsup\Layers\MGCP\G_Land_Prod</a><br> </div> | GAS; HOU; MN; UNPLANNED | GViewer | 20 | William Robertson Jr | Done | 2021-03-02T18:59:08.163Z | 2021-03-13T22:11:44.583Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS |  | UNPLANNED
3858 | Task | 3857 | Add the layer to the Minnesota Active Facilities map service. |  |  |  |  | William Robertson Jr | Done | 2021-03-03T12:54:58.61Z | 2021-03-09T14:27:57.06Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3859 | Task | 3857 | Publish the Minnesota Active Facilities map service. |  |  |  |  | William Robertson Jr | Done | 2021-03-03T12:56:50.83Z | 2021-03-09T14:28:01.803Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3860 | Task | 3857 | Refresh the Minnesota G.Viewer website. |  |  |  |  | Christopher Thomas | Done | 2021-03-03T12:57:32.42Z | 2021-03-10T14:24:37.72Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3861 | Task | 3862 | Troubleshoot Intermittent Issue of Data from County not being correct | <div><ul><li>Data from county is not correct </li> </ul> </div> |  |  |  | Saud Ahmad | In Progress | 2021-03-03T14:16:32.373Z | 2021-03-12T15:30:52.45Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3862 | Product Backlog Item | 3928 | Production Issue: Outage Tracker County Report Issue |  | ELECTRIC; HOU; UNPLANNED | Outage |  | Saud Ahmad | Started | 2021-03-03T14:17:54.323Z | 2021-03-12T16:03:31.98Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | ELECTRIC |  | UNPLANNED
3864 | Product Backlog Item |  | Production Issue: Gas DataPrep tool not working on all DBs but Houston |  | GAS; HOU; UNPLANNED | Data Extraction |  | C_Varalakshmi Srinivasan | Done | 2021-03-03T14:34:22.24Z | 2021-03-12T16:03:04.57Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS |  | UNPLANNED
3865 | Product Backlog Item |  | 10.6.1 - Investigate "Unknown Error" in DDS Migration Tool for work order 93985128 |  | ELECTRIC; HOU; UNPLANNED | 1061 Migration |  | C_Varalakshmi Srinivasan | Started | 2021-03-03T14:36:33.443Z | 2021-03-10T14:33:00.3Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | ELECTRIC |  | UNPLANNED
3866 | Task | 3864 | Troubleshoot the stoner tool |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-03-03T14:38:23.09Z | 2021-03-04T14:23:04.467Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3867 | Task | 3865 | Troubleshoot the DDS Migration Tool |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-03-03T14:48:11.633Z | 2021-03-05T14:18:28.157Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3870 | Product Backlog Item |  | Add Domain Value to GAS_FACILITY_OWNER (OK) | <div>&nbsp;<span style="color:steelblue;font-size:12px;font-weight:bold;">HD0000525072</span> </div><div>Katherine Graham </div><div><br> </div><div><span>Please add “CenterPoint Energy Intrastate Pipeline. LLC” as an option to the domain for GAS_FACILITY_OWNER (GAS_OWNER_OPERATOR) in the Oklahoma Database<br>-I am not sure if I selected the correct database above</span> </div><div><br> </div><div><br> </div> | GAS; HOU; UNPLANNED | Business | 20 | William Robertson Jr | Done | 2021-03-04T13:19:10.077Z | 2021-03-13T22:11:33.277Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS |  | UNPLANNED
3873 | Task | 3578 | Reviewing Services |  |  |  |  | Goddard, Susan C. | In Progress | 2021-03-04T14:22:18.07Z | 2021-03-04T14:22:41.86Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3874 | Task | 3864 | GSD/User Testing | [5 empty] | Done | 2021-03-04T14:23:19.233Z | 2021-03-12T15:33:06.77Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3875 | Task | 3353 | Update code to use Different Credential |  |  |  |  | Hanh Tran | Done | 2021-03-04T14:27:54.913Z | 2021-03-11T14:24:26.613Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3876 | Task | 2544 | ADA Compliance Testing |  |  |  |  | Christopher Thomas | To Do | 2021-03-04T14:30:27.297Z | 2021-03-05T14:23:55.557Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3877 | Task | 3857 | Meet with Brad and Chen on Changes |  |  |  |  | William Robertson Jr | Done | 2021-03-04T14:33:32.363Z | 2021-03-09T14:27:49.297Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3878 | Product Backlog Item |  | Add Domain Value to Town_CD in G_CITY_py Feature Class | <div><span>Chad Hilton</span> </div><div><span><span style="color:steelblue;font-size:12px;font-weight:bold;">HD0000525074</span> </span> </div><div><span><br></span> </div><div><span>Please add domain value, M99200, to attribute TOWN_CD in G_City_py feature class in Minnesota GIS production database. </span><br> </div> | GAS; HOU; UNPLANNED | Business | 20 | William Robertson Jr | Done | 2021-03-04T21:43:02.06Z | 2021-03-13T22:11:18.34Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS |  | UNPLANNED
3879 | Task | 3870 | Add domain value to GAS_OWNER_OPERATOR in Oklahoma production |  |  |  |  | William Robertson Jr | Done | 2021-03-05T12:43:42.337Z | 2021-03-09T14:23:44.347Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3880 | Task | 3878 | Add domain value M99200 in Minnesota Test |  |  |  |  | William Robertson Jr | Done | 2021-03-05T13:19:03.653Z | 2021-03-05T14:22:17.527Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3881 | Task | 3870 | Add domain value to GAS_OWNER_OPERATOR in Oklahoma Test |  |  |  |  | William Robertson Jr | Done | 2021-03-05T13:19:42.21Z | 2021-03-05T14:23:07.85Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3882 | Task | 3865 | DDS Team working with Electric DM Team |  |  |  |  | Goddard, Susan C. | Done | 2021-03-05T14:18:45.827Z | 2021-03-12T15:33:39.96Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3883 | Task | 3436 | Add Geocoders to MetroD |  |  |  |  | Christopher Thomas | Done | 2021-03-05T14:20:09.257Z | 2021-03-08T14:24:34.223Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3884 | Task | 3878 | GSD Testing |  |  |  |  | Douglas Kjellander | Done | 2021-03-05T14:22:22.687Z | 2021-03-08T14:23:06.687Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3885 | Task | 3870 | GSD Testing |  |  |  |  | Douglas Kjellander | Done | 2021-03-05T14:23:11.763Z | 2021-03-08T14:23:20.587Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3888 | Task | 3404 | Add vendor column to AGING_QC_COMP_ORDERS Table |  |  |  |  | Hanh Tran | Done | 2021-03-05T16:46:50.473Z | 2021-03-09T14:30:15.78Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3889 | Task | 3404 | Create 6 views ( 2 gas, 2 electric, 2 landbase) |  |  |  |  | Hanh Tran | Done | 2021-03-05T16:47:28.757Z | 2021-03-10T14:25:57.477Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3890 | Task | 3404 | Create stored procedure to populate AGING_QC_COMP_ORDERS And QC_COMP_TURNAROUND_GAS_ORDERS |  |  |  |  | Hanh Tran | In Progress | 2021-03-05T16:47:45.957Z | 2021-03-10T14:26:22.723Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3891 | Task | 3404 | Update interface project code |  |  |  |  | Hanh Tran | To Do | 2021-03-05T16:48:09.01Z | 2021-03-05T16:48:38.7Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3893 | Product Backlog Item |  | EIP - DR1 Pre Tech Cutover Tasks |  | EIP; INOH | EIP | 50 |  | Done | 2021-03-08T13:29:08.14Z | 2021-03-12T13:58:23.797Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3894 | Task | 3353 | Research potentially installing new SDK package |  |  |  |  | Hanh Tran | Done | 2021-03-08T14:20:28.86Z | 2021-03-11T14:24:14.507Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3896 | Task | 3878 | Implement into Prod |  |  |  |  | William Robertson Jr | Done | 2021-03-08T14:23:13.68Z | 2021-03-09T14:23:31.44Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3898 | Task | 2544 | Investigate the javascript issue causing blank maps |  |  |  |  | Christopher Thomas | In Progress | 2021-03-08T15:34:51.217Z | 2021-03-11T02:43:06.75Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3899 | Task | 3436 | Verify MaximoToWOTS interface |  |  |  |  | Hanh Tran | Done | 2021-03-08T15:43:03.617Z | 2021-03-09T14:20:42.437Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3904 | Task | 2544 | review outage tracker code |  |  |  |  | Christopher Thomas | In Progress | 2021-03-09T14:24:24.55Z | 2021-03-11T14:28:00.74Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3905 | Task | 3777 | Request access to data for GSI contractors |  |  |  |  | Chen Liang | Done | 2021-03-09T14:27:00.39Z | 2021-03-12T15:43:47.243Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3906 | Task | 3777 | Looking at extracting directly from PRO |  |  |  |  | Goddard, Susan C. | Done | 2021-03-09T14:27:13.74Z | 2021-03-12T15:45:25.83Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3907 | Task | 3404 | Knowledge Share w/ Varu |  |  |  |  | C_Varalakshmi Srinivasan | Done | 2021-03-09T14:29:02.86Z | 2021-03-11T14:30:17.993Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3908 | Task | 3404 | Knowledge Share w/ Varu |  |  |  |  | Hanh Tran | Done | 2021-03-09T14:29:35.95Z | 2021-03-11T14:30:20.15Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3909 | Task | 3893 | Brad |  |  |  |  | Bradley Painter | Done | 2021-03-09T15:46:57.447Z | 2021-03-12T13:57:46.567Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3910 | Task | 3893 | Kelsey |  |  |  |  | Kelsey Mobley | Done | 2021-03-09T15:47:10.8Z | 2021-03-12T13:58:21.18Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3911 | Task | 3893 | Chris |  |  |  |  | Christopher Thomas | Done | 2021-03-09T15:47:32.127Z | 2021-03-12T13:57:43.4Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3912 | Task | 3893 | Hanna |  |  |  |  | Hanh Tran | Done | 2021-03-09T15:47:45.05Z | 2021-03-12T13:57:41.273Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3913 | Task | 3893 | Chen |  |  |  |  | Chen Liang | Done | 2021-03-09T15:48:04.167Z | 2021-03-10T18:45:42.7Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3914 | Task | 2331 | Develop process to get user match from active directory and update PX XML |  |  |  |  | Kelsey Mobley | Done | 2021-03-09T19:28:35.32Z | 2021-03-09T19:28:46.573Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3918 | Task | 3353 | Meeting with Chen to Troubleshoot Connection Issue |  |  |  |  | Hanh Tran | Done | 2021-03-10T14:21:39.457Z | 2021-03-11T14:24:09.557Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3919 | Task | 3777 | Meeting with GSI on 3/11 |  |  |  |  | Goddard, Susan C. | Done | 2021-03-10T14:24:10.057Z | 2021-03-12T15:44:12.737Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3921 | Product Backlog Item |  | Add SURCHARGE_PROJECT_PY to MN G. Viewer Where Am I | <div><span style="display:inline !important;">Add Surchargeproject_py to G.Viewer in MN G. Viewer</span><br> </div> | GAS; MN; UNPLANNED | GViewer |  | William Robertson Jr | Started | 2021-03-10T14:29:09.843Z | 2021-03-11T13:54:14.677Z | CNP.GIS | CNP.GIS\Sprint 21.03-A | GAS |  | UNPLANNED
3924 | Task | 3921 | Add SURCHARGE_PROJECT_PY to the Minnesota Where Am I map service |  |  |  |  | William Robertson Jr | Done | 2021-03-10T16:04:12.163Z | 2021-03-12T15:40:19.76Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3925 | Task | 3921 | Publish the updated Minnesota Where AM I |  |  |  |  | William Robertson Jr | Done | 2021-03-10T16:17:19.873Z | 2021-03-12T15:40:23.343Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3926 | Task | 3921 | Refresh the Minnesota website |  |  |  |  | Christopher Thomas | In Progress | 2021-03-10T16:17:49.54Z | 2021-03-12T15:40:28.31Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3927 | Product Backlog Item |  | EIP - New EIP Oracle Users and Permissions | <div>Compile List of all required new Oracle Users and Permissions that will need to be created for EIP. We can use this list and create/test the users in production before Business Cut-Over Weekend.&nbsp; </div> | EIP; INOH | EIP | 50 | Kelsey Mobley | Started | 2021-03-10T16:51:12.05Z | 2021-03-12T15:15:36.993Z | CNP.GIS | CNP.GIS\Sprint 21.03-A |  | INOH
3942 | Task | 3114 | Deploy MS/LA for testing |  |  |  |  | Mary Torres | To Do | 2021-03-11T14:23:42.017Z | 2021-03-11T14:23:47.38Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3968 | Task | 3927 | Identify Oracle Users and Permissions that are necessary for EIP |  |  |  |  | Kelsey Mobley | In Progress | 2021-03-12T15:15:06.963Z | 2021-03-12T15:15:34.223Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3970 | Task | 3865 | GSI Team looking into the global ID changes | [5 empty] | In Progress | 2021-03-12T15:33:53.647Z | 2021-03-12T22:57:13.503Z | CNP.GIS | CNP.GIS\Sprint 21.03-A
3971 | Task | 3353 | Populate with consultant name and phone # |  |  |  |  | Hanh Tran | To Do | 2021-03-12T15:38:33.813Z | 2021-03-12T22:53:30.25Z | CNP.GIS | CNP.GIS\Sprint 21.03-A